## Rollup (hidden)
Summary of Capital Projects
Data Updated Through 12/02/19
Cabinet Wide Rollup
| Total Current Budget | Total Unobligated | Total Cash Balance
| #REF! | #REF! | #REF!
Project Management | #REF! | #REF! | #REF!
Heritage Land | #REF! | #REF! | #REF!
Maintenance Pool | #REF! | #REF! | #REF!
Various | #REF! | #REF! | #REF!
| Total Current Budget | Total Unobligated | Total Cash balance
HWMF | #REF! | #REF! | #REF!
Dept | Fund | Fund Name | Active Status | Current Budget | Unobligated | Cash Balance | Project Initiation Date | EEC Contacts | Estimated Completion Date | Notes
129 | C1H6 | HWMF-Various Projects | Active | 7975600 | 358760.92 | 128461.68 | 1993-04-23 | Hughes, Larry
129 | C2PV | HWMF-KY Tie & Timber | Active | #REF! | #REF! | #REF! | 2006-06-02
129 | C2PW | HWMF-Kim's Dry Cleaners | Active | #REF! | #REF! | #REF! | 2006-06-03 | Hancock, Nathan
129 | C4Q7 | HWMF-Louisville Environmental Services | Active | 507700 | 13968.9 | 39130.13 | 2008-05-09 | Hancock, Nathan
129 | C52F | HWMF-Distler Brickyard | Active | 204871.93 | 23700 | 23700 | 2009-04-15
129 | C52G | HWMF-Distler Farm | Active | 159577.99 | 7140 | 7140 | 2009-04-15
129 | C5GL | HWMF - Lees Lane Project | Active | 135000 | 59832.13 | 59832.13 | 2010-06-01 | Uhlenbruch, Christopher
129 | C6AM | HWMF - Jackson's Pronto Cleaners | Active | 46575 | 10748.01 | 11909.01 | 2016-12-01 | Kirby, Jim
129 | C6D2 | HWMF-Familee Laundry Phase 2 | Active | #REF! | #REF! | #REF! | 2012-05-18 | Brown, Eric
129 | C7TQ | HWMF-Former Bill's Quality Cleaners | Active | 65000 | 43552.4 | 43552.4 | 2014-12-11 | Brown, Eric
129 | C7TR | HWMF-Parrish Avenue | Active | 197400 | 63150.26 | 65742.48 | 2014-12-15 | Brown, Eric
129 | C7TS | HWMF-Miracle Dry Cleaners | Active | 161900 | 13004.5 | 13004.5 | 2014-11-11 | Grow, Jeff
129 | C83A | HWMF-Former West Point Bank Property | Active | 195000 | 122359.3 | 22359.3 | 2015-12-17 | Hancock, Nathan
129 | C83G | HWMF-Clark and Riggs | Active | 18900 | 9403 | 9403 | 2015-11-11 | Hancock, Nathan
129 | C83H | HWMF-West KY Wildlife Area Burn Site | Active | #REF! | #REF! | #REF! | 2015-11-11 | Hancock, Nathan
129 | C8SC | HWMF-A&S Tools and Gage | Active | #REF! | #REF! | #REF! | 2017-08-17
129 | C8X0 | HWMF-Wiley Property | Active | 75000 | 42050 | 42050 | 2018-02-26 | Brown, Eric
129 | C8ZG | HWMF-Former Henry Vogt Machine Co | Active | #REF! | #REF! | #REF! | 2018-06-05 | Hancock, Nathan
129 | C95Q | HWMF-Southern Wood Treatment-Long's Lane Op. & Maint Phase | Active | 455900 | 368305 | 377902.5 | 2018-08-10 | Brown, Eric
129 | C9FV | HWMF-Sam Meyers Formal Wear | Active | 70000 | 55241.62 | 70000 | 2019-09-28 | Cary, Brent
129 | C9FW | HWMF-Former Hartco | Active | #REF! | #REF! | #REF! | 2019-09-28 | Hancock, Nathan
129 | C9FX | HWMF-Mount Sterling City Landfill | Active | 132600 | 42321.61 | 42321.61 | 2019-09-28 | Polly, Derek
129 | C9G5 | HWMF-Jefferson Memorial Forest | Active | 20000 | 20000 | 20000 | 2019-09-28 | Hancock, Nathan
| Total Current Budget | Total Unobligated | Total Cash balance
PRIDE | #REF! | #REF! | #REF!
Dept | Fund | Fund Name | Active Status | Current Budget | Unobligated | Cash Balance | Project Initiation Date | EEC Contacts | Estimated Completion Date | Notes
129 | C5Y8 | PRIDE-Mt. Sterling Landfill | Active | #REF! | #REF! | #REF! | 2011-05-24
129 | C62D | PRIDE - Johnson County Landfill | Active | #REF! | #REF! | #REF! | 2011-08-09 | Melton, Ken
129 | C70B | PRIDE - Butler Co. Landfill | Active | #REF! | #REF! | #REF! | 2014-04-21 | Melton, Ken
129 | C713 | PRIDE-Mercer County Landfill | Active | #REF! | #REF! | #REF! | 2014-06-09
129 | C714 | PRIDE-Well Abandonment at Closed Landfills | Active | #REF! | #REF! | #REF! | 2014-06-09
129 | C7UQ | PRIDE-Bullitt County Historic Landfill | Active | #REF! | #REF! | #REF! | 2015-02-12 | Melton, Ken
129 | C7VX | PRIDE-Foothills Sanitary Landfill | Active | #REF! | #REF! | #REF! | 2015-03-27 | Melton, Ken
129 | C7XC | PRIDE-McCracken County Historic Landfill | Active | #REF! | #REF! | #REF! | 2015-05-05 | Melton, Ken
129 | C84E | PRIDE - Covington Landfill | Active | 6883200 | #REF! | #REF! | 2016-02-17 | Melton, Ken
129 | C84L | PRIDE - Goodridge Avenue | Active | #REF! | #REF! | #REF! | 2016-02-17 | Melton, Ken
129 | C8CW | PRIDE- City of Cadiz | Active | #REF! | #REF! | #REF! | 2016-07-19
129 | C8J1 | PRIDE-Northwest-Central Site Characterization | Active | 1450000 | #REF! | #REF! | 2017-01-13 | Melton, Ken
129 | C8J4 | PRIDE- South Central Site Characterization | Active | 35472.65 | #REF! | #REF! | 2017-01-23 | Melton, Ken
129 | C9GR | PRIDE-Butler County Landfill II | Active | #REF! | #REF! | #REF! | 2019-10-01 | Melton, Ken
| Total Current Budget | Total Unobligated | Total Cash balance
UST | #REF! | #REF! | #REF!
Dept | Fund | Fund Name | Active Status | Current Budget | Unobligated | Cash Balance | Project Initiation Date | EEC Contacts | Estimated Completion Date | Notes
129 | C5PZ | LUST - Clinton Oil & Tire Emergency | Active | #REF! | #REF! | #REF! | 2010-07-06
129 | C7WV | LUST - Logsdon Property | Active | #REF! | #REF! | #REF! | 2015-04-22 | Voisard, Vicki
129 | C8GG | LUST-Mike Winchester Site | Active | #REF! | #REF! | #REF! | 2016-10-19 | Smith, Adam |  | Requested an additional $500,000 in apporpriation this week
129 | C8LX | LUST-Norb Nie | Active | #REF! | #REF! | #REF! | 2017-03-03 | Albright, Michael
129 | C9AL | LUST-Garner Quick Stop | Active | #REF! | #REF! | #REF! | 2019-02-26 | Hickerson, Kelly |  | Will be requesting $600,000 in apporpriation within the next week.
129 | C9AM | LUST-Interstate Brands Warehouse | Active | #REF! | #REF! | #REF! | 2019-02-26 | Smith, Adam |  | Will be requesting $1,000,000 in apporpriation within the next week.
129 | C9AZ | LUST-Sportman Market | Active | #REF! | #REF! | #REF! | 2019-03-04 | Highley, Alan |  | Will be requesting $500,000 in apporpriation within the next week.
129 | C9BA | LUST-H&T Stop & Go | Active | #REF! | #REF! | #REF! | 2019-03-04 | Highley, Alan |  | Will be requesting $500,000 in apporpriation within the next week.
| Total Current Budget | Total Unobligated | Total Cash balance
Maxey Flats | #REF! | #REF! | #REF!
Dept | Fund | Fund Name | Active Status | Current Budget | Unobligated | Cash Balance | Project Initiation Date | EEC Contacts | Estimated Completion Date | Notes
129 | C6BK | Maxey Flats Cap | Active | #REF! | #REF! | #REF! |  | Webb, Jeff | Perpetual
| Total Current Budget | Total Unobligated | Total Cash balance
SODR | #REF! | #REF! | #REF!
Dept | Fund | Fund Name | Active Status | Current Budget | Unobligated | Cash Balance | Project Initiation Date | EEC Contacts | Estimated Completion Date | Notes
129 | C1GH | SODR-Willisburg Lake Dam-Washington County | Active | #REF! | #REF! | #REF! | 2000-07-01
129 | C1GK | SODR Bullock Pen Lake Dam | Active | #REF! | #REF! | #REF! |  | Wells, Gary
129 | C55B | SODR-Scenic Lake Dam | Active | #REF! | #REF! | #REF! | 2009-06-24
129 | C55C | SODR-Beech Creek Dam | Active | #REF! | #REF! | #REF! | 2009-06-24 | Wells, Gary
129 | C93R | State-Owned Dam Repair - 2018-2020 | Active | #REF! | #REF! | #REF!
| Total Current Budget | Total Unobligated | Total Cash balance
MISC-DEP | #REF! | #REF! | #REF!
Dept | Fund | Fund Name | Active Status | Current Budget | Unobligated | Cash Balance | Project Initiation Date | EEC Contacts | Estimated Completion Date | Notes
129 | C562 | A.L. Taylor Site | Active | #REF! | #REF! | #REF! |  |  | Perpetual
129 | C5J2 | Solid Waste - Jones Landfill | Active | #REF! | #REF! | #REF! | 2010-06-22
129 | C8RG | WTTF-Rubberized Asphalt Testing | Active | #REF! | #REF! | #REF! | 2017-08-01
129 | C84J | DEP Central Lab Modifications | Active | #REF! | #REF! | #REF! | 2018-04-24
126 | C852 | EEC Storage Building | Active | #REF! | #REF! | #REF! | 2016-03-17
126 | C9HM | Grede Foundries Site | Active | #REF! | #REF! | #REF! | 2019-10-01
| Total Current Budget | Total Unobligated | Total Cash balance
KHLCF | #REF! | #REF! | #REF!
Dept | Fund | Fund Name | Active Status | Current Budget | Unobligated | Cash Balance | Project Initiation Date | EEC Contacts | Estimated Completion Date | Notes
140 | C0N9 | KHLCF-Adv. Land Acquisition Cost | Active | #REF! | #REF! | #REF! | 1996-08-15 | Frazier, Brent
126 | C1G8 | KHLCF | Active | #REF! | #REF! | #REF! | 2009-04-08
128 | C1J1 | KHLCF-Adv Costs for Land Acquisition | Active | #REF! | #REF! | #REF! | 1996-08-28
140 | C8YA | KHLCF-Green River-Timberlake Tract | Active | #REF! | #REF! | #REF! | 2018-04-24 | Lillpop, Josh & Frazier, Brent
140 | C8YB | KHLCF-Blanton Forest-Coleman Tract | Active | #REF! | #REF! | #REF! | 2018-04-24 | Lillpop, Josh & Frazier, Brent
140 | C8YC | KHLCF-Archer Benge-Hyslope Tract | Active | #REF! | #REF! | #REF! | 2018-04-24
140 | C8YD | KHLCF-Archer Benge-University of Cumberlands Tract | Active | #REF! | #REF! | #REF! | 2018-04-24
140 | C8YJ | KHLCF-Rockcress Hills-Gatewood Tract | Active | #REF! | #REF! | #REF! | 2018-04-24
140 | C97Z | KHLCF-Drennon Creek SNP | Active | #REF! | #REF! | #REF! | 2018-10-25 | Lillpop, Josh & Frazier, Brent
140 | C980 | KHLCF-Red River-Gritter Ridge | Active | #REF! | #REF! | #REF! | 2018-10-25 | Lillpop, Josh & Frazier, Brent
140 | C981 | KHLCF-Eastview Barrens-Ashlock Tract | Active | #REF! | #REF! | #REF! | 2018-10-25 | Lillpop, Josh & Frazier, Brent
| Total Current Budget | Total Unobligated | Total Cash balance
Maintenance Pool | #REF! | #REF! | #REF!
Dept | Fund | Fund Name | Active Status | Current Budget | Unobligated | Cash Balance | Project Initiation Date | EEC Contacts | Estimated Completion Date | Notes
126 | C93Q | Maintenance Pool - 2018-2020 | Active | #REF! | #REF! | #REF!
140 | C68Z | MP-OKNP Maintenance Equipment | Active | #REF! | #REF! | #REF! | 2012-03-06 | Frazier, Brent
140 | C8F7 | MP-Hi Lewis Pine Barrens SNP Abandoned Dwelling | Active | #REF! | #REF! | #REF! | 2016-09-07 | Napier, Kyle
140 | C96E | MP-OKNP-Venon Douglas Parking Lot Gravel and Grading | Active | #REF! | #REF! | #REF! | 2018-08-24
140 | C96F | MP-OKNP-Tom Dorman Parking Area | Active | #REF! | #REF! | #REF! | 2018-08-24
140 | C96G | MP-OKNP-Red River Natural Area House and Barn Demo | Active | #REF! | #REF! | #REF! | 2018-08-24
140 | C96H | MP-OKNP-Blanton Forest Kiosk Bridge Trail Maint. | Active | #REF! | #REF! | #REF! | 2018-08-27
129 | C96D | MP-Maxey Flats Repair/Replace Office Building Roofs | Active | #REF! | #REF! | #REF! | 2018-08-24
128 | C5CJ | MP-North Eastern District | Active | #REF! | #REF! | #REF! | 2010-03-03
128 | C63V | MP-JPRN Soil Replacement | Active | #REF! | #REF! | #REF! | 2011-09-16
128 | C6SB | MP-JPRN Various Projects | Active | #REF! | #REF! | #REF! | 2013-05-14
128 | C8L9 | MP-Bert T. Combs Various Projects | Active | #REF! | #REF! | #REF! | 2017-03-09
128 | C8S4 | MP-State Forest Road & Parking Area Maintenance | Active | #REF! | #REF! | #REF! | 2017-08-02
128 | C96C | MP-JPRN Top Pruner | Active | #REF! | #REF! | #REF! | 2018-08-24

## CALE McKee Edits (hidden)
Updated as of 2/5/2024
Allotments
|  |  | Appropriation |  |  |  | Unobligated
Status | CALE- Superfund Sites | Cash Balance | Current Budget | Encumbrance | Expenditures | Unobligated | E701 | E703 | E166 | Total | Notes
Active | Capital Budget Line Item | 2742279.73 | 2824000 | 0 | 81720.27 | 2742279.73 | 214425 | 1480405 | 47449.73 | 1742279.73 | $1.8 loaded 7/2/2022. $1M loaded 7/5/2023.
|  | Total Expenditures | E701 | E703 | E166 | Notes
Active | 415 Sites with no Viable PRP & RCRA Generator Ranking Project | 62618.87 | 9575 | 3670 | 49373.87 | Testing and Samples
| Big B Cleaners, Hopkins Co- AI# 38519-Soil Characterization |  |  |  | 2500
| SFB-UST Oil Removal - Douglas Nunn Property AI# 174392 |  |  | 3670
| Beacon Environmental-Characterization-Soil Samples-Non IT |  |  |  | 2645
| Coronet Dry Cleaners, Jefferson County - AI# 47888 |  |  |  | 2950
| Coronet Dry Cleaners AI# 47888 - Jefferson County |  |  |  | 1094.4
| SFB - PSG Sample Collection and Analysis - Multiple Sites |  |  |  | 3370
| On the Spot Utility Services |  | 1600
| On the Spot Utility Services |  | 975
| On the Spot Utility Services |  | 1175
| On the Spot Utility Services |  | 1775
| SFB - PSG Sample Collection and Analysis - Multiple Sites |  |  |  | 1505
| SFB - PSG Sample Collection and Analysis - Multiple Sites |  |  |  | 2655
| SFB - PSG Sample Collection and Analysis - Multiple Sites |  |  |  | 1990
| BEACON - UNRETURNED SAMPLER FEE |  |  |  | 50
| SFB - PSG Sample Collection and Analysis - Multiple Sites |  |  |  | 840
| SFB - PSG Sample Collection and Analysis - Multiple Sites |  |  |  | 1530
| SFB - PSG Sample Collection and Analysis - Multiple Sites |  |  |  | 4315
| BEACON - UNRETURNED SAMPLER FEE |  |  |  | 50
| On the Spot Utility Services |  | 825
| On the Spot Utility Services |  | 650
| SFB - PSG Sample Collection and Analysis - Multiple Sites |  |  |  | 300
| SFB - PSG Sample Collection and Analysis - Multiple Sites |  |  |  | 2195
| On the Spot Utility Services |  | 825
| SFB Livermore Plating Project - sampling |  |  |  | 1002.21
| SFB Livermore Plating Project - sampling |  |  |  | 5816.46
| On the Spot Utility Services |  | 925
| SFB - PSG Sample Collection and Analysis - AI# 51529 Plant Cut-Off Road Area of Concern Calvert City |  |  |  | 4980
| On the Spot Utility Services |  | 825
| SFB - PSG Sample Collection and Analysis - Multiple Sites |  |  |  | 3345
| SFB - PSG Sample Collection and Analysis - Multiple Sites |  |  |  | 1810
| Former Peter Pan Dry Cleaner AI# 48115 - Sampling Event |  |  |  | 1921.2
| Hart's Laundry Project AI#37970 - Sample Event |  |  |  | 1004.6
| SFB - PSG Sample Collection and Analysis - Multiple Sites |  |  |  | 1300
| SFB - PSG Sample Collection and Analysis - Multiple Sites |  |  |  | 205
Complete | Rough River Youth Ranch (petro) | 15925 | 0 | 15925 | 0
| Rough River Youth Ranch, McDaniels Co. - AI# 107622 |  |  | 15925
Active | National Linen (ALSCO) | 0 | 0 | 0 | 0 | Estimate of $400k, pending selection of contractor. Set up in eComm
Active | Dorsey Plaza
Active | Mt Sterling Landfill |  |  |  |  | Construction could be $1m
Active | Lees Lane (NPL) |  |  |  |  | Monitoring only
Active | Leitchfield Cleaners |  |  |  |  | Investigation complete
Active | Kings Cleaners |  |  |  |  | Cannot access property
Active | Parrish Avenue |  |  |  |  | Will use CALE for remediation. Ready for Design
Active | Bowie Coal Washing plant in Estill Co |  |  |  |  | ERT handled first incident has been referred to Superfund Branch
Charges to projects NOT on the Orig CALE list
C7TQ | HWMF- Former Bill's Quality Cleaners | 3176.4 | 0 | 0 | 3176.4
| Quality Dry Cleaners AI#39175 Sample Analysis |  |  |  | 1462.9
| SFB - Quality Dry Cleaners - Marshall County - AI# 39175 |  |  |  | 1462.9
| Quality Dry Cleaners AI#39175 Sample Analysis-Expedited TAT |  |  |  | 250.6
| Other CALE Projects Not Active | Cost | Notes
| Former Standard Metals | 75000 | Corrective Action
| Hi-Acres Shopping Center | 60000 | Corrective Action
| Statewide Properties (petro) | 10000 | Characterization
| Barrel Services | 20000 | Characterization
| Saylor Battery Systems | 80000 | Characterization and Cleanup (Haz. Waste Site)
| York Properties(petro) | 10000 | Characterization
| Livermore Brass & Silver Shop | 200000 | Characterization, Corrective

## $71 Million
|  | $71 Million HJR 56 |  |  |  |  | As of 12/11/25
Fund | Sub Fund | Project Name | Project Budget (Appropriation) | Expenditures | Bid Status | Estimated Completion | PARKS - Notes
CBD0 |  | Building Systems Repair & Replacement Pool | 6883200
| CB74 | CO-Multi Park Building Automated Systems Updates | 6283200 | 969843
|  | Barren River HVAC Replacement | 0 |  | In Construction | 2026-03-01 | The building automation controls and chiller replacement project is currently under construction. Good progress is being made by general contractor and sub-contractors. Regular construction progress meetings are being held.
|  | General Butler BAS System Replacement |  |  | In Design | 2026-10-15 | The design phase is 95% complete. They are downgrading scope to fit the funding. Ready to advertise documents should be ready by Jan 15, 2026.
| CBE8 | Building Systems Upgrades- Various Parks | 600000 | 37886.51
|  | Jenny Wiley-Cooling Tower Replacements |  | 461267.22 | Completed | 2025-07-15 | Jenny Wiley cooling tower replacement project is now complete. Project replaced the cooling towers at both the lodge and convention center. Units replaced were thirty years old and failing.
CBD1 |  | Life Safety System Upgrades and Replacement Pool | 3000000
|  | Dale Hollow-Oak1-Elevator Upgrade | 80800 | 80800 | Completed | 2025-11-05 | Elevator project is complete. Invoice was sent to Financial Operations on November 12 for payment processing.
|  | Jenny Wiley-Lodge-Elevator Repairs | 56800 | 52096 | Completed | 2025-11-17 | Elevator project is complete. Vendor had to make adjustments to invoice as not all work was deemed necessary once repairs were completed. Invoice sent for payment on December 3, 2025.
|  | John James Audubon-Business Off-Repair Sprinkler System | 22760.88 |  | Completed |  | Construction complete.
|  | Door Locking Systems | 800000 | 742712.5
|  | GB-Visitor Management System (Door Locking System) |  |  | Completed | 2025-01-31 | All guest room locks have been installed and new access system is online.
|  | RR-Visitor Management System (Door Locking System) |  |  | Substantial Completion |  | All guest room locks have been installed and new access system is online.
|  | NB-Visitor Management System (Door Locking System) |  |  | Substantial Completion |  | All guest room locks have been installed and new access system is online.
|  | JW-Visitor Management System (Door Locking System) | 100214.6 | 90383.5 | Substantial Completion |  | All guest room locks have been installed and new access system is online.
|  | DH-Visitor Management System (Door Locking System) | 102632.26 |  | Substantial Completion |  | All guest room locks have been installed and new access system is online.
|  | CC-Visitor Management System (Door Locking System) | 83570.76 |  | Substantial Completion |  | All guest room locks have been installed and new access system is online.
|  | CF-Visitor Management System (Door Locking System) | 175514.7 |  | Substantial Completion |  | All guest room locks have been installed and new access system is online.
|  | GO-Visitor Management System (Door Locking System) | 125478.35 |  | Substantial Completion |  | All guest room locks have been installed and new access system is online.
|  | BL-Visitor Management System (Door Locking System) | 92709.49 | 82106.49 | Substantial Completion |  | All guest room locks have been installed and new access system is online.
|  | KD-Visitor Management System (Door Locking System) | 238917.24 | 209010.74 | Substantial Completion |  | All guest room locks have been installed and new access system is online.
|  | LB-Visitor Management System (Door Locking System) | 219431.68 | 219431.68 | Substantial Completion |  | All guest room locks have been installed and new access system is online.
|  | BR-Visitor Management System (Door Locking System) | 145555.25 | 145555.25 | Substantial Completion |  | All guest room locks have been installed and new access system is online.
|  | PM-Visitor Management System (Door Locking System) | 124957.48 | 124957.48 | Substantial Completion |  | All guest room locks have been installed and new access system is online.
|  | PF-Visitor Management System (Door Locking System) | 109978.71 | 98716.21 | Substantial Completion |  | All guest room locks have been installed and new access system is online.
|  | KL-Visitor Management System (Door Locking System) | 128641.14 | 128641.14 | Substantial Completion |  | All guest room locks have been installed and new access system is online.
|  | LC-Visitor Management System (Door Locking System) | 202136.31 | 202136.31 | Substantial Completion |  | All guest room locks have been installed and new access system is online.
|  | BK-Visitor Management System (Door Locking System) | 98130.5 | 98130.5 | Substantial Completion |  | All guest room locks have been installed and new access system is online.
|  | JJ-Visitor Management System (Door Locking System) | 22760.88 | 22760.88 | Substantial Completion |  | All guest room locks have been installed and new access system is online.
|  | Access Control Cards | 14940 | 14940 | Completed | 2025-02-12 | The purchasing of bulk quantity of access control cards is complete.
CBD2 |  | Structural and Safety Repairs Pool | 7011800
| CA6R | CO-Multi-Park Struct Invest-West | 2480000 | 327380.84
|  | CO-Multi-Park Struct Invest-Dale Hollow | 825147 |  | Ready to Advertise |  | Design Phase C complete and Ready To Advertise documents are being prepared for bid posting.
|  | CO-Multi-Park Struct Invest-Lake Cumberland | 1246947 | 411249.89 | In Construction |  | Contract has been awarded. Construction has started; however, there is a delay on written approval from the Army Corps of Engineers for a retaining wall due to the recent federal shutdown.
| CA6S | CO-Multi-Park Struct Invest-East | 3500000 | 274464.25 |  |  | The consultant for eastern parks will start with Cumberland Falls, Natural Bridge, and Pine Mountain State Resort Parks. On-site assessments are complete and the ready to advertise documents are in the Finance Facilities (DECA) buyer's review.
|  | CO-Multi-Park Struct Invest-Natural Bridge | 571273.07 | 575260.58 | Completed | 2025-11-17 | The project is in substantial completion.
|  | CO-Multi-Park Struct Invest-Pine Mountain | 1450000 | 1133127.41 | Completed | 2025-11-17 | The project is in substantial completion.
|  | CO-Multi-Park Struct Invest-Cumberland Falls | 257400 | 207052.84 | Completed | 2025-11-17 | The project is in substantial completion.
CBD3 |  | State Wide ADA Mobility Improvements Pool | 1065000 | 761906.55 | In Construction | 2026-01-31 | Project is under construction. Regularly scheduled site meetings are being held to monitor project status and work. Work is progressing and project is on schedule.
CBD4 |  | Dam Safety Reconstruction and Repairs Pool | 5000000
|  | PF-Pennyrile Forest Dam | 3697250 | 445798.33 | In Design |  | Pennyrile Forest State Resort Park dam repairs are in the final design phase, Phase C 95% complete. Ready To Advertise documents have been approved by DECA Project Manager but will not go out to bid until later in 2026 so it will not impact beach season.
|  | GO-Greenbo Dam |  |  | On Hold |  | Greenbo Lake State Resort Park is in preliminary design. This project is on hold due to a $9 million cost estimate. A capital project has been added to the six-year plan for funding to repair this dam.
CBD5 |  | EP Tom Sawyer Pool and Recreational Bldg. Upgrades Pool | 1280000 | 9000 | In Construction | 2026-05-01 | Project contract has been awarded. Preconstruction site meeting is scheduled for December 15, 2025.
CBD6 |  | Lake Barkley State Resort Park Lodge Wing Interior Upgrades | 2760000 | 1601121.59 | In Construction | 2025-12-15 | Lake Barkley State Resort Park lodge wing design has been completed. Construction on lodge wing interior upgrades are 99% complete.
CBD7 |  | Accommodations & Hospitality Upgrades Pool | 22000000 |  |  |  | There are two projects: One for Finance Facilities (DECA) to administer and one for State Parks to administer.
| CBE9 | Accommodations & Hospitality Upgrades PARKS | 1000000 | 568432.38 | On Order | 2026-02-15 | New mattresses are currently on order for Dale Hollow. Buckhorn is currently under review for new mattresses.
| CBEA | Accommodations & Hospitality Upgrades DECA | 21000000 | 1166238 | In Design |  | Regularly scheduled bi-weekly meetings are being held between the design consultant, Parks, and the Finance Facilities (DECA) project manager to review project design plans and potential design themes. Lake Cumberland is scheduled to start in January. Barren River and Jenny Wiley State Resort Parks are scheduled to start in March. Phase C 95%.
|  | BR-Accommodations & Hospitality Upgrades | 4133800 |  | Ready To Advertise |  | Prebid site meeting is scheduled December 15, 2025.
|  | LB-Accommodations & Hospitality Upgrades(Volume C) | 1911800 |  | Under Contract |  | Lake Barkley-Accommodations & Hospitality Upgrades is now under contract.
|  | LC-Accommodations & Hospitality Upgrades | 4908777 |  | Ready to Advertise | 2026-12-30 | Lake Cumberland-Accommodations & Hospitality Upgrades - Ready To Advertise documents are being completed for bid posting. Bid goes out 1/06/2026.
CBD8 |  | Pool Improvement and Repairs Pool | 11955900 | 927289.5 | In Design |  | The priority list includes Fort Boonesborough, Lake Barkley, and Greenbo Lake State Resort Parks. Lake Barkley State Resort Park is out to bid.
|  | LB-DEMO and Construct New Pool (Volume B) | 5729000 |  | In Construction |  | Contractor has mobilized to the park and currently establishing safe access process for construction demo.
|  | FB-Pool |  |  | In Design |  | Funding review will take place after Lake Barkley Pool projects are awarded.
|  | GO-Lodge Pool |  |  | In Design |  | Funding review will take place after Fort Boonesborough and Lake Barkley Pool projects are awarded.
|  | KL-Pool |  |  | In Design |  | Funding review will take place after Fort Boonesborough and Lake Barkley Pool projects are awarded.
CBD9 |  | Beach Refurbishment Pool | 310604.62
|  | CO-Various Parks-Beach Sand | 35995.38 | 59494.68 | Completed | 2025-03-01 | Next sand and beach equipment review will be done prior to FY26 spring opening.
CBDA |  | Playground Upgrades and Improvements Pool | 1200000
|  | EP Tom Sawyer-Playground-New Equipment | 90766.39 | 90766.39 | Completed |  | EP Tom Sawyer State Park playground is complete.
|  | Jefferson Davis-Playground-New Equipment | 86910.61 | 86910.61 | Completed |  | Jefferson Davis Historic Site playground is complete.
|  | Kentucky Dam-Playground-New Equipment | 85711.41 | 85711.41 | Completed |  | Kentucky Dam Village State Park playground is complete.
|  | Carter Caves-Playground-New Equipment | 149862 | 149862 | Completed |  | Carter Caves State Park playground is complete.
|  | Pine Mountain-Playground- New Equipment | 77799.35 | 77799.35 | Completed |  | Pine Mountain State Park playground is complete.
|  | Jenny Wiley-Playground-New Equipment | 119516.47 | 119516.47 | Completed |  | Jenny Wiley State Park playground is complete.
|  | Yatesville Lake-Playground-New Equipment | 102634.49 | 102634.49 | Completed |  | Yatesville Lake State Park playground is complete.
|  | Natural Bridge-Playground-New Equipment | 35472.65 | 35472.65 | Completed |  | Natural Bridge State Park playground is complete.
|  | Big Bone-Playground-New Equipment | 88944.92 | 88944.92 | Completed |  | Big Bone Lick State Park playground is complete.
|  | Pennyrile Forest-Playground-New Equipment | 114608 | 114608 | Completed |  | Pennyrile Forest State Park playground is complete.
|  | Taylorsville Lake-Playground-New Equipment | 90000 | 65352.82 | Completed |  | Taylorsville Lake State Park playground is complete.
|  | Waveland-Playground-New Equipment | 64470.38 | 64470.38 | Completed |  | Waveland Historic Site playground is complete.
|  | Buckhorn Lake-Playground-New Equipment | 78643.37 | 78643.37 | Completed |  | Buckhorn Lake State Park playground is complete.
CBDB |  | Golf Course Irrigation Replacement | 5332500 | 131175 | In Design | 2026-12-01 | Golf course irrigation design project is underway and currently in Phase A. Bid date is estimated for mid February 2026. Target for construction start is late April, 2026.The design will encompass four golf courses at the following state parks: Barren River (first priority), My Old Kentucky Home, Kentucky Dam Village, and Lake Barkley.
CBDC |  | Golf Course Bermuda Greens Conversion Pool | 575000 | 516348.77 | Completed |  | Work on the Bermuda Greens has been completed.
CBDD |  | Golf Course Bunker Repair Pool | 2590000
| DH00 | Dale Hollow | 608553 | 608553 | Completed | 2025-04-01 | Dale Hollow is complete.
| GL00 | Grayson Lake | 963000 | 962806 | Completed | 2025-05-10 | Grayson Lake is complete.
| MM07 | Mineral Mound | 201900 | 201900 | Completed | 2025-03-21 | Mineral Mound is complete.
| YL12 | Yatesville Lake | 434000 | 433860 | Completed | 2025-07-11 | Yatesville Lake is complete.
|  | Totals | 71000000 | 16264527.88
Note on E37: Gaines, Missy L (PARKS): Amount is for all of E701 Design Fees

## Key
Abbrev
ADA | Americans with Disabilities Act
B210 | Cost Estimate by DECA
BO | Beneficial Occupancy
C of O | Certificate of Completion
CCC | Civilian Conservation Corps
CCD | Contract Completion Date
CO | Central Office
CPBOC | Capital Projects Bond Oversight Committee
DECA | Division of Engineering and Contract Admin
DO | Delivery Order
eCOMM | Construction Information Management Software
EEC | Energy & Environment Cabinet
HBC | Housing Building & Construction
INFE | infrastructure - Electrical
INFS | Infrastructure - Sewer
INFW | Infrastructure - Water
MA | Master Agreement
OPS | Finance Cabinet Office of Procurement Services
OSBD | Office of State Budget Director
P-9 | Parks Force Account Labor (Construction Branch)
Phase A | Schematic Design
Phase B | Design Development
Phase C | Contract Document Production
PM | Project Manager
PO | Purchase Order
RFB | Request For Bids
RFP | Request For Proposal
RFQ | Request For Qualifications
RTA | Ready to Advertise
SC | Substantial Completion
WWTP | Waste Water Treatment Plant

## Parks
Abbrev | PARK NAME
BR | Barren River Lake State Resort Park
BB | Big Bone Lick State Park
BL | Blue Licks Battlefield State Resort Park
BK | Buckhorn Lake State Resort Park
CK | Carr Creek State Park
CC | Carter Caves State Resort Park
CB | Columbus-Belmont State Park
CF | Cumberland Falls State Resort Park
DH | Dale Hollow Lake State Resort Park
TW | Dr. Thomas Walker State Historic Site
EP | E.P. Tom Sawyer State Park
FB | Fort Boonesborough State Park
BS | General Burnside Island State Park
GB | General Butler State Resort Park
GL | Grayson Lake State Park
GR | Green River Lake State Park
GO | Greenbo Lake State Resort Park
IS | Isaac Shelby Cemetery State Historic Site
JD | Jefferson Davis State Historic Site
JW | Jenny Wiley State Resort Park
JJ | John James Audubon State Park
KL | Kenlake State Resort Park
KD | Kentucky Dam Village State Resort Park
KA | Kincaid Lake State Park
KC | Kingdom Come State Park
LB | Lake Barkley State Resort Park
LC | Lake Cumberland State Resort Park
LM | Lake Malone State Park
LH | Lincoln Homestead State Park
MM | Mineral Mound State Park
MO | My Old Kentucky Home State Park
NB | Natural Bridge State Resort Park
NL | Nolin Lake State Park
FH | Old Fort Harrod State Park
OM | Old Mulkey Meetinghouse State Historic Site
PL | Paintsville Lake State Park
PF | Pennyrile Forest State Resort Park
PB | Perryville Battlefield State Historic Site
PM | Pine Mountain State Resort Park
RR | Rough River Dam State Resort Park
TL | Taylorsville Lake State Park
WL | Waveland State Historic Site
WM | Wickliffe Mounds State Historic Site
YL | Yatesville Lake State Park