## Counties Q12026
Qtrly Report Start time | Qtrly Report Completion time | Organization Name | FY2026 Reporting Quarter | Is this project a City or County road? | District | County Project/Roadway Name | Progress on project? | Has your project been advertised and let? | Are you planning to do the project yourself? | Name of Contractor | Contractor State Vendor # | Contractor awarded contract amount | Contractor current amount earned | Contract percentage of work completed | Have you completed the project? | Estimated date for completion of project | Final actual cost to complete the project | Actual contract completion date
2025-10-14 16:42 | 2025-10-14 16:51 | Adair County Fiscal Court | Q1 (July 1-Sept 30) | County (CR) | District 8 | Adair County Fiscal Court CR 1016 Sulphur Creek Road | No progress | [8 empty] | 2025-10-31
2025-10-14 16:51 | 2025-10-14 16:52 | Adair County Fiscal Court | Q1 (July 1-Sept 30) | County (CR) | District 8 | Adair County Fiscal Court CR 1059 Abrell Road | No progress | [8 empty] | 2025-10-31
2025-10-08 15:23 | 2025-10-08 15:39 | Allen County Fiscal Court | Q1 (July 1-Sept 30) | County (CR) | District 3 | Allen Fiscal Court CR 1010 Capital Hill Road | Progress | Yes |  | Scottys Contracting | 2519 | 95446 | 62462.47 | 100 | Yes |  | 62462.47 | 2025-09-15
2025-10-08 15:39 | 2025-10-08 15:41 | Allen County Fiscal Court | Q1 (July 1-Sept 30) | County (CR) | District 3 | Allen Fiscal Court CR 1236 New Roe | Progress | Yes |  | Scottys Contracting | 2519 | 305114 | 322204.82 | 100 | Yes |  | 322204.82 | 2025-08-15
2025-10-08 13:53 | 2025-10-08 14:14 | Ballard Co. Fiscal Court | Q1 (July 1-Sept 30) | County (CR) | District 1 | Ballard County Fiscal Court CR 1204 VFW | Progress | Yes |  | Jim Smith Contracting | 2618 | 125000 | 0 | 25 | No | 2025-12-31
2025-10-08 15:10 | 2025-10-08 15:50 | Barren County Fiscal Court | Q1 (July 1-Sept 30) | County (CR) | District 3 | Barren County Fiscal Court CR-1243 Matthews Mill Road | No progress | [8 empty] | 2025-10-15
2025-10-09 13:44 | 2025-10-09 16:35 | Barren County Fiscal Court | Q1 (July 1-Sept 30) | County (CR) | District 3 | Barren County Fiscal Court CR-1150 Beechtree Lane | Progress | Yes |  | Scotty's Contracting & Stone | 2519 | 384823.9 | 0 | 100 | Yes |  | 349173.82 | 2025-08-21
2025-10-08 14:38 | 2025-10-08 14:53 | Bath County Fiscal Court | Q1 (July 1-Sept 30) | County (CR) | District 9 | Bath County Fiscal Court CR 1219 North Stepstone | Progress | Yes |  | Freedom Asphalt | 49287 | 167808.17 | 167808.17 | 100 | Yes |  | 167808.17 | 2025-07-28
2025-10-08 14:53 | 2025-10-08 14:56 | Bath County Fiscal Court | Q1 (July 1-Sept 30) | County (CR) | District 9 | Bath County Fiscal Court CR 1309 North Little Flat Ledford | Progress | Yes |  | Freedom Asphalt | 49287 | 199751.6 | 199751.6 | 100 | Yes |  | 199751.6 | 2025-07-31
2025-10-13 11:44 | 2025-10-13 11:48 | Bell County Fiscal Court | Q1 (July 1-Sept 30) | County (CR) | District 11 | Bell County Fiscal Court CR 1365 Blanton Branch Road | No progress | [8 empty] | 2026-04-01
2025-10-09 14:13 | 2025-10-09 17:11 | Bourbon County Fiscal Court | Q1 (July 1-Sept 30) | County (CR) | District 7 | Bourbon County Fiscal Court CR 1115 Prescott Lane | Progress | Yes |  | Hinkle Contracting | 3229 | 254314 | 0 | 0 | No | 2026-06-01
2025-10-09 13:18 | 2025-10-09 16:09 | Boyle County Fiscal Court | Q1 (July 1-Sept 30) | County (CR) | District 7 | Boyle County Fiscal Court CR 1316 Cocanougher Road | Progress | Yes |  | The Allen Company | 135 | 46000 | 46000 | 100 | Yes |  | 46000 | 2025-05-09
2025-10-09 08:45 | 2025-10-09 08:48 | Breckinridge County Fiscal Court | Q1 (July 1-Sept 30) | County (CR) | District 4 | Breckinridge County Fiscal Court CR 1162 Church of God Road | No progress | [8 empty] | 2026-05-29
2025-10-09 08:48 | 2025-10-09 08:49 | Breckinridge County Fiscal Court | Q1 (July 1-Sept 30) | County (CR) | District 4 | Breckinridge County Fiscal Court CR 1040 Harold Lucas Lane | No progress | [8 empty] | 2026-05-29
2025-10-09 11:07 | 2025-10-09 13:32 | Bullitt County Fiscal Court | Q1 (July 1-Sept 30) | County (CR) | District 5 | Bullitt County Fiscal Court CR 1312 P'Poole Lane | Progress | No | Yes |  |  |  |  | 100 | Yes |  | 19900 | 2025-08-25
2025-10-08 14:37 | 2025-10-08 14:52 | Butler County Fiscal Court | Q1 (July 1-Sept 30) | County (CR) | District 3 | Butler County CR 1064 Grancer Road | Progress | Yes |  | Scotty’s Contracting and Stone | 2519 | 574437.64 | 574437.64 | 100 | Yes |  | 574437.64 | 2025-08-25
2025-10-09 12:21 | 2025-10-09 12:33 | Caldwell County Fiscal Court | Q1 (July 1-Sept 30) | County (CR) | District 2 | Caldwell County Fiscal Court CR 1216 Rocksprings Road | Progress | Yes |  | Rogers Group, Inc. | 29875 | 189344.75 | 189344.75 | 100 | Yes |  | 189344.75 | 2025-08-08
2025-10-09 12:33 | 2025-10-09 12:35 | Caldwell County Fiscal Court | Q1 (July 1-Sept 30) | County (CR) | District 2 | Caldwell County Fiscal Court CR 1366 Pleasant Valley Road | Progress | Yes |  | Rogers Group, Inc. | 29875 | 411429.9 | 411429.9 | 100 | Yes |  | 411429.9 | 2025-08-13
2025-10-13 08:17 | 2025-10-14 15:07 | Clay County Fiscal Court | Q1 (July 1-Sept 30) | County (CR) | District 11 | Clay County Fiscal Court CR 1249 Whites Branch | Progress | Yes |  | ATS Construction | 1947 | 189000 | 189521.2 | 100 | Yes |  | 189521.2 | 2025-05-01
2025-10-15 16:07 | 2025-10-15 16:18 | Crittenden County Fiscal Court | Q1 (July 1-Sept 30) | County (CR) | District 1 | Crittenden County Fiscal Court CR 1257 Claylick Creek Road | Progress | Yes |  | Roger's Group | 818 | 87000 | 0 | 0 | No | 2025-11-14
2025-10-15 16:18 | 2025-10-15 16:25 | Crittenden County Fiscal Court | Q1 (July 1-Sept 30) | County (CR) | District 1 | Crittenden County Fiscal Court CR 1346 A. T. Crider Road | Progress | Yes |  | Roger's Group | 818 | 114000 | 0 | 0 | No | 2025-11-14
2025-10-08 13:55 | 2025-10-08 15:35 | Edmonson County Fiscal Court | Q1 (July 1-Sept 30) | County (CR) | District 3 | Edmonson County Fiscal Court CR 1144 James Parsley Road | Progress | Yes |  | Scotty's Contracting & Stone | 2519 | 26000 | 25425.46 | 100 | Yes |  | 25425.46 | 2025-08-04
2025-10-09 08:34 | 2025-10-09 09:05 | Estill County Fiscal Court | Q1 (July 1-Sept 30) | County (CR) | District 10 | Estill County Fiscal Court CR 1061 Patsy Road | Progress | Yes |  | Hinkle Contracting Company | 28986 | 476037 | 0 | 0 | No | 2026-03-30
2025-10-08 14:04 | 2025-10-08 14:11 | Fleming County Fiscal Court | Q1 (July 1-Sept 30) | County (CR) | District 9 | Fleming County Fiscal Court 035-CR 1027 Carpenter Road | Progress | Yes |  | HG Mays | 360 | 223000 | 178340.3 | 95 | No | 2025-11-20
2025-10-09 12:11 | 2025-10-09 12:14 | Floyd County Fiscal Court | Q1 (July 1-Sept 30) | County (CR) | District 12 | Floyd County Fiscal Court CR 1238 Old Hunter Road | No progress | [8 empty] | 2025-11-30
2025-10-09 10:53 | 2025-10-09 10:56 | Grant County Fiscal Court | Q1 (July 1-Sept 30) | County (CR) | District 6 | Grant County Fiscal Court CR 1140 Mason Cordova Road | Progress | Yes |  | Riegler Blacktop Inc | 837 | 327389.75 | 327389.75 | 100 | Yes |  | 327389.75 | 2025-09-30
2025-10-09 10:56 | 2025-10-09 10:59 | Grant County Fiscal Court | Q1 (July 1-Sept 30) | County (CR) | District 6 | Grant County Fiscal Court CR 1027 Lanter Road | Progress | Yes |  | Riegler Blacktop INC | 837 | 23000 | 0 | 10 | No | 2025-11-21
2025-10-14 07:32 | 2025-10-14 07:38 | Graves County Fiscal Court | Q1 (July 1-Sept 30) | County (CR) | District 1 | Graves County Fiscal Court CR 1125 Grace Park Road | Progress | Yes |  | Jim Smith Contracting | 2618 | 90000 | 90000 | 100 | Yes |  | 77838.46 | 2025-08-31
2025-10-10 16:18 | 2025-10-10 16:26 | Green County Fiscal Court | Q1 (July 1-Sept 30) | County (CR) | District 4 | Green County Fiscal Court CR 1314 Doc Ward Road | Progress | Yes |  | Haydon Materials | 2848 | 216336.64 | 216336.64 | 100 | Yes |  | 216336.64 | 2025-08-25
2025-10-10 16:26 | 2025-10-10 16:28 | Green County Fiscal Court | Q1 (July 1-Sept 30) | County (CR) | District 4 | Green County Fiscal Court CR 1052 Hall Cemetery Road | Progress | Yes |  | Haydon Materials | 2848 | 137820.8 | 137820.8 | 100 | Yes |  | 137820.8 | 2025-08-25
2025-10-09 12:56 | 2025-10-09 13:33 | Greenup County Fiscal Court | Q1 (July 1-Sept 30) | County (CR) | District 9 | Greenup County Fiscal Court CR 1385 Beauty Ridge | Progress | Yes |  | Mountain Enterprises | 2938 | 124927 | 0 | 0 | No | 2025-11-07
2025-10-08 13:56 | 2025-10-08 14:27 | Hancock County Fiscal Court | Q1 (July 1-Sept 30) | County (CR) | District 2 | Hancock County Fiscal Court CR 1223 North Indian Hill | Progress | Yes |  | Scotty's Contracting & Stone | 2519 | 275000 | 256891.35 | 100 | Yes |  | 256891.35 | 2025-09-30
2025-10-14 09:49 | 2025-10-14 10:47 | Hardin County Fiscal Court | Q1 (July 1-Sept 30) | County (CR) | District 4 | Hardin County Fiscal Court CR 1158 Middle Creek Road | Progress | Yes |  | Scotty's Contracting & Stone | 2519 | 170000 | 137347 | 100 | Yes |  | 137347 | 2025-08-28
2025-10-14 10:47 | 2025-10-14 14:45 | Hardin County Fiscal Court | Q1 (July 1-Sept 30) | County (CR) | District 4 | Hardin County Fiscal Court CR 1359 Nacke Pike | No progress | [8 empty] | 2025-10-31
2025-10-09 12:23 | 2025-10-09 13:06 | Harlan County Fiscal Court | Q1 (July 1-Sept 30) | County (CR) | District 11 | Harlan County Fiscal Court CR 1351 Daws Branch | Progress | Yes |  | Mountain Enterprises | 34177 | 42000 | 0 | 0 | No | 2025-11-30
2025-10-10 14:28 | 2025-10-10 14:32 | Hart County Fiscal Court | Q1 (July 1-Sept 30) | County (CR) | District 4 | Hart Fiscal Court CR 1420 Rocky Hill Road | Progress | Yes |  | Scotty's Contracting and Stone, LLC | 2519 | 218771.82 | 218771.82 | 100 | Yes |  | 218771.82 | 2025-08-22
2025-10-10 14:32 | 2025-10-10 14:33 | Hart County Fiscal Court | Q1 (July 1-Sept 30) | County (CR) | District 4 | Hart Fiscal Court CR 1132 Halltown Road | Progress | Yes |  | Scotty's Contracting and Stone, LLC | 2519 | 159296.9 | 159296.9 | 100 | Yes |  | 159296.9 | 2025-09-30
2025-10-08 14:49 | 2025-10-08 15:54 | Hopkins County Fiscal Court | Q1 (July 1-Sept 30) | County (CR) | District 2 | Hopkins County Fiscal Court CR 1486 Laurel Road | Progress | Yes |  | Scotty's Paving | 2519 | 138291.14 | 138291.14 | 100 | Yes |  | 138291.14 | 2025-09-05
2025-10-08 15:54 | 2025-10-08 16:05 | Hopkins County Fiscal Court | Q1 (July 1-Sept 30) | County (CR) | District 2 | Hopkins County Fiscal Court CR 1341 Bet Level Road | Progress | Yes |  | Scotty's Paving | 2519 | 189633.74 | 189633.74 | 100 | Yes |  | 189633.74 | 2025-08-07
2025-10-09 09:42 | 2025-10-09 09:43 | Jackson County Fiscal Court | Q1 (July 1-Sept 30) | County (CR) | District 11 | Jackson County Fiscal Court CR 055-1153 Maulden Owsley Road | No progress | [8 empty] | 2025-11-24
2025-10-08 14:05 | 2025-10-08 14:13 | Jessamine County Fiscal Court | Q1 (July 1-Sept 30) | County (CR) | District 7 | Jessamine County Fiscal Court CR 1106 Marble Creek Lane | Progress | Yes |  | Allen Company | 2067 | 123820.15 | 123820.15 | 100 | Yes |  | 123820.15 | 2025-08-22
2025-10-13 18:02 | 2025-10-13 18:05 | Johnson County Fiscal Court | Q1 (July 1-Sept 30) | County (CR) | District 12 | Johnson County Fiscal Court CR 1009 V Vanhoose road | No progress | [8 empty] | 2025-10-31
2025-10-13 18:06 | 2025-10-13 18:12 | Johnson County Fiscal Court | Q1 (July 1-Sept 30) | County (CR) | District 12 | Johnson County Fiscal Court CR 1434 American Standard Dr. | No progress | [8 empty] | 2026-08-15
2025-10-08 14:37 | 2025-10-08 14:38 | LaRue County Fiscal Court | Q1 (July 1-Sept 30) | County (CR) | District 4 | LaRue County Fiscal Court CR 1214 Cruse Road | No progress | [8 empty] | 2026-05-30
2025-10-09 14:16 | 2025-10-09 14:18 | Lawrence County Fiscal Court | Q1 (July 1-Sept 30) | County (CR) | District 12 | Lawrence County Fiscal Court CR 1322 Bells Trace | No progress | [8 empty] | 2026-04-30
2025-10-09 14:19 | 2025-10-09 14:20 | Lawrence County Fiscal Court | Q1 (July 1-Sept 30) | County (CR) | District 12 | Lawrence County Fiscal Court Cr 1225 Old Terryville Road | No progress | [8 empty] | 2026-04-30
2025-10-10 11:02 | 2025-10-10 11:12 | LEE COUNTY FISCAL COURT | Q1 (July 1-Sept 30) | County (CR) | District 10 | Lee County Fiscal Court CR 1226 Todds Road | Progress | Yes |  | Donnie Best Mudcat Construction | 3934 | 241059.52 | 241059.52 | 100 | Yes |  | 440397.2 | 2025-09-19
2025-10-10 11:12 | 2025-10-10 11:14 | LEE COUNTY FISCAL COURT | Q1 (July 1-Sept 30) | County (CR) | District 10 | Lee County Fiscal Court CR 1151 Joe Davidson Road | Progress | Yes |  | DONNIE BEST MUDCAT CONSTRUCTION | 3934 | 31299.84 | 31299.84 | 100 | Yes |  | 57182.4 | 2025-10-02
2025-10-09 09:33 | 2025-10-09 11:10 | Leslie County Fiscal Court | Q1 (July 1-Sept 30) | County (CR) | District 11 | Leslie County Fiscal Court CR 1032 Flackey Branch Road | Progress | Yes |  | Mountain Enterprises | 14687 | 120048.66 | 120048.66 | 100 | Yes |  | 120048.66 | 2025-07-31
2025-10-09 11:10 | 2025-10-09 11:14 | Leslie County Fiscal Court | Q1 (July 1-Sept 30) | County (CR) | District 11 | Leslie County Fiscal Court CR 1041 Pleasant Valley Road | Progress | Yes |  | Mountain Enterprises | 14687 | 220258.11 | 220258.11 | 100 | Yes |  | 220258.11 | 2025-07-31
2025-10-09 09:27 | 2025-10-09 11:09 | Lewis County Fiscal | Q1 (July 1-Sept 30) | County (CR) | District 9 | Lewis County Fiscal Court CR 1219 Beechy | Progress | Yes |  | H.G. Mays Corporation | 360 | 53230.77 | 53230.77 | 100 | Yes |  | 53230.77 | 2025-07-31
2025-10-09 11:10 | 2025-10-09 11:18 | Lewis County Fiscal Court | Q1 (July 1-Sept 30) | County (CR) | District 9 | Lewis County Fiscal Court CR 1102 Lower Kinney | Progress | Yes |  | H. G Mays Corporation | 360 | 37198.94 | 37198.94 | 100 | Yes |  | 37198.94 | 2025-07-31
2025-10-08 13:57 | 2025-10-08 14:00 | Livingston County Fiscal Court | Q1 (July 1-Sept 30) | County (CR) | District 1 | Livingston County Fiscal Court CR 1262 Ostle Loop | No progress | [8 empty] | 2026-05-30
2025-10-08 13:50 | 2025-10-08 14:17 | Lyon County Fiscal Court | Q1 (July 1-Sept 30) | County (CR) | District 1 | Lyon County Fiscal Court CR 1146 Birdie Bannister #1 | No progress | [8 empty] | 2026-06-30
2025-10-08 13:50 | 2025-10-08 14:17 | Lyon County Fiscal Court | Q1 (July 1-Sept 30) | County (CR) | District 1 | Lyon County Fiscal Court CR 1146 Birdie Bannister #2 | No progress | [8 empty] | 2026-06-30
2025-10-09 14:00 | 2025-10-09 15:50 | Madison County Fiscal Court | Q1 (July 1-Sept 30) | County (CR) | District 7 | Madison County Fiscal Court CR 1243 Peytontown Road | Progress | Yes |  | The Allen Company, Inc. | 135 | 159079.91 | 159079.91 | 100 | Yes |  | 159079.91 | 2025-09-16
2025-10-09 08:50 | 2025-10-09 09:25 | Marion County Fiscal Court | Q1 (July 1-Sept 30) | County (CR) | District 4 | Marion County Fiscal Court CR 1331 Brown Foreman Road | Progress | Yes |  | Haydon Materials | 2848 | 184894.99 | 184894.99 | 100 | Yes |  | 184894.99 | 2025-08-28
2025-10-08 14:59 | 2025-10-08 15:01 | Martin County Fiscal Court | Q1 (July 1-Sept 30) | County (CR) | District 12 | Martin County Fiscal Court CR 1313 Little Laurel | No progress | [8 empty] | 2025-12-12
2025-10-08 15:02 | 2025-10-08 15:02 | Martin County Fiscal Court | Q1 (July 1-Sept 30) | County (CR) | District 12 | Martin County Fiscal Court CR 1320 Cassell Branch | No progress | [8 empty] | 2025-11-30
2025-10-08 16:00 | 2025-10-08 16:14 | McCracken County Fiscal Court | Q1 (July 1-Sept 30) | County (CR) | District 1 | McCracken County Fiscal Court CR 1106F Westchester Lane | Progress | Yes |  | Jim Smith Contracting | 2618 | 100000 | 0 | 0 | No | 2025-12-19
2025-10-13 09:28 | 2025-10-13 09:32 | McLean County Fiscal Court | Q1 (July 1-Sept 30) | County (CR) | District 2 | McLean County Fiscal Court CR 1006 Hicks Road | No progress | [8 empty] | 2026-05-15
2025-10-13 09:32 | 2025-10-13 09:34 | McLean County Fiscal Court | Q1 (July 1-Sept 30) | County (CR) | District 2 | McLean County Fiscal Court CR 1009 Nuchols/Old Buck Creek Road | No progress | [8 empty] | 2026-05-22
2025-10-09 13:27 | 2025-10-09 13:32 | Menifee County Fiscal Court | Q1 (July 1-Sept 30) | County (CR) | District 10 | Menifee County Fiscal Court CR 1057 Cub Run Road | Progress | Yes |  | Walker Construction and Materials | 3832 | 172000 | 172000 | 100 | Yes |  | 191910.1 | 2025-08-31
2025-10-09 13:32 | 2025-10-09 13:34 | Menifee County Fiscal Court | Q1 (July 1-Sept 30) | County (CR) | District 10 | Menifee County Fiscal Court CR 1505 Canyon Ridge Road | Progress | Yes |  | Walker Construction and Materials | 3832 | 172000 | 191910.1 | 100 | Yes |  | 191910.1 | 2025-08-31
2025-10-08 14:59 | 2025-10-08 15:32 | Mercer County Fiscal Court | Q1 (July 1-Sept 30) | County (CR) | District 7 | Mercer County Fiscal Court CR 1209 Tewmey Lane | Progress | Yes |  | Mago Construction Company, LLC | 2432 | 116342.25 | 112261.51 | 100 | Yes |  | 112261.51 | 2025-08-23
2025-10-08 15:32 | 2025-10-08 15:36 | Mercer County Fiscal Court | Q1 (July 1-Sept 30) | County (CR) | District 7 | Mercer County Fiscal Court CR 1222 Falls Run | Progress | Yes |  | Mago Construction Company, LLC | 2432 | 222961.5 | 222098.17 | 100 | Yes |  | 222098.17 | 2025-09-06
2025-10-09 08:04 | 2025-10-09 08:23 | Montgomery County Fiscal Court | Q1 (July 1-Sept 30) | County (CR) | District 7 | Montgomery County Fiscal Court CR 1313 Cecil Road | Progress | Yes |  | Walker Construction & Materials LLC | 5008 | 302850 | 350317 | 100 | Yes |  | 350317 | 2025-09-26
2025-10-09 08:23 | 2025-10-09 08:27 | Montgomery County Fiscal Court | Q1 (July 1-Sept 30) | County (CR) | District 7 | Montgomery County Fiscal Court CR 1342A Meadow View Court | Progress | Yes |  | Walker Construction & Materials LLC | 5008 | 50475 | 55477 | 100 | Yes |  | 554779262025 | 2025-09-26
2025-10-14 08:43 | 2025-10-14 09:09 | Morgan County Fiscal Court | Q1 (July 1-Sept 30) | County (CR) | District 10 | Morgan County Fiscal Court CR 1515 Ivy Lane | No progress | [8 empty] | 2026-06-30
2025-10-14 09:09 | 2025-10-14 09:10 | Morgan County Fiscal Court | Q1 (July 1-Sept 30) | County (CR) | District 10 | Morgan County Fiscal Court CR 1558 Old HWY 172 | No progress | [8 empty] | 2026-06-30
2025-10-08 13:52 | 2025-10-08 14:05 | Muhlenberg County Fiscal Court | Q1 (July 1-Sept 30) | County (CR) | District 2 | Muhlenberg County Fiscal Court 089CR 1245 Friendship Road | No progress | [8 empty] | 2026-06-30
2025-10-08 14:20 | 2025-10-10 14:03 | Nicholas County Fiscal Court | Q1 (July 1-Sept 30) | County (CR) | District 9 | Nicholas County Fiscal Court CR 1102 Locust Grove | Progress | Yes |  | Hinkle Contracting | 3229 | 525835 | 565735 | 100 | No | 2025-09-11
2025-10-14 09:01 | 2025-10-14 09:08 | Ohio County Fiscal Court | Q1 (July 1-Sept 30) | County (CR) | District 2 | Ohio County Fiscal Court CR 1379 Beda Road | Progress | Yes |  | Scotty's Contracting & Stone | 2519 | 302409.25 | 299527.32 | 100 | Yes |  | 299527.32 | 2025-09-15
2025-10-14 09:08 | 2025-10-14 09:10 | Ohio County Fiscal Court | Q1 (July 1-Sept 30) | County (CR) | District 2 | Ohio County Fiscal Court CR 1399 Raymond Curry Road | Progress | Yes |  | Scotty's Contracting & Stone | 2519 | 108854.5 | 105149.47 | 100 | Yes |  | 105149.47 | 2025-09-29
2025-10-13 16:12 | 2025-10-13 16:21 | Owen County Fiscal Court | Q1 (July 1-Sept 30) | County (CR) | District 6 | Owen County Fiscal Court CR 1144 Fox Trail | No progress | [8 empty] | 2025-11-28
2025-10-10 10:23 | 2025-10-10 10:26 | Owsley County Fiscal Court | Q1 (July 1-Sept 30) | County (CR) | District 10 | Owsley County Fiscal Court CR 1115 Right Fork Buffalo Road | Progress | Yes |  | Hinkle | 3229 | 116761.5 | 116761.5 | 100 | Yes |  | 116761.5 | 2025-10-31
2025-10-10 10:26 | 2025-10-10 10:28 | Owsley County Fiscal Court | Q1 (July 1-Sept 30) | County (CR) | District 10 | Owsley County Fiscal Court CR 1120 Left Fork Buffalo Road | Progress | Yes |  | Hinkle | 3229 | 402165 | 402165 | 100 | Yes |  | 402165 | 2025-10-31
2025-10-10 09:51 | 2025-10-10 10:00 | Perry County Fiscal Court | Q1 (July 1-Sept 30) | County (CR) | District 10 | Perry County Fiscal Court 097 CR 1229 Wells Fork Road | No progress | [8 empty] | 2025-12-05
2025-10-10 10:19 | 2025-10-10 10:21 | Powell County Fiscal Court | Q1 (July 1-Sept 30) | County (CR) | District 10 | Powell County Fiscal Court CR 1307 Old Winchester Road | No progress | [8 empty] | 2025-11-30
2025-10-10 10:22 | 2025-10-10 10:23 | Powell County Fiscal Court | Q1 (July 1-Sept 30) | County (CR) | District 10 | Powell County Fiscal Court CR 1306 Copperras Creek Rd | No progress | [8 empty] | 2025-11-30
2025-10-15 08:36 | 2025-10-15 16:12 | Pulaski County Fiscal Court | Q1 (July 1-Sept 30) | County (CR) | District 8 | Pulaski County Fiscal Court CR 1648 Dye Road | Progress | Yes |  | Hinkle Contracting Company LLC | 3229 | 62875.75 | 61020.48 | 100 | Yes |  | 61020.48 | 2025-08-18
2025-10-15 16:12 | 2025-10-15 16:16 | Pulaski County Fiscal Court | Q1 (July 1-Sept 30) | County (CR) | District 8 | Pulaski County Fiscal Court CR 1232 Bauer Road | Progress | Yes |  | Hinkle Contracting Company LLC | 3229 | 254065 | 245592.58 | 100 | Yes |  | 245592.58 | 2025-09-18
2025-10-08 14:02 | 2025-10-08 14:04 | Rowan County Fiscal Court | Q1 (July 1-Sept 30) | County (CR) | District 9 | Rowan County Fiscal Court CR 1145 Crix Ridge Road | Progress | Yes |  | Hinkle Contracting Company, LLC | 3229 | 164080 | 164527.09 | 100 | Yes |  | 164527.09 | 2025-08-25
2025-10-08 13:50 | 2025-10-08 14:02 | Rowan County Fsical Court | Q1 (July 1-Sept 30) | County (CR) | District 9 | Rowan County Fiscal Court CR 1110 East Clack Mountain Road | Progress | Yes |  | Hinkle Contracting Company, LLC | 3229 | 302960 | 300030.98 | 100 | Yes |  | 300030.98 | 2025-08-25
2025-10-09 15:40 | 2025-10-09 15:41 | Russell County Fiscal Court | Q1 (July 1-Sept 30) | County (CR) | District 8 | Russell County Fiscal Court CR 1737 Kara Lane | No progress | [8 empty] | 2025-10-24
2025-10-08 15:08 | 2025-10-08 15:09 | Todd County Fiscal Court | Q1 (July 1-Sept 30) | County (CR) | District 3 | Todd County Fiscal Court CR 1350 Stringtown Road | Progress | Yes |  | Scotty's Contracting | 2519 | 245000 | 0 | 100 | Yes |  | 222995.1 | 2025-09-11
2025-10-08 15:09 | 2025-10-08 15:09 | Todd County Fiscal Court | Q1 (July 1-Sept 30) | County (CR) | District 3 | Todd County Fiscal Court CR 1231 Morton Lane | No progress | [8 empty] | 2025-10-31
2025-10-10 10:10 | 2025-10-10 10:46 | Warren County Road Department | Q1 (July 1-Sept 30) | County (CR) | District 3 | Warren County Fiscal Court CR 1284 Vance Lane | No progress | [8 empty] | 2026-05-01
2025-10-10 10:46 | 2025-10-10 10:50 | Warren County Road Department | Q1 (July 1-Sept 30) | County (CR) | District 3 | Warren County Fiscal Court CR 1075 Shanty Hollow Road | Progress | Yes |  | Scotty's Contracting and Stone | 2519 | 175856.16 | 68791.8 | 100 | Yes |  | 167929.2 | 2025-09-22
2025-10-08 13:52 | 2025-10-09 11:37 | Washington County Fiscal Court | Q1 (July 1-Sept 30) | County (CR) | District 4 | Washington County Fiscal Court CR 1142 Tick Creek Road | Progress | Yes |  | Haydon Materials LLC | 2848 | 373917.8 | 381483.04 | 100 | Yes |  | 381483.04 | 2025-08-06
2025-10-09 11:37 | 2025-10-09 11:39 | Washington County Fiscal Court | Q1 (July 1-Sept 30) | County (CR) | District 4 | Washington County Fiscal Court CR 1014 Glens Creek Road | Progress | Yes |  | Haydon Materials LLC | 2848 | 164209.81 | 166276.8 | 100 | Yes |  | 166276.8 | 2025-08-07
2025-10-09 08:31 | 2025-10-09 08:35 | Webster County Fiscal Court City of Dixon | Q1 (July 1-Sept 30) | County (CR) | District 2 | Webster County Fiscal Court CR 1325 Waggoner Chalybeate | No progress | [8 empty] | 2026-04-29
2025-10-09 07:41 | 2025-10-09 08:31 | Webster County Fiscal Court of Dixon | Q1 (July 1-Sept 30) | County (CR) | District 2 | Webster County Fiscal Court CR 1306 Andy Sisk | No progress | [8 empty] | 2026-04-23
*Denotes project complete |  |  |  |  | ****THIS QUARTERLY REPORT HAS BEEN COMPILED WITH INFORMATION SUPPLIED BY THE COUNTY/CITY.
AWAITING RESPONSE:
Boyd | Boyd County Fiscal Court | Stephens Meade Road | CR 1337B
Boyd | Boyd County Fiscal Court | Twin Ridge Road | CR 1242
Bracken | Bracken County Fiscal Court | Ford's Avenue | CR 1214
Bracken | Bracken County Fiscal Court | Thompson Ridge | CR 1111
Breathitt | Breathitt County Fiscal Court | Strong Branch Road | CR 1146
Breathitt | Breathitt County Fiscal Court | Hardshell Caney Road | CR 1117
Carroll | Carroll County Fiscal Court | Lansdale Lane | CR1100
Carter | Carter County Fiscal Court | Smokey Creek Road | CR 1464
Carter | Carter County Fiscal Court | Wells Branch Road | CR 1190
Christian | Christian County Fiscal Court | Britmart Road | CR 1069
Clark | Clark County Fiscal Court | Ecton Road | CR 1012
Clark | Clark County Fiscal Court | Oil Springs Road | CR 1105
CUMBERLAND | Cumberland County Fiscal Court | Bethel Scott Road | CR 1287
Elliott | Elliott County Fiscal Court | Stringtown | CR 1353
Elliott | Elliott County Fiscal Court | Gillium Branch | CR11113
Estill | Estill County Fiscal Court | Round Mountain Road | CR 1228
Floyd | Floyd County Fiscal Court | Conley Fork of Spurlock | CR 1423
Gallatin | Gallatin County Fiscal Court | Vera Cruz Road | CR 1201
Gallatin | Gallatin County Fiscal Court | Knox Lillard Road#2 | CR 1208
Grayson | Grayson County Fiscal Court | Hickory Flats Road | CR 1634
Grayson | Grayson County Fiscal Court | Eveleigh Road | CR-1094
Hancock | Hancock County Fiscal Court | North Indian Hill | CR 1223
Letcher | Letcher County Fiscal Court | Downhill Drive | CR 1577
Letcher | Letcher County Fiscal Court | Thicket Branch | CR 1144
Livingston | Livingston County Fiscal Court | Bluff Road | CR 1326
Magoffin | Magoffin County Fiscal Court | Bennie Patrick Road | CR 1002
Monroe | Monroe County Fiscal Court | D Lyons Road | CR 1036
Nelson | Nelson County Fiscal Court | Shady Lane | CR 1241
Nelson | Nelson County Fiscal Court | Yates Cooney Neck Road | CR 1022
Pendleton | Pendleton County Fiscal Court | Lenoxburg Road | CR 1064
Perry | Perry County Fiscal Court | Colwell Fork Road | 097 CR 1314
Taylor | Taylor County Fiscal Court | Cuddler Creek | CR 1017
Wolfe | Wolfe County Fiscal Court | Cable Ridge Road | CR 1288
Wolfe | Wolfe County Fiscal Court | Smokey Branch Road | CR 1204

## Cities Q12026
Qtrly Report Start time | Qtrly Report Completion time | Organization Name | FY2026 Reporting Quarter | Is this project a City or County road? | City Project/Roadway Name | Progress on project? | Has your project been advertised and let? | Are you planning to do the project yourself? | Name of Contractor | Contractor State Vendor # | Contractor awarded contract amount | Contractor current amount earned | Contract percentage of work completed | Have you completed the project? | Estimated date for completion of project | Final actual cost to complete the project | Actual contract completion date
2025-10-08 13:58 | 2025-10-08 13:59 | City of Bardwell | Q1 (July 1-Sept 30) | City (CS) | City of Bardwell CS 1014 East Court Street | No progress | [8 empty] | 2025-12-01
2025-10-08 14:06 | 2025-10-08 15:51 | City of Edmonton | Q1 (July 1-Sept 30) | City (CS) | City of Edmonton CS 1065 River Road | No progress | [8 empty] | 2025-12-30
2025-10-08 15:51 | 2025-10-08 15:51 | City of Edmonton | Q1 (July 1-Sept 30) | City (CS) | City of Edmonton CS 1007 Hill Street | No progress | [8 empty] | 2025-12-31
2025-10-09 11:44 | 2025-10-09 11:49 | City of Fort Thomas | Q1 (July 1-Sept 30) | City (CS) | City of Fort Thomas CS 4036 James Avenue | No progress | [8 empty] | 2026-06-30
2025-10-14 07:18 | 2025-10-14 07:26 | City of Frankfort | Q1 (July 1-Sept 30) | City (CS) | City of Frankfort CS1429 Michael C. Davenport Blvd | Progress | Yes |  | Louisville Paving Company, Inc | Unk | 110000 | 0 | 95 | No | 2025-11-01
2025-10-09 09:00 | 2025-10-09 09:01 | City of Franklin | Q1 (July 1-Sept 30) | City (CS) | City of Franklin CS 1025 Breckinridge Street | No progress | [8 empty] | 2026-08-01
2025-10-09 09:01 | 2025-10-09 09:02 | City of Franklin | Q1 (July 1-Sept 30) | City (CS) | City of Franklin CS 1004 McGoodwin Ave | Progress | No | Yes |  |  |  |  | 100 | Yes |  | 30000 | 2025-09-30
2025-10-13 11:17 | 2025-10-13 11:19 | CITY OF HARLAN KENTUCKY | Q1 (July 1-Sept 30) | City (CS) | City of Harlan CS 1050 Oak Street | No progress | [8 empty] | 2026-06-30
2025-10-13 09:46 | 2025-10-13 09:52 | City of Lebanon | Q1 (July 1-Sept 30) | City (CS) | City of Lebanon CS 1036 E. Mulberry St. | Progress | Yes |  | Haydon materials | 2848 | 42000 | 42000 | 100 | No | 2025-04-25
2025-10-08 16:23 | 2025-10-08 16:24 | City of Liberty | Q1 (July 1-Sept 30) | City (CS) | City of Liberty CS 1015 Combest Street | No progress | [8 empty] | 2026-04-30
2025-10-13 10:25 | 2025-10-13 11:23 | City of Russellville | Q1 (July 1-Sept 30) | City (CS) | City of Russellville CS 1242/CS1248 Thurston Drive | Progress | Yes |  | Scotty's Contracting & Stone | 2519 | 98240 | 98240 | 100 | Yes |  | 98240 | 2025-07-05
2025-10-13 03:43 | 2025-10-13 03:45 | City of Salyersville | Q1 (July 1-Sept 30) | City (CS) | City of Salyersville CS 1017 Coal Branch Road | No progress | [8 empty] | 2026-04-30
2025-10-15 11:10 | 2025-10-15 11:32 | City of Oak Grove | Q1 (July 1-Sept 30) | City (CS) | City of Oakgrove CS 5036 Oak Tree Dr. | No progress | [8 empty] | 2026-06-30
2025-10-15 10:40 | 2025-10-15 13:28 | City of Falmouth | Q1 (July 1-Sept 30) | City (CS) | City of Falmouth CS 1002 West Shelby Street | Progress | Yes |  | Mago Construction | 87896 | 129350 | 129350 | 100 | Yes |  | 129350 | 2025-08-15
*Denotes project complete | [6 empty] | ***THIS QUARTERLY REPORT HAS BEEN COMPILED WITH INFORMATION SUBMITTED BY THE COUNTY/CITY.
AWAITING RESPONSE:
|  | City of Middlesboro | CS 2306 | Lower Gibson Lane
|  | City of Paris | CS 1105 | Springhill Drive
|  | City of Bardwell | CS 1028 | Front St.
|  | City of Hodgenville | CS 1076 | College St.
|  | City of Stamping Ground | CS 3016 | Commonwealth Drive
|  | City of Lancaster | CS 1017 | S. Campbell
|  | City of Lancaster | CS 1056 | Hamilton Avenue
|  | City of Central City | CS 2121 | Park Street