## Counties Q2 2026
Qtrly Report Start Time | Qtrly Report Completion Time | Organization Name | FY2026 Reporting Quarter | Is this project a City or County road? | District | County Project/Roadway Name | Progress on project? | Has your project been advertised and let? | Are you planning to do the project yourself? | Name of Contractor | Contractor State Vendor # | Contractor awarded contract amount | Contractor current amount earned | Contract percentage of work completed | Have you completed the project? | Estimated date for completion of project | Final actual cost to complete the project | Actual contract completion date
2025-10-27 07:14 | 2025-10-27 07:16 | City of Lancaster | Q1 (July 1-Sept 30) | City (CS) |  |  | Progress | Yes |  | The Allen Company | 11111 | 108000 | 0 | 0 | No | 2025-11-26
2025-10-27 07:16 | 2025-10-27 07:17 | City of Lancaster | Q1 (July 1-Sept 30) | City (CS) |  |  | Progress | Yes |  | The Allen Company | 11111 | 0 | 0 | 0 | No | 2026-05-30
2025-12-12 11:21 | 2025-12-12 11:26 | Adair County Fiscal Court | Q2 (October 1-December 31) | County (CR) | District 8 (Adair, Casey, Clinton, Cumberland, Lincoln, McCreary, Pulaski, Rockcastle, Russell, and Wayne counties) | Adair County Fiscal Court CR 1016 Sulphur Creek Road | Progress | Yes |  | Gaddie Shamrock | 2493 | 192000 | 191861.52 | 100 | Yes |  | 191861.52 | 2025-11-22
2025-12-12 11:26 | 2025-12-12 11:30 | Adair County Fiscal Court | Q2 (October 1-December 31) | County (CR) | District 8 (Adair, Casey, Clinton, Cumberland, Lincoln, McCreary, Pulaski, Rockcastle, Russell, and Wayne counties) | Adair County Fiscal Court CR 1059 Abrell Road | Progress | Yes |  | Gaddie Shamrock | 2493 | 120000 | 119960.92 | 100 | Yes |  | 119960.92 | 2025-11-21
2025-12-11 08:26 | 2025-12-11 08:30 | Allen County Fiscal Court | Q2 (October 1-December 31) | County (CR) | District 3 (Allen, Barren, Butler, Edmonson, Logan, Metcalfe, Monroe, Simpson, Todd and Warren counties) | Allen Fiscal Court CR 1010 Capital Hill Road--COMPLETE DO NOT REPORT | Progress | Yes |  | Scotty's | 2519 | 67462.47 | 67462.47 | 100 | Yes |  | 67462.47 | 2025-08-04
2025-12-10 11:26 | 2025-12-10 14:46 | Ballard County Fiscal Court | Q2 (October 1-December 31) | County (CR) | District 1 (Ballard, Calloway, Carlisle, Crittenden, Fulton, Graves, Hickman, Livingston, Lyon, Marshall, McCracken, & Trigg counties) | Ballard County Fiscal Court CR 1204 VFW | Progress | Yes |  | Jim Smith Construction | 2618 | 125000 | 120000 | 100 | Yes |  | 120000 | 2025-10-30
2025-12-11 10:50 | 2025-12-11 10:59 | Barren County Fiscal Court | Q2 (October 1-December 31) | County (CR) | District 3 (Allen, Barren, Butler, Edmonson, Logan, Metcalfe, Monroe, Simpson, Todd and Warren counties) | Barren County Fiscal Court CR-1150 Beechtree Lane | Progress | Yes |  | Scotty's Contracting | 2519 | 384823.9 | 349173.82 | 100 | Yes |  | 349173.82 | 2025-08-25
2025-12-11 15:47 | 2025-12-11 16:09 | Barren County Fiscal Court | Q2 (October 1-December 31) | County (CR) | District 3 (Allen, Barren, Butler, Edmonson, Logan, Metcalfe, Monroe, Simpson, Todd and Warren counties) | Barren County Fiscal Court CR-1243 Matthews Mill Road | Progress | Yes |  | Scotty's Contracting | 2519 | 119487.5 | 0 | 100 | Yes |  | 119487.5 | 2025-10-21
2025-12-16 13:33 | 2025-12-16 13:35 | Bell County Fiscal Court | Q2 (October 1-December 31) | County (CR) | District 11 (Bell, Clay, Harlan, Jackson, Knox, Laurel, Leslie, and Whitley counties) | Bell County Fiscal Court CR 1365 Blanton Branch Road | No progress | [8 empty] | 2026-05-01
2025-12-10 15:02 | 2025-12-10 15:09 | Bourbon County Fiscal Court | Q2 (October 1-December 31) | County (CR) | District 7 (Anderson, Bourbon, Boyle, Clark, Fayette, Garrard, Jessamine, Madison, Mercer, Montgomery, Scott, and Woodford counties) | Bourbon County Fiscal Court CR 1115 Prescott Lane | No progress | [8 empty] | 2026-06-01
2026-01-06 13:45 | 2026-01-06 13:49 | Boyle County Fiscal Court | Q2 (October 1-December 31) | County (CR) | District 7 (Anderson, Bourbon, Boyle, Clark, Fayette, Garrard, Jessamine, Madison, Mercer, Montgomery, Scott, and Woodford counties) | Boyle County Fiscal Court CR 1316 Cocanougher Road | Progress | Yes |  | The Allen Company | 135 | 46000 | 46000 | 100 | No | 2025-05-09
2025-12-10 11:57 | 2025-12-10 11:59 | Breckinridge County Fiscal Court | Q2 (October 1-December 31) | County (CR) | District 4 (Breckinridge, Grayson, Green, Hardin, Hart, LaR​​​​​​ue, Marion, Meade, Nelson, Taylor, and Washington counties) | Breckinridge County Fiscal Court CR 1162 Church of God Road | No progress | [8 empty] | 2026-05-29
2025-12-11 08:55 | 2025-12-15 09:30 | Carroll County Fiscal Court | Q2 (October 1-December 31) | County (CR) | District 6 (Boone, Bracken, Campbell, Carroll, Gallatin, Grant, Harrison, Kenton, Owen, Pendleton, and Robertson counties) | Carroll County Fiscal Court CR1100 Lansdale Lane | Progress | Yes |  | Hinkle Contracting | 3229 | 4027.14 | 4027.14 | 100 | Yes |  | 4027.14 | 2024-11-27
2025-12-10 11:54 | 2025-12-10 12:00 | Carter County Fiscal Court | Q2 (October 1-December 31) | County (CR) | District 9 (Bath, Boyd, Carter, Elliott, Fleming, Greenup, Lewis, Mason, Nicholas, and Rowan counties) | Carter County Fiscal Court CR 1464 Smokey Creek Road | Progress | Yes |  | Mountain Enterprises | 2938 | 345571.05 | 345571.05 | 100 | Yes |  | 345571.05 | 2025-10-09
2025-12-10 13:35 | 2025-12-10 13:41 | City of Lebanon | Q2 (October 1-December 31) | City (CS) |  |  | Progress | Yes |  | Nally and Haydon | 85472 | 42000 | 42000 | 100 | No | 2025-04-25
2025-12-10 12:00 | 2025-12-10 12:02 | Carter County Fiscal Court | Q2 (October 1-December 31) | County (CR) | District 9 (Bath, Boyd, Carter, Elliott, Fleming, Greenup, Lewis, Mason, Nicholas, and Rowan counties) | Carter County Fiscal Court CR 1190 Wells Branch Road | Progress | Yes |  | Mountain Enterprises | 2938 | 161646.26 | 161646.26 | 100 | Yes |  | 161646.26 | 2025-10-02
2025-12-10 13:59 | 2025-12-10 14:04 | CITY OF HARLAN KY | Q2 (October 1-December 31) | City (CS) |  |  | Progress | Yes |  | MOUNTAIN ENTERPRISES, INC | 0 | 30000 | 0 | 0 | No | 2026-05-31
2025-12-19 12:45 | 2025-12-19 13:10 | Clark County Fiscal Court | Q2 (October 1-December 31) | County (CR) | District 7 (Anderson, Bourbon, Boyle, Clark, Fayette, Garrard, Jessamine, Madison, Mercer, Montgomery, Scott, and Woodford counties) | Clark County Fiscal Court CR 1012 Ecton Road | Progress | Yes |  | The Allen Company | 135 | 333359.83 | 333359.83 | 100 | Yes |  | 333359.83 | 2025-11-24
2025-12-10 13:25 | 2025-12-10 13:26 | Crittenden County Fiscal Court | Q2 (October 1-December 31) | County (CR) | District 1 (Ballard, Calloway, Carlisle, Crittenden, Fulton, Graves, Hickman, Livingston, Lyon, Marshall, McCracken, & Trigg counties) | Crittenden County Fiscal Court CR 1257 Claylick Creek Road | No progress | [8 empty] | 2026-04-30
2025-12-10 13:26 | 2025-12-10 13:27 | Crittenden County Fiscal Court | Q2 (October 1-December 31) | County (CR) | District 1 (Ballard, Calloway, Carlisle, Crittenden, Fulton, Graves, Hickman, Livingston, Lyon, Marshall, McCracken, & Trigg counties) | Crittenden County Fiscal Court CR 1346 A. T. Crider Road | No progress | [8 empty] | 2026-04-30
2025-12-11 11:51 | 2025-12-11 11:52 | Elliott Fiscal Court | Q2 (October 1-December 31) | County (CR) | District 9 (Bath, Boyd, Carter, Elliott, Fleming, Greenup, Lewis, Mason, Nicholas, and Rowan counties) | Elliott County Fiscal Court CR 1353 Stringtown | No progress | [8 empty] | 2026-05-30
2025-12-11 11:52 | 2025-12-11 11:53 | Elliott Fiscal Court | Q2 (October 1-December 31) | County (CR) | District 9 (Bath, Boyd, Carter, Elliott, Fleming, Greenup, Lewis, Mason, Nicholas, and Rowan counties) | Elliott County Fiscal Court CR11113 Gillium Branch | No progress | [8 empty] | 2026-05-31
2026-01-07 09:09 | 2026-01-07 09:26 | Estill County Fiscal Court | Q2 (October 1-December 31) | County (CR) | District 10 ( Breathitt, Estill, Lee, Magoffin, Menifee, Morgan, Owsley, Perry, Powell, and Wolfe counties) | Estill County Fiscal Court CR 1228 Round Mountain Road | Progress | Yes |  | Hinkle Contracting Corporation | 28986 | 173988 | 173099.84 | 100 | Yes |  | 173099.84 | 2025-12-02
2026-01-07 09:27 | 2026-01-07 09:30 | Estill County Fiscal Court | Q2 (October 1-December 31) | County (CR) | District 10 ( Breathitt, Estill, Lee, Magoffin, Menifee, Morgan, Owsley, Perry, Powell, and Wolfe counties) | Estill County Fiscal Court CR 1061 Patsy Road | Progress | Yes |  | Hinkle Contracting Company, LLC | 28986 | 302049 | 299190.11 | 100 | Yes |  | 299190.11 | 2025-12-02
2025-12-19 10:45 | 2025-12-19 12:36 | FLEMING COUNTY FISCAL COURT | Q2 (October 1-December 31) | County (CR) | District 9 (Bath, Boyd, Carter, Elliott, Fleming, Greenup, Lewis, Mason, Nicholas, and Rowan counties) | Fleming County Fiscal Court 035-CR 1027 Carpenter Road | Progress | Yes |  | H G MAYS | 360 | 223000 | 193253 | 100 | Yes |  | 193253 | 2025-09-23
2026-01-15 13:04 | 2026-01-15 14:01 | Greenup County Fiscal Court | Q2 (October 1-December 31) | County (CR) | District 9 (Bath, Boyd, Carter, Elliott, Fleming, Greenup, Lewis, Mason, Nicholas, and Rowan counties) | Greenup County Fiscal Court CR 1385 Beauty Ridge | Progress | Yes |  | Mountain Enterprises | 2938 | 122221 | 123017.99 | 100 | Yes |  | 123017.99 | 2025-11-24
2026-01-06 13:15 | 2026-01-06 13:44 | Hardin County Fiscal Court | Q2 (October 1-December 31) | County (CR) | District 4 (Breckinridge, Grayson, Green, Hardin, Hart, LaR​​​​​​ue, Marion, Meade, Nelson, Taylor, and Washington counties) | Hardin County Fiscal Court CR 1359 Nacke Pike | Progress | Yes |  | Scotty's Contracting and Stone | 2519 | 281932.32 | 281932.32 | 100 | Yes |  | 281932.32 | 2025-10-27
2026-01-06 13:44 | 2026-01-06 13:49 | Hardin County Fiscal Court | Q1 (July 1-Sept 30) | County (CR) | District 4 (Breckinridge, Grayson, Green, Hardin, Hart, LaR​​​​​​ue, Marion, Meade, Nelson, Taylor, and Washington counties) | Hardin County Fiscal Court CR 1158 Middle Creek Road | Progress | Yes |  | Scotty' Contracting and Stone | 2519 | 137346.71 | 137346.71 | 100 | Yes |  | 137346.71 | 2025-09-02
2025-12-29 10:59 | 2025-12-29 11:00 | Harlan County Fiscal Court | Q2 (October 1-December 31) | County (CR) | District 11 (Bell, Clay, Harlan, Jackson, Knox, Laurel, Leslie, and Whitley counties) | Harlan County Fiscal Court CR 1351 Daws Branch | No progress | [8 empty] | 2026-06-30
2026-01-12 15:18 | 2026-01-12 15:30 | Harlan County Fiscal Court | Q1 (July 1-Sept 30) | County (CR) | District 11 (Bell, Clay, Harlan, Jackson, Knox, Laurel, Leslie, and Whitley counties) | Harlan County Fiscal Court CR 1351 Daws Branch | No progress | [8 empty] | 2026-05-30
2025-12-11 08:57 | 2025-12-11 09:13 | Hart County Fiscal Court | Q2 (October 1-December 31) | County (CR) | District 4 (Breckinridge, Grayson, Green, Hardin, Hart, LaR​​​​​​ue, Marion, Meade, Nelson, Taylor, and Washington counties) | Hart Fiscal Court CR 1132 Halltown Road | Progress | Yes |  | Scotty's Contracting | 2519 | 159296.9 | 159296.9 | 100 | Yes |  | 159296.9 | 2025-09-30
2025-12-11 09:14 | 2025-12-11 09:17 | Hart County Fiscal Court | Q2 (October 1-December 31) | County (CR) | District 4 (Breckinridge, Grayson, Green, Hardin, Hart, LaR​​​​​​ue, Marion, Meade, Nelson, Taylor, and Washington counties) | Hart Fiscal Court CR 1420 Rocky Hill Road | Progress | Yes |  | Gaddie-Shamrock Inc. | 02493 | 218771.82 | 218771.82 | 100 | Yes |  | 218771.82 | 2025-09-30
2025-12-11 12:05 | 2025-12-11 12:06 | Jackson County Fiscal Court | Q2 (October 1-December 31) | County (CR) | District 11 (Bell, Clay, Harlan, Jackson, Knox, Laurel, Leslie, and Whitley counties) | Jackson County Fiscal Court CR 055-1153 Maulden Owsley Road | No progress | [8 empty] | 2026-04-13
2025-12-11 08:04 | 2025-12-11 08:07 | Johnson County Fiscal Court | Q2 (October 1-December 31) | County (CR) | District 12 (Floyd, Johnson, Knott, Lawrence, Letcher, Martin & Pike counties) | Johnson County Fiscal Court CR 1009 V Vanhoose road | No progress | [8 empty] | 2026-04-15
2025-12-11 08:07 | 2025-12-11 08:09 | Johnson County Fiscal Court | Q2 (October 1-December 31) | County (CR) | District 12 (Floyd, Johnson, Knott, Lawrence, Letcher, Martin & Pike counties) | Johnson County Fiscal Court CR 1434 American Standard Dr. | No progress | [8 empty] | 2026-08-15
2026-01-14 12:14 | 2026-01-14 12:20 | Lawrence County Fiscal Court | Q2 (October 1-December 31) | County (CR) | District 12 (Floyd, Johnson, Knott, Lawrence, Letcher, Martin & Pike counties) | Lawrence County Fiscal Court Cr 1225 Old Terryville Road | Progress | Yes |  | Blacktop Industries | 0 | 83560.52 | 83560.52 | 100 | Yes |  | 83560.52 | 2025-11-29
2026-01-14 12:20 | 2026-01-14 12:23 | Lawrence County Fiscal Court | Q2 (October 1-December 31) | County (CR) | District 12 (Floyd, Johnson, Knott, Lawrence, Letcher, Martin & Pike counties) | Lawrence County Fiscal Court CR 1322 Bells Trace | No progress | [8 empty] | 2026-04-30
2025-12-18 09:59 | 2025-12-18 10:21 | Letcher County Fiscal Court | Q2 (October 1-December 31) | County (CR) | District 12 (Floyd, Johnson, Knott, Lawrence, Letcher, Martin & Pike counties) | Letcher County Fiscal Court CR 1144 Thicket Branch | Progress | Yes |  | Mountain Enterprise | 0 | 67000 | 4148.32 | 100 | Yes |  | 4148.32 | 2025-12-11
2025-12-18 10:21 | 2025-12-18 10:22 | Letcher County Fiscal Court | Q2 (October 1-December 31) | County (CR) | District 12 (Floyd, Johnson, Knott, Lawrence, Letcher, Martin & Pike counties) | Letcher County Fiscal Court CR 1577 Downhill Drive | No progress | [8 empty] | 2026-03-31
2025-12-10 13:57 | 2025-12-10 13:59 | Livingston County Fiscal Court | Q2 (October 1-December 31) | County (CR) | District 1 (Ballard, Calloway, Carlisle, Crittenden, Fulton, Graves, Hickman, Livingston, Lyon, Marshall, McCracken, & Trigg counties) | Livingston County Fiscal Court CR 1326 Bluff Road | No progress | [8 empty] | 2026-05-30
2025-12-10 13:59 | 2025-12-10 14:00 | Livingston County Fiscal Court | Q2 (October 1-December 31) | County (CR) | District 1 (Ballard, Calloway, Carlisle, Crittenden, Fulton, Graves, Hickman, Livingston, Lyon, Marshall, McCracken, & Trigg counties) | Livingston County Fiscal Court CR 1262 Ostle Loop | No progress | [8 empty] | 2026-05-30
2025-12-10 13:12 | 2025-12-10 13:13 | Lyon County Fiscal Court | Q2 (October 1-December 31) | County (CR) | District 1 (Ballard, Calloway, Carlisle, Crittenden, Fulton, Graves, Hickman, Livingston, Lyon, Marshall, McCracken, & Trigg counties) | Lyon County Fiscal Court CR 1146 Birdie Bannister #1 | No progress | [8 empty] | 2026-10-30
2025-12-10 13:13 | 2025-12-10 13:14 | Lyon County Fiscal Court | Q2 (October 1-December 31) | County (CR) | District 1 (Ballard, Calloway, Carlisle, Crittenden, Fulton, Graves, Hickman, Livingston, Lyon, Marshall, McCracken, & Trigg counties) | Lyon County Fiscal Court CR 1146 Birdie Bannister #2 | No progress | [8 empty] | 2026-10-30
2025-12-11 16:28 | 2025-12-12 14:27 | Magoffin County Fiscal Court | Q2 (October 1-December 31) | County (CR) | District 10 ( Breathitt, Estill, Lee, Magoffin, Menifee, Morgan, Owsley, Perry, Powell, and Wolfe counties) | Magoffin County Fiscal Court CR 1002 Bennie Patrick Road | Progress | Yes |  | Hinkle Contracting | 28986 | 33000 | 32244.66 | 100 | Yes |  | 32244.66 | 2025-10-23
2025-12-12 13:02 | 2025-12-12 13:04 | Martin County Fiscal Court | Q2 (October 1-December 31) | County (CR) | District 12 (Floyd, Johnson, Knott, Lawrence, Letcher, Martin & Pike counties) | Martin County Fiscal Court CR 1320 Cassell Branch | Progress | Yes |  | Hinkle Blacktop LLC | 4046 | 118 | 116227.02 | 100 | Yes |  | 116227.02 | 2025-11-13
2025-12-12 13:04 | 2025-12-12 13:15 | Martin County Fiscal Court | Q2 (October 1-December 31) | County (CR) | District 12 (Floyd, Johnson, Knott, Lawrence, Letcher, Martin & Pike counties) | Martin County Fiscal Court CR 1313 Little Laurel | Progress | Yes |  | Hinkle Blacktop LLC | 4046 | 110 | 0 | 100 | Yes |  | 0 | 2025-12-01
2026-01-03 10:38 | 2026-01-03 10:40 | City of Lancaster | Q2 (October 1-December 31) | City (CS) |  |  | Progress | Yes |  | The Allen Company | 12345 | 108000 | 0 | 0 | No | 2026-03-31
2026-01-03 10:40 | 2026-01-03 10:42 | City of Lancaster | Q2 (October 1-December 31) | City (CS) |  |  | Progress | Yes |  | N/a - it was advertised but not awarded yet | 12345 | 0 | 0 | 0 | No | 2026-05-31
2025-12-10 15:40 | 2025-12-10 15:47 | McCracken County Fiscal Court | Q2 (October 1-December 31) | County (CR) | District 1 (Ballard, Calloway, Carlisle, Crittenden, Fulton, Graves, Hickman, Livingston, Lyon, Marshall, McCracken, & Trigg counties) | McCracken County Fiscal Court CR 1106F Westchester Lane | Progress | No | Yes |  |  |  |  | 95 | No | 2025-12-31
2025-12-10 11:38 | 2025-12-10 12:12 | Monroe County Fiscal Court | Q2 (October 1-December 31) | County (CR) | District 3 (Allen, Barren, Butler, Edmonson, Logan, Metcalfe, Monroe, Simpson, Todd and Warren counties) | Monroe County Fiscal Court CR 1036 D Lyons Road | Progress | Yes |  | Scotty's Contracting & Stone | 2519 | 3000 | 3000 | 100 | Yes |  | 3000 | 2025-11-01
2025-12-29 16:25 | 2025-12-29 16:58 | Muhlenberg County Fiscal Court | Q2 (October 1-December 31) | County (CR) | District 2 (Caldwell, Christian, Daviess, Hancock, Henderson, Hopkins, McLean, Muhlenberg, Ohio, Union, & Webster counties) | Muhlenberg County Fiscal Court 089CR 1245 Friendship Road | Progress | Yes |  | Scotty's Contracting and stone | 2519 | 320760 | 322241.24 | 100 | Yes |  | 322241.24 | 2025-12-11
2025-12-11 09:23 | 2025-12-11 09:48 | Nicholas County Fiscal Court | Q2 (October 1-December 31) | County (CR) | District 9 (Bath, Boyd, Carter, Elliott, Fleming, Greenup, Lewis, Mason, Nicholas, and Rowan counties) | Nicholas County Fiscal Court CR 1102 Locust Grove | Progress | Yes |  | Hinkle Construction | 3229 | 570000 | 556552.09 | 100 | Yes |  | 556552.09 | 2025-09-11
2025-12-10 11:27 | 2025-12-10 11:30 | Owen County Fiscal Court | Q2 (October 1-December 31) | County (CR) | District 6 (Boone, Bracken, Campbell, Carroll, Gallatin, Grant, Harrison, Kenton, Owen, Pendleton, and Robertson counties) | Owen County Fiscal Court CR 1144 Fox Trail | No progress | [8 empty] | 2026-03-31
2025-12-10 11:21 | 2025-12-10 12:07 | Russell County Fiscal Court | Q2 (October 1-December 31) | County (CR) | District 8 (Adair, Casey, Clinton, Cumberland, Lincoln, McCreary, Pulaski, Rockcastle, Russell, and Wayne counties) | Russell County Fiscal Court CR 1737 Kara Lane | Progress | Yes |  | Gaddie Shamrock | N/A | 50429.61 | 50429.61 | 100 | Yes |  | 50429.61 | 2025-10-16
2026-01-14 10:35 | 2026-01-14 10:38 | City of Stamping Ground | Q2 (October 1-December 31) | City (CS) |  |  | No progress | [8 empty] | 2026-06-01
2025-12-10 11:49 | 2025-12-10 11:54 | Todd County Fiscal Court | Q2 (October 1-December 31) | County (CR) | District 3 (Allen, Barren, Butler, Edmonson, Logan, Metcalfe, Monroe, Simpson, Todd and Warren counties) | Todd County Fiscal Court CR 1231 Morton Lane | Progress | Yes |  | Scotty's Contracting | 2519 | 296000 | 73004.9 | 100 | Yes |  | 84611 | 2025-10-31
2025-12-10 14:10 | 2025-12-10 14:17 | Webster County Fiscal Court ( Road Department ) | Q2 (October 1-December 31) | County (CR) | District 2 (Caldwell, Christian, Daviess, Hancock, Henderson, Hopkins, McLean, Muhlenberg, Ohio, Union, & Webster counties) | Webster County Fiscal Court CR 1306 Andy Sisk | No progress | [8 empty] | 2026-04-07
2025-12-10 14:17 | 2025-12-10 14:19 | Webster County Fiscal Court ( Road Department ) | Q2 (October 1-December 31) | County (CR) | District 2 (Caldwell, Christian, Daviess, Hancock, Henderson, Hopkins, McLean, Muhlenberg, Ohio, Union, & Webster counties) | Webster County Fiscal Court CR 1325 Waggoner Chalybeate | No progress | [8 empty] | 2026-04-15
*Denotes project complete | [6 empty] | ***THIS QUARTERLY REPORT HAS BEEN COMPILED WITH INFORMATION SUBMITTED BY THE COUNTY/CITY.
AWAITING RESPONSE FROM OPEN PROJECTS:
| Boyd | Boyd County Fiscal Court | Stephens Meade Road | CR 1337B
| Boyd | Boyd County Fiscal Court | Twin Ridge Road | CR 1242
| Bracken | Bracken County Fiscal Court | Ford's Avenue | CR 1214
| Bracken | Bracken County Fiscal Court | Thompson Ridge | CR 1111
| Breathitt | Breathitt County Fiscal Court | Strong Branch Road | CR 1146
| Breathitt | Breathitt County Fiscal Court | Hardshell Caney Road | CR 1117
| Breckinridge | Breckinridge County Fiscal Court | Harold Lucas Lane | CR 1040
| Christian | Christian County Fiscal Court | Britmart Road | CR 1069
| Clark | Clark County Fiscal Court | Oil Springs Road | CR 1105
| Clay | Clay County Fiscal Court | Whites Branch | CR 1249
| Cumberland | Cumberland County Fiscal Court | Bethel Scott Road | CR 1287
| Floyd | Floyd County Fiscal Court | Conley Fork of Spurlock | CR 1423
| Floyd | Floyd County Fiscal Court | Old Hunter Road | CR 1238
| Gallatin | Gallatin County Fiscal Court | Vera Cruz Road | CR 1201
| Gallatin | Gallatin County Fiscal Court | Knox Lillard Road#2 | CR 1208
| Grant | Grant County Fiscal Court | Lanter Road | CR 1027
| Grayson | Grayson County Fiscal Court | Hickory Flats Road | CR 1634
| Grayson | Grayson County Fiscal Court | Eveleigh Road | CR 1094
| McLean | McLean County Fiscal Court | Nuchols/Old Buck Creek Road | CR 1009
| McLean | McLean County Fiscal Court | Hicks Road | CR 1006
| LaRue | LaRue County Fiscal Court | Cruse Road | CR 1214
| Morgan | Morgan County Fiscal Court | Old HWY 172 | CR 1558
| Morgan | Morgan County Fiscal Court | Ivy Lane | CR 1515
| Nelson | Nelson County Fiscal Court | Shady Lane | CR 1241
| Nelson | Nelson County Fiscal Court | Yates Cooney Neck Road | CR 1022
| McLean | McLean County Fiscal Court | Hicks Road | CR 1006
| McLean | McLean County Fiscal Court | Nuchols/Old Buck Creek Road | CR 1009
| Pendleton | Pendleton County Fiscal Court | Lenoxburg Road | CR 1064
| Perry | Perry County Fiscal Court | Colwell Fork Road | 097 CR 1314
| Perry | Perry County Fiscal Court | Wells Fork Road | CR 1229
| Powell | Powell County Fiscal Court | Old Winchester Road | CR 1307
| Powell | Powell County Fiscal Court | Copperras Creek Road | CR 1306
| Pike | Pike County Fiscal Court | Sycamore Road | CR 1351Q4
| Taylor | Taylor County Fiscal Court | Cuddler Creek | CR 1017
| Warren | Warren County Fiscal Court | Vance Lane | CR 1284
| Wolfe | Wolfe County Fiscal Court | Cable Ridge Road | CR 1288
| Wolfe | Wolfe County Fiscal Court | Smokey Branch Road | CR 1204

## Cities Q2 2026
Qtrly Report Start Time | Qtrly Report Completion Time | Organization Name | FY2026 Reporting Quarter | Is this project a City or County road? | District | City Project/Roadway Name | Progress on project? | Has your project been advertised and let? | Are you planning to do the project yourself? | Name of Contractor | Contractor State Vendor # | Contractor awarded contract amount | Contractor current amount earned | Contract percentage of work completed | Have you completed the project? | Estimated date for completion of project | Final actual cost to complete the project | Actual contract completion date
2025-10-27 07:14 | 2025-10-27 07:16 | City of Lancaster | Q1 (July 1-Sept 30) | City (CS) |  | City of Lancaster CS 1017 S. Campbell | Progress | Yes |  | The Allen Company | 11111 | 108000 | 0 | 0 | No | 2025-11-26
2025-10-27 07:16 | 2025-10-27 07:17 | City of Lancaster | Q1 (July 1-Sept 30) | City (CS) |  | City of Lancaster CS 1056 Hamilton Avenue | Progress | Yes |  | The Allen Company | 11111 | 0 | 0 | 0 | No | 2026-05-30
2025-12-10 11:21 | 2025-12-10 12:07 | Russell County Fiscal Court | Q2 (October 1-December 31) | County (CR) | District 8 (Adair, Casey, Clinton, Cumberland, Lincoln, McCreary, Pulaski, Rockcastle, Russell, and Wayne counties) |  | Progress | Yes |  | Gaddie Shamrock | N/A | 50429.61 | 50429.61 | 100 | Yes |  | 50429.61 | 2025-10-16
2025-12-10 11:26 | 2025-12-10 14:46 | Ballard County Fiscal Court | Q2 (October 1-December 31) | County (CR) | District 1 (Ballard, Calloway, Carlisle, Crittenden, Fulton, Graves, Hickman, Livingston, Lyon, Marshall, McCracken, & Trigg counties) |  | Progress | Yes |  | Jim Smith Construction | 2618 | 125000 | 120000 | 100 | Yes |  | 120000 | 2025-10-30
2025-12-10 11:27 | 2025-12-10 11:30 | Owen County Fiscal Court | Q2 (October 1-December 31) | County (CR) | District 6 (Boone, Bracken, Campbell, Carroll, Gallatin, Grant, Harrison, Kenton, Owen, Pendleton, and Robertson counties) |  | No progress | [8 empty] | 2026-03-31
2025-12-10 11:38 | 2025-12-10 12:12 | Monroe County Fiscal Court | Q2 (October 1-December 31) | County (CR) | District 3 (Allen, Barren, Butler, Edmonson, Logan, Metcalfe, Monroe, Simpson, Todd and Warren counties) |  | Progress | Yes |  | Scotty's Contracting & Stone | 2519 | 3000 | 3000 | 100 | Yes |  | 3000 | 2025-11-01
2025-12-10 11:49 | 2025-12-10 11:54 | Todd County Fiscal Court | Q2 (October 1-December 31) | County (CR) | District 3 (Allen, Barren, Butler, Edmonson, Logan, Metcalfe, Monroe, Simpson, Todd and Warren counties) |  | Progress | Yes |  | Scotty's Contracting | 2519 | 296000 | 73004.9 | 100 | Yes |  | 84611 | 2025-10-31
2025-12-10 11:54 | 2025-12-10 12:00 | Carter County Fiscal Court | Q2 (October 1-December 31) | County (CR) | District 9 (Bath, Boyd, Carter, Elliott, Fleming, Greenup, Lewis, Mason, Nicholas, and Rowan counties) |  | Progress | Yes |  | Mountain Enterprises | 2938 | 345571.05 | 345571.05 | 100 | Yes |  | 345571.05 | 2025-10-09
2025-12-10 11:57 | 2025-12-10 11:59 | Breckinridge County Fiscal Court | Q2 (October 1-December 31) | County (CR) | District 4 (Breckinridge, Grayson, Green, Hardin, Hart, LaR​​​​​​ue, Marion, Meade, Nelson, Taylor, and Washington counties) |  | No progress | [8 empty] | 2026-05-29
2025-12-10 12:00 | 2025-12-10 12:02 | Carter County Fiscal Court | Q2 (October 1-December 31) | County (CR) | District 9 (Bath, Boyd, Carter, Elliott, Fleming, Greenup, Lewis, Mason, Nicholas, and Rowan counties) |  | Progress | Yes |  | Mountain Enterprises | 2938 | 161646.26 | 161646.26 | 100 | Yes |  | 161646.26 | 2025-10-02
2025-12-10 13:12 | 2025-12-10 13:13 | Lyon County Fiscal Court | Q2 (October 1-December 31) | County (CR) | District 1 (Ballard, Calloway, Carlisle, Crittenden, Fulton, Graves, Hickman, Livingston, Lyon, Marshall, McCracken, & Trigg counties) |  | No progress | [8 empty] | 2026-10-30
2025-12-10 13:13 | 2025-12-10 13:14 | Lyon County Fiscal Court | Q2 (October 1-December 31) | County (CR) | District 1 (Ballard, Calloway, Carlisle, Crittenden, Fulton, Graves, Hickman, Livingston, Lyon, Marshall, McCracken, & Trigg counties) |  | No progress | [8 empty] | 2026-10-30
2025-12-10 13:25 | 2025-12-10 13:26 | Crittenden County Fiscal Court | Q2 (October 1-December 31) | County (CR) | District 1 (Ballard, Calloway, Carlisle, Crittenden, Fulton, Graves, Hickman, Livingston, Lyon, Marshall, McCracken, & Trigg counties) |  | No progress | [8 empty] | 2026-04-30
2025-12-10 13:26 | 2025-12-10 13:27 | Crittenden County Fiscal Court | Q2 (October 1-December 31) | County (CR) | District 1 (Ballard, Calloway, Carlisle, Crittenden, Fulton, Graves, Hickman, Livingston, Lyon, Marshall, McCracken, & Trigg counties) |  | No progress | [8 empty] | 2026-04-30
2025-12-10 13:35 | 2025-12-10 13:41 | City of Lebanon | Q2 (October 1-December 31) | City (CS) |  | City of Lebanon CS 1036 E. Mulberry St. | Progress | Yes |  | Nally and Haydon | 85472 | 42000 | 42000 | 100 | No | 2025-04-25
2025-12-10 13:57 | 2025-12-10 13:59 | Livingston County Fiscal Court | Q2 (October 1-December 31) | County (CR) | District 1 (Ballard, Calloway, Carlisle, Crittenden, Fulton, Graves, Hickman, Livingston, Lyon, Marshall, McCracken, & Trigg counties) |  | No progress | [8 empty] | 2026-05-30
2025-12-10 13:59 | 2025-12-10 14:04 | CITY OF HARLAN KY | Q2 (October 1-December 31) | City (CS) |  | City of Harlan CS 1050 Oak Street | Progress | Yes |  | MOUNTAIN ENTERPRISES, INC | 0 | 30000 | 0 | 0 | No | 2026-05-31
2025-12-10 13:59 | 2025-12-10 14:00 | Livingston County Fiscal Court | Q2 (October 1-December 31) | County (CR) | District 1 (Ballard, Calloway, Carlisle, Crittenden, Fulton, Graves, Hickman, Livingston, Lyon, Marshall, McCracken, & Trigg counties) |  | No progress | [8 empty] | 2026-05-30
2025-12-10 14:10 | 2025-12-10 14:17 | Webster County Fiscal Court ( Road Department ) | Q2 (October 1-December 31) | County (CR) | District 2 (Caldwell, Christian, Daviess, Hancock, Henderson, Hopkins, McLean, Muhlenberg, Ohio, Union, & Webster counties) |  | No progress | [8 empty] | 2026-04-07
2025-12-10 14:17 | 2025-12-10 14:19 | Webster County Fiscal Court ( Road Department ) | Q2 (October 1-December 31) | County (CR) | District 2 (Caldwell, Christian, Daviess, Hancock, Henderson, Hopkins, McLean, Muhlenberg, Ohio, Union, & Webster counties) |  | No progress | [8 empty] | 2026-04-15
2025-12-10 15:02 | 2025-12-10 15:09 | Bourbon County Fiscal Court | Q2 (October 1-December 31) | County (CR) | District 7 (Anderson, Bourbon, Boyle, Clark, Fayette, Garrard, Jessamine, Madison, Mercer, Montgomery, Scott, and Woodford counties) |  | No progress | [8 empty] | 2026-06-01
2025-12-10 15:40 | 2025-12-10 15:47 | McCracken County Fiscal Court | Q2 (October 1-December 31) | County (CR) | District 1 (Ballard, Calloway, Carlisle, Crittenden, Fulton, Graves, Hickman, Livingston, Lyon, Marshall, McCracken, & Trigg counties) |  | Progress | No | Yes |  |  |  |  | 95 | No | 2025-12-31
2025-12-11 08:04 | 2025-12-11 08:07 | Johnson County Fiscal Court | Q2 (October 1-December 31) | County (CR) | District 12 (Floyd, Johnson, Knott, Lawrence, Letcher, Martin & Pike counties) |  | No progress | [8 empty] | 2026-04-15
2025-12-11 08:07 | 2025-12-11 08:09 | Johnson County Fiscal Court | Q2 (October 1-December 31) | County (CR) | District 12 (Floyd, Johnson, Knott, Lawrence, Letcher, Martin & Pike counties) |  | No progress | [8 empty] | 2026-08-15
2025-12-11 08:26 | 2025-12-11 08:30 | Allen County Fiscal Court | Q2 (October 1-December 31) | County (CR) | District 3 (Allen, Barren, Butler, Edmonson, Logan, Metcalfe, Monroe, Simpson, Todd and Warren counties) |  | Progress | Yes |  | Scotty's | 2519 | 67462.47 | 67462.47 | 100 | Yes |  | 67462.47 | 2025-08-04
2025-12-11 08:55 | 2025-12-15 09:30 | Carroll County Fiscal Court | Q2 (October 1-December 31) | County (CR) | District 6 (Boone, Bracken, Campbell, Carroll, Gallatin, Grant, Harrison, Kenton, Owen, Pendleton, and Robertson counties) |  | Progress | Yes |  | Hinkle Contracting | 3229 | 4027.14 | 4027.14 | 100 | Yes |  | 4027.14 | 2024-11-27
2025-12-11 08:57 | 2025-12-11 09:13 | Hart County Fiscal Court | Q2 (October 1-December 31) | County (CR) | District 4 (Breckinridge, Grayson, Green, Hardin, Hart, LaR​​​​​​ue, Marion, Meade, Nelson, Taylor, and Washington counties) |  | Progress | Yes |  | Scotty's Contracting | 2519 | 159296.9 | 159296.9 | 100 | Yes |  | 159296.9 | 2025-09-30
2025-12-11 09:14 | 2025-12-11 09:17 | Hart County Fiscal Court | Q2 (October 1-December 31) | County (CR) | District 4 (Breckinridge, Grayson, Green, Hardin, Hart, LaR​​​​​​ue, Marion, Meade, Nelson, Taylor, and Washington counties) |  | Progress | Yes |  | Scotty's Contracting | 2519 | 218771.82 | 218771.82 | 100 | Yes |  | 218771.82 | 2025-09-30
2025-12-11 09:23 | 2025-12-11 09:48 | nicholas county fiscal court | Q2 (October 1-December 31) | County (CR) | District 9 (Bath, Boyd, Carter, Elliott, Fleming, Greenup, Lewis, Mason, Nicholas, and Rowan counties) |  | Progress | Yes |  | Hinkle Construction | 3229 | 570000 | 556552.09 | 100 | Yes |  | 556552.09 | 2025-09-11
2025-12-11 10:50 | 2025-12-11 10:59 | Barren County Fiscal Court | Q2 (October 1-December 31) | County (CR) | District 3 (Allen, Barren, Butler, Edmonson, Logan, Metcalfe, Monroe, Simpson, Todd and Warren counties) |  | Progress | Yes |  | Scotty's Contracting | 2519 | 384823.9 | 349173.82 | 100 | Yes |  | 349173.82 | 2025-08-25
2025-12-11 11:51 | 2025-12-11 11:52 | Elliott Fiscal Court | Q2 (October 1-December 31) | County (CR) | District 9 (Bath, Boyd, Carter, Elliott, Fleming, Greenup, Lewis, Mason, Nicholas, and Rowan counties) |  | No progress | [8 empty] | 2026-05-30
2025-12-11 11:52 | 2025-12-11 11:53 | Elliott Fiscal Court | Q2 (October 1-December 31) | County (CR) | District 9 (Bath, Boyd, Carter, Elliott, Fleming, Greenup, Lewis, Mason, Nicholas, and Rowan counties) |  | No progress | [8 empty] | 2026-05-31
2025-12-11 12:05 | 2025-12-11 12:06 | Jackson County Fiscal Court | Q2 (October 1-December 31) | County (CR) | District 11 (Bell, Clay, Harlan, Jackson, Knox, Laurel, Leslie, and Whitley counties) |  | No progress | [8 empty] | 2026-04-13
2025-12-11 15:47 | 2025-12-11 16:09 | Barren County Fiscal Court | Q2 (October 1-December 31) | County (CR) | District 3 (Allen, Barren, Butler, Edmonson, Logan, Metcalfe, Monroe, Simpson, Todd and Warren counties) |  | Progress | Yes |  | Scotty's Contracting | 2519 | 119487.5 | 0 | 100 | Yes |  | 119487.5 | 2025-10-21
2025-12-11 16:28 | 2025-12-12 14:27 | Magoffin County Fiscal Court | Q2 (October 1-December 31) | County (CR) | District 10 ( Breathitt, Estill, Lee, Magoffin, Menifee, Morgan, Owsley, Perry, Powell, and Wolfe counties) |  | Progress | Yes |  | Hinkle Contracting | 28986 | 33000 | 32244.66 | 100 | Yes |  | 32244.66 | 2025-10-23
2025-12-12 11:21 | 2025-12-12 11:26 | Adair County Fiscal Court | Q2 (October 1-December 31) | County (CR) | District 8 (Adair, Casey, Clinton, Cumberland, Lincoln, McCreary, Pulaski, Rockcastle, Russell, and Wayne counties) |  | Progress | Yes |  | Gaddie Shamrock | 2493 | 192000 | 191861.52 | 100 | Yes |  | 191861.52 | 2025-11-22
2025-12-12 11:26 | 2025-12-12 11:30 | Adair County Fiscal Court | Q2 (October 1-December 31) | County (CR) | District 8 (Adair, Casey, Clinton, Cumberland, Lincoln, McCreary, Pulaski, Rockcastle, Russell, and Wayne counties) |  | Progress | Yes |  | Gaddie Shamrock | 2493 | 120000 | 119960.92 | 100 | Yes |  | 119960.92 | 2025-11-21
2025-12-12 13:02 | 2025-12-12 13:04 | Martin County Fiscal Court | Q2 (October 1-December 31) | County (CR) | District 12 (Floyd, Johnson, Knott, Lawrence, Letcher, Martin & Pike counties) |  | Progress | Yes |  | Hinkle Blacktop LLC | 4046 | 118 | 116227.02 | 100 | Yes |  | 116227.02 | 2025-11-13
2025-12-12 13:04 | 2025-12-12 13:15 | Martin County Fiscal Court | Q2 (October 1-December 31) | County (CR) | District 12 (Floyd, Johnson, Knott, Lawrence, Letcher, Martin & Pike counties) |  | Progress | Yes |  | Hinkle Blacktop LLC | 4046 | 110 | 0 | 100 | Yes |  | 0 | 2025-12-01
2025-12-16 13:33 | 2025-12-16 13:35 | Bell County Fiscal Court | Q2 (October 1-December 31) | County (CR) | District 11 (Bell, Clay, Harlan, Jackson, Knox, Laurel, Leslie, and Whitley counties) |  | No progress | [8 empty] | 2026-05-01
2025-12-18 09:59 | 2025-12-18 10:21 | Letcher County Fiscal Court | Q2 (October 1-December 31) | County (CR) | District 12 (Floyd, Johnson, Knott, Lawrence, Letcher, Martin & Pike counties) |  | Progress | Yes |  | Mountain Enterprise | 0 | 67000 | 4148.32 | 100 | Yes |  | 4148.32 | 2025-12-11
2025-12-18 10:21 | 2025-12-18 10:22 | Letcher County Fiscal Court | Q2 (October 1-December 31) | County (CR) | District 12 (Floyd, Johnson, Knott, Lawrence, Letcher, Martin & Pike counties) |  | No progress | [8 empty] | 2026-03-31
2025-12-19 10:45 | 2025-12-19 12:36 | FLEMING COUNTY FISCAL COURT | Q2 (October 1-December 31) | County (CR) | District 9 (Bath, Boyd, Carter, Elliott, Fleming, Greenup, Lewis, Mason, Nicholas, and Rowan counties) |  | Progress | Yes |  | H G MAYS | 360 | 223000 | 193253 | 100 | Yes |  | 193253 | 2025-09-23
2025-12-19 12:45 | 2025-12-19 13:10 | Clark County Fiscal Court | Q2 (October 1-December 31) | County (CR) | District 7 (Anderson, Bourbon, Boyle, Clark, Fayette, Garrard, Jessamine, Madison, Mercer, Montgomery, Scott, and Woodford counties) |  | Progress | Yes |  | The Allen Company | 135 | 333359.83 | 333359.83 | 100 | Yes |  | 333359.83 | 2025-11-24
2025-12-29 10:59 | 2025-12-29 11:00 | Harlan County Fiscal Court | Q2 (October 1-December 31) | County (CR) | District 11 (Bell, Clay, Harlan, Jackson, Knox, Laurel, Leslie, and Whitley counties) |  | No progress | [8 empty] | 2026-06-30
2025-12-29 16:25 | 2025-12-29 16:58 | Muhlenberg County Fiscal Court | Q2 (October 1-December 31) | County (CR) | District 2 (Caldwell, Christian, Daviess, Hancock, Henderson, Hopkins, McLean, Muhlenberg, Ohio, Union, & Webster counties) |  | Progress | Yes |  | Scotty's Contracting and stone | 2519 | 320760 | 322241.24 | 100 | Yes |  | 322241.24 | 2025-12-11
2026-01-03 10:38 | 2026-01-03 10:40 | City of Lancaster | Q2 (October 1-December 31) | City (CS) |  | City of Lancaster CS 1017 S. Campbell | Progress | Yes |  | The Allen Company | 12345 | 108000 | 0 | 0 | No | 2026-03-31
2026-01-03 10:40 | 2026-01-03 10:42 | City of Lancaster | Q2 (October 1-December 31) | City (CS) |  | City of Lancaster CS 1056 Hamilton Avenue | Progress | Yes |  | N/a - it was advertised but not awarded yet | 12345 | 0 | 0 | 0 | No | 2026-05-31
2026-01-06 13:15 | 2026-01-06 13:44 | Hardin County Fiscal Court | Q2 (October 1-December 31) | County (CR) | District 4 (Breckinridge, Grayson, Green, Hardin, Hart, LaR​​​​​​ue, Marion, Meade, Nelson, Taylor, and Washington counties) |  | Progress | Yes |  | Scotty's Contracting and Stone | 2519 | 281932.32 | 281932.32 | 100 | Yes |  | 281932.32 | 2025-10-27
2026-01-06 13:44 | 2026-01-06 13:49 | Hardin County Fiscal Court | Q1 (July 1-Sept 30) | County (CR) | District 4 (Breckinridge, Grayson, Green, Hardin, Hart, LaR​​​​​​ue, Marion, Meade, Nelson, Taylor, and Washington counties) |  | Progress | Yes |  | Scotty' Contracting and Stone | 2519 | 137346.71 | 137346.71 | 100 | Yes |  | 137346.71 | 2025-09-02
2026-01-06 13:45 | 2026-01-06 13:49 | Boyle County Fiscal Court | Q2 (October 1-December 31) | County (CR) | District 7 (Anderson, Bourbon, Boyle, Clark, Fayette, Garrard, Jessamine, Madison, Mercer, Montgomery, Scott, and Woodford counties) |  | Progress | Yes |  | The Allen Company | 135 | 46000 | 46000 | 100 | No | 2025-05-09
2026-01-07 09:09 | 2026-01-07 09:26 | Estill County Fiscal Court | Q2 (October 1-December 31) | County (CR) | District 10 ( Breathitt, Estill, Lee, Magoffin, Menifee, Morgan, Owsley, Perry, Powell, and Wolfe counties) |  | Progress | Yes |  | Hinkle Contracting Corporation | 28986 | 173988 | 173099.84 | 100 | Yes |  | 173099.84 | 2025-12-02
2026-01-07 09:27 | 2026-01-07 09:30 | Estill County Fiscal Court | Q2 (October 1-December 31) | County (CR) | District 10 ( Breathitt, Estill, Lee, Magoffin, Menifee, Morgan, Owsley, Perry, Powell, and Wolfe counties) |  | Progress | Yes |  | Hinkle Contracting Company, LLC | 28986 | 302049 | 299190.11 | 100 | Yes |  | 299190.11 | 2025-12-02
2026-01-12 15:18 | 2026-01-12 15:30 | Harlan County Fiscal Court | Q1 (July 1-Sept 30) | County (CR) | District 11 (Bell, Clay, Harlan, Jackson, Knox, Laurel, Leslie, and Whitley counties) |  | No progress | [8 empty] | 2026-05-30
2026-01-14 10:35 | 2026-01-14 10:38 | City of Stamping Ground | Q2 (October 1-December 31) | City (CS) |  | City of Stamping CS 3016 Commonwealth Drive | No progress | [8 empty] | 2026-06-01
2026-01-14 12:14 | 2026-01-14 12:20 | Lawrence County | Q2 (October 1-December 31) | County (CR) | District 12 (Floyd, Johnson, Knott, Lawrence, Letcher, Martin & Pike counties) |  | Progress | Yes |  | Blacktop Industries | 0 | 83560.52 | 83560.52 | 100 | Yes |  | 83560.52 | 2025-11-29
2026-01-14 12:20 | 2026-01-14 12:23 | Lawrence County | Q2 (October 1-December 31) | County (CR) | District 12 (Floyd, Johnson, Knott, Lawrence, Letcher, Martin & Pike counties) |  | No progress | [8 empty] | 2026-04-30
2026-01-15 13:04 | 2026-01-15 14:01 | Greenup County Fiscal Court | Q2 (October 1-December 31) | County (CR) | District 9 (Bath, Boyd, Carter, Elliott, Fleming, Greenup, Lewis, Mason, Nicholas, and Rowan counties) |  | Progress | Yes |  | Mountain Enterprises | 2938 | 122221 | 123017.99 | 100 | Yes |  | 123017.99 | 2025-11-24
*Denotes report made after Q1 deadline. | [6 empty] | ***THIS QUARTERLY REPORT HAS BEEN COMPILED WITH INFORMATION SUBMITTED BY THE COUNTY/CITY.
AWAITING RESPONSE FROM OPEN PROJECTS:
|  | City of Middlesboro | Lower Gibson Lane | CS 2306
|  | City of Paris | Springhill Drive | CS 1105
|  | City of Bardwell | Front St. | CS 1028
|  | City of Bardwell | East Court Street | CS 1014
|  | City of Central City | Park Street | CS 2121
|  | City of Edmonton | Hill Street | CS 1007
|  | City of Edmonton | River Road | CS 1065
|  | City of Fort Thomas | James Avenue | CS 4036
|  | City of Frankfort | C. Michael Davenport Blvd | CS 1429
|  | City of Franklin | Breckinridge Street | CS 1025
|  | City of Hodgenville | College St. | CS 1076
|  | City of Lebanon | E. Mulberry St. | CS 1036
|  | City of Liberty | Combest Street | CS 1015
|  | City of Paris | Springhill Drive | CS 1105
|  | City of Oakgrove | Oak Tree Dr. | CS 5036
|  | City of Salyersville | Coal Branch Road | CS 1017