## Rollup (hidden)
Summary of Capital Projects
Data Updated Through 12/02/19
Cabinet Wide Rollup
| Total Current Budget | Total Unobligated | Total Cash Balance
| #REF! | #REF! | #REF!
Project Management | #REF! | #REF! | #REF!
Heritage Land | #REF! | #REF! | #REF!
Maintenance Pool | #REF! | #REF! | #REF!
Various | #REF! | #REF! | #REF!
| Total Current Budget | Total Unobligated | Total Cash balance
HWMF | #REF! | #REF! | #REF!
Dept | Fund | Fund Name | Active Status | Current Budget | Unobligated | Cash Balance | Project Initiation Date | EEC Contacts | Estimated Completion Date | Notes
129 | C1H6 | HWMF-Various Projects | Active | 7975600 | 358760.92 | 128461.68 | 1993-04-23 | Hughes, Larry
129 | C2PV | HWMF-KY Tie & Timber | Active | #REF! | #REF! | #REF! | 2006-06-02
129 | C2PW | HWMF-Kim's Dry Cleaners | Active | #REF! | #REF! | #REF! | 2006-06-03 | Hancock, Nathan
129 | C4Q7 | HWMF-Louisville Environmental Services | Active | 507700 | 13968.9 | 39130.13 | 2008-05-09 | Hancock, Nathan
129 | C52F | HWMF-Distler Brickyard | Active | 204871.93 | 23700 | 23700 | 2009-04-15
129 | C52G | HWMF-Distler Farm | Active | 159577.99 | 7140 | 7140 | 2009-04-15
129 | C5GL | HWMF - Lees Lane Project | Active | 135000 | 59832.13 | 59832.13 | 2010-06-01 | Uhlenbruch, Christopher
129 | C6AM | HWMF - Jackson's Pronto Cleaners | Active | 46575 | 10748.01 | 11909.01 | 2016-12-01 | Kirby, Jim
129 | C6D2 | HWMF-Familee Laundry Phase 2 | Active | #REF! | #REF! | #REF! | 2012-05-18 | Brown, Eric
129 | C7TQ | HWMF-Former Bill's Quality Cleaners | Active | 65000 | 43552.4 | 43552.4 | 2014-12-11 | Brown, Eric
129 | C7TR | HWMF-Parrish Avenue | Active | 197400 | 63150.26 | 65742.48 | 2014-12-15 | Brown, Eric
129 | C7TS | HWMF-Miracle Dry Cleaners | Active | 161900 | 13004.5 | 13004.5 | 2014-11-11 | Grow, Jeff
129 | C83A | HWMF-Former West Point Bank Property | Active | 195000 | 122359.3 | 22359.3 | 2015-12-17 | Hancock, Nathan
129 | C83G | HWMF-Clark and Riggs | Active | 18900 | 9403 | 9403 | 2015-11-11 | Hancock, Nathan
129 | C83H | HWMF-West KY Wildlife Area Burn Site | Active | #REF! | #REF! | #REF! | 2015-11-11 | Hancock, Nathan
129 | C8SC | HWMF-A&S Tools and Gage | Active | #REF! | #REF! | #REF! | 2017-08-17
129 | C8X0 | HWMF-Wiley Property | Active | 75000 | 42050 | 42050 | 2018-02-26 | Brown, Eric
129 | C8ZG | HWMF-Former Henry Vogt Machine Co | Active | #REF! | #REF! | #REF! | 2018-06-05 | Hancock, Nathan
129 | C95Q | HWMF-Southern Wood Treatment-Long's Lane Op. & Maint Phase | Active | 455900 | 368305 | 377902.5 | 2018-08-10 | Brown, Eric
129 | C9FV | HWMF-Sam Meyers Formal Wear | Active | 70000 | 55241.62 | 70000 | 2019-09-28 | Cary, Brent
129 | C9FW | HWMF-Former Hartco | Active | #REF! | #REF! | #REF! | 2019-09-28 | Hancock, Nathan
129 | C9FX | HWMF-Mount Sterling City Landfill | Active | 132600 | 42321.61 | 42321.61 | 2019-09-28 | Polly, Derek
129 | C9G5 | HWMF-Jefferson Memorial Forest | Active | 20000 | 20000 | 20000 | 2019-09-28 | Hancock, Nathan
| Total Current Budget | Total Unobligated | Total Cash balance
PRIDE | #REF! | #REF! | #REF!
Dept | Fund | Fund Name | Active Status | Current Budget | Unobligated | Cash Balance | Project Initiation Date | EEC Contacts | Estimated Completion Date | Notes
129 | C5Y8 | PRIDE-Mt. Sterling Landfill | Active | #REF! | #REF! | #REF! | 2011-05-24
129 | C62D | PRIDE - Johnson County Landfill | Active | #REF! | #REF! | #REF! | 2011-08-09 | Melton, Ken
129 | C70B | PRIDE - Butler Co. Landfill | Active | #REF! | #REF! | #REF! | 2014-04-21 | Melton, Ken
129 | C713 | PRIDE-Mercer County Landfill | Active | #REF! | #REF! | #REF! | 2014-06-09
129 | C714 | PRIDE-Well Abandonment at Closed Landfills | Active | #REF! | #REF! | #REF! | 2014-06-09
129 | C7UQ | PRIDE-Bullitt County Historic Landfill | Active | #REF! | #REF! | #REF! | 2015-02-12 | Melton, Ken
129 | C7VX | PRIDE-Foothills Sanitary Landfill | Active | #REF! | #REF! | #REF! | 2015-03-27 | Melton, Ken
129 | C7XC | PRIDE-McCracken County Historic Landfill | Active | #REF! | #REF! | #REF! | 2015-05-05 | Melton, Ken
129 | C84E | PRIDE - Covington Landfill | Active | 6883200 | #REF! | #REF! | 2016-02-17 | Melton, Ken
129 | C84L | PRIDE - Goodridge Avenue | Active | #REF! | #REF! | #REF! | 2016-02-17 | Melton, Ken
129 | C8CW | PRIDE- City of Cadiz | Active | #REF! | #REF! | #REF! | 2016-07-19
129 | C8J1 | PRIDE-Northwest-Central Site Characterization | Active | 2760000 | #REF! | #REF! | 2017-01-13 | Melton, Ken
129 | C8J4 | PRIDE- South Central Site Characterization | Active | 575000 | #REF! | #REF! | 2017-01-23 | Melton, Ken
129 | C9GR | PRIDE-Butler County Landfill II | Active | #REF! | #REF! | #REF! | 2019-10-01 | Melton, Ken
| Total Current Budget | Total Unobligated | Total Cash balance
UST | 4884900 | 4546777.94 | 4412200
Dept | Fund | Fund Name | Active Status | Current Budget | Unobligated | Cash Balance | Project Initiation Date | EEC Contacts | Estimated Completion Date | Notes
129 | C5PZ | LUST - Clinton Oil & Tire Emergency | Active | 1850000 | 1775000 | 1850000 | 2010-07-06
129 | C7WV | LUST - Logsdon Property | Active | 1850000 | 1756500 | 1850000 | 2015-04-22 | Voisard, Vicki
129 | C8GG | LUST-Mike Winchester Site | Active | 308000 | 308000 | 308000 | 2016-10-19 | Smith, Adam |  | Requested an additional $500,000 in apporpriation this week
129 | C8LX | LUST-Norb Nie | Active | 244200 | 244200 | 244200 | 2017-03-03 | Albright, Michael
129 | C9AL | LUST-Garner Quick Stop | Active | 160000 | 159981.31 | 160000 | 2019-02-26 | Hickerson, Kelly |  | Will be requesting $600,000 in apporpriation within the next week.
129 | C9AM | LUST-Interstate Brands Warehouse | Active | 142000 | 142000 | 0 | 2019-02-26 | Smith, Adam |  | Will be requesting $1,000,000 in apporpriation within the next week.
129 | C9AZ | LUST-Sportman Market | Active | 183000 | 161096.63 | 0 | 2019-03-04 | Highley, Alan |  | Will be requesting $500,000 in apporpriation within the next week.
129 | C9BA | LUST-H&T Stop & Go | Active | 147700 | 0 | 0 | 2019-03-04 | Highley, Alan |  | Will be requesting $500,000 in apporpriation within the next week.
| Total Current Budget | Total Unobligated | Total Cash balance
Maxey Flats | #REF! | #REF! | #REF!
Dept | Fund | Fund Name | Active Status | Current Budget | Unobligated | Cash Balance | Project Initiation Date | EEC Contacts | Estimated Completion Date | Notes
129 | C6BK | Maxey Flats Cap | Active | #REF! | #REF! | #REF! |  | Webb, Jeff | Perpetual
| Total Current Budget | Total Unobligated | Total Cash balance
SODR | #REF! | #REF! | #REF!
Dept | Fund | Fund Name | Active Status | Current Budget | Unobligated | Cash Balance | Project Initiation Date | EEC Contacts | Estimated Completion Date | Notes
129 | C1GH | SODR-Willisburg Lake Dam-Washington County | Active | #REF! | #REF! | #REF! | 2000-07-01
129 | C1GK | SODR Bullock Pen Lake Dam | Active | #REF! | #REF! | #REF! |  | Wells, Gary
129 | C55B | SODR-Scenic Lake Dam | Active | #REF! | #REF! | #REF! | 2009-06-24
129 | C55C | SODR-Beech Creek Dam | Active | #REF! | #REF! | #REF! | 2009-06-24 | Wells, Gary
129 | C93R | State-Owned Dam Repair - 2018-2020 | Active | #REF! | #REF! | #REF!
| Total Current Budget | Total Unobligated | Total Cash balance
MISC-DEP | #REF! | #REF! | #REF!
Dept | Fund | Fund Name | Active Status | Current Budget | Unobligated | Cash Balance | Project Initiation Date | EEC Contacts | Estimated Completion Date | Notes
129 | C562 | A.L. Taylor Site | Active | #REF! | #REF! | #REF! |  |  | Perpetual
129 | C5J2 | Solid Waste - Jones Landfill | Active | #REF! | #REF! | #REF! | 2010-06-22
129 | C8RG | WTTF-Rubberized Asphalt Testing | Active | #REF! | #REF! | #REF! | 2017-08-01
129 | C84J | DEP Central Lab Modifications | Active | #REF! | #REF! | #REF! | 2018-04-24
126 | C852 | EEC Storage Building | Active | #REF! | #REF! | #REF! | 2016-03-17
126 | C9HM | Grede Foundries Site | Active | #REF! | #REF! | #REF! | 2019-10-01
| Total Current Budget | Total Unobligated | Total Cash balance
KHLCF | #REF! | #REF! | #REF!
Dept | Fund | Fund Name | Active Status | Current Budget | Unobligated | Cash Balance | Project Initiation Date | EEC Contacts | Estimated Completion Date | Notes
140 | C0N9 | KHLCF-Adv. Land Acquisition Cost | Active | #REF! | #REF! | #REF! | 1996-08-15 | Frazier, Brent
126 | C1G8 | KHLCF | Active | #REF! | #REF! | #REF! | 2009-04-08
128 | C1J1 | KHLCF-Adv Costs for Land Acquisition | Active | #REF! | #REF! | #REF! | 1996-08-28
140 | C8YA | KHLCF-Green River-Timberlake Tract | Active | #REF! | #REF! | #REF! | 2018-04-24 | Lillpop, Josh & Frazier, Brent
140 | C8YB | KHLCF-Blanton Forest-Coleman Tract | Active | #REF! | #REF! | #REF! | 2018-04-24 | Lillpop, Josh & Frazier, Brent
140 | C8YC | KHLCF-Archer Benge-Hyslope Tract | Active | #REF! | #REF! | #REF! | 2018-04-24
140 | C8YD | KHLCF-Archer Benge-University of Cumberlands Tract | Active | #REF! | #REF! | #REF! | 2018-04-24
140 | C8YJ | KHLCF-Rockcress Hills-Gatewood Tract | Active | #REF! | #REF! | #REF! | 2018-04-24
140 | C97Z | KHLCF-Drennon Creek SNP | Active | #REF! | #REF! | #REF! | 2018-10-25 | Lillpop, Josh & Frazier, Brent
140 | C980 | KHLCF-Red River-Gritter Ridge | Active | #REF! | #REF! | #REF! | 2018-10-25 | Lillpop, Josh & Frazier, Brent
140 | C981 | KHLCF-Eastview Barrens-Ashlock Tract | Active | #REF! | #REF! | #REF! | 2018-10-25 | Lillpop, Josh & Frazier, Brent
| Total Current Budget | Total Unobligated | Total Cash balance
Maintenance Pool | #REF! | #REF! | #REF!
Dept | Fund | Fund Name | Active Status | Current Budget | Unobligated | Cash Balance | Project Initiation Date | EEC Contacts | Estimated Completion Date | Notes
126 | C93Q | Maintenance Pool - 2018-2020 | Active | #REF! | #REF! | #REF!
140 | C68Z | MP-OKNP Maintenance Equipment | Active | #REF! | #REF! | #REF! | 2012-03-06 | Frazier, Brent
140 | C8F7 | MP-Hi Lewis Pine Barrens SNP Abandoned Dwelling | Active | #REF! | #REF! | #REF! | 2016-09-07 | Napier, Kyle
140 | C96E | MP-OKNP-Venon Douglas Parking Lot Gravel and Grading | Active | #REF! | #REF! | #REF! | 2018-08-24
140 | C96F | MP-OKNP-Tom Dorman Parking Area | Active | #REF! | #REF! | #REF! | 2018-08-24
140 | C96G | MP-OKNP-Red River Natural Area House and Barn Demo | Active | #REF! | #REF! | #REF! | 2018-08-24
140 | C96H | MP-OKNP-Blanton Forest Kiosk Bridge Trail Maint. | Active | #REF! | #REF! | #REF! | 2018-08-27
129 | C96D | MP-Maxey Flats Repair/Replace Office Building Roofs | Active | #REF! | #REF! | #REF! | 2018-08-24
128 | C5CJ | MP-North Eastern District | Active | #REF! | #REF! | #REF! | 2010-03-03
128 | C63V | MP-JPRN Soil Replacement | Active | #REF! | #REF! | #REF! | 2011-09-16
128 | C6SB | MP-JPRN Various Projects | Active | #REF! | #REF! | #REF! | 2013-05-14
128 | C8L9 | MP-Bert T. Combs Various Projects | Active | #REF! | #REF! | #REF! | 2017-03-09
128 | C8S4 | MP-State Forest Road & Parking Area Maintenance | Active | #REF! | #REF! | #REF! | 2017-08-02
128 | C96C | MP-JPRN Top Pruner | Active | #REF! | #REF! | #REF! | 2018-08-24

## Project Management Rollup (hidden)
Summary of Capital Projects
Data Updated Through 12/02/19
Project Management Rollup
| Total Current Budget | Total Unobligated | Total Cash Balance
| #REF! | #REF! | #REF!
| Total Current Budget | Total Unobligated | Total Cash balance
HWMF | #REF! | #REF! | #REF!
Dept | Fund | Fund Name | Active Status | Current Budget | Unobligated | Cash Balance | Project Initiation Date | EEC Contacts | Estimated Completion Date | Notes
129 | C1H6 | HWMF-Various Projects | Active | 7975600 | 358760.92 | 128461.68 | 1993-04-23 | Hughes, Larry
129 | C2PV | HWMF-KY Tie & Timber | Active | #REF! | #REF! | #REF! | 2006-06-02
129 | C2PW | HWMF-Kim's Dry Cleaners | Active | #REF! | #REF! | #REF! | 2006-06-03 | Hancock, Nathan
129 | C4Q7 | HWMF-Louisville Environmental Services | Active | 507700 | 13968.9 | 39130.13 | 2008-05-09 | Hancock, Nathan
129 | C52F | HWMF-Distler Brickyard | Active | 204871.93 | 23700 | 23700 | 2009-04-15
129 | C52G | HWMF-Distler Farm | Active | 159577.99 | 7140 | 7140 | 2009-04-15
129 | C5GL | HWMF - Lees Lane Project | Active | 135000 | 59832.13 | 59832.13 | 2010-06-01 | Uhlenbruch, Christopher
129 | C6AM | HWMF - Jackson's Pronto Cleaners | Active | 46575 | 10748.01 | 11909.01 | 2016-12-01 | Kirby, Jim
129 | C6D2 | HWMF-Familee Laundry Phase 2 | Active | #REF! | #REF! | #REF! | 2012-05-18 | Brown, Eric
129 | C7TQ | HWMF-Former Bill's Quality Cleaners | Active | 65000 | 43552.4 | 43552.4 | 2014-12-11 | Brown, Eric
129 | C7TR | HWMF-Parrish Avenue | Active | 197400 | 63150.26 | 65742.48 | 2014-12-15 | Brown, Eric
129 | C7TS | HWMF-Miracle Dry Cleaners | Active | 161900 | 13004.5 | 13004.5 | 2014-11-11 | Grow, Jeff
129 | C83A | HWMF-Former West Point Bank Property | Active | 195000 | 122359.3 | 22359.3 | 2015-12-17 | Hancock, Nathan
129 | C83G | HWMF-Clark and Riggs | Active | 18900 | 9403 | 9403 | 2015-11-11 | Hancock, Nathan
129 | C83H | HWMF-West KY Wildlife Area Burn Site | Active | #REF! | #REF! | #REF! | 2015-11-11 | Hancock, Nathan
129 | C8SC | HWMF-A&S Tools and Gage | Active | #REF! | #REF! | #REF! | 2017-08-17
129 | C8X0 | HWMF-Wiley Property | Active | 75000 | 42050 | 42050 | 2018-02-26 | Brown, Eric
129 | C8ZG | HWMF-Former Henry Vogt Machine Co | Active | #REF! | #REF! | #REF! | 2018-06-05 | Hancock, Nathan
129 | C95Q | HWMF-Southern Wood Treatment-Long's Lane Op. & Maint Phase | Active | 455900 | 368305 | 377902.5 | 2018-08-10 | Brown, Eric
129 | C9FV | HWMF-Sam Meyers Formal Wear | Active | 70000 | 55241.62 | 70000 | 2019-09-28 | Cary, Brent
129 | C9FW | HWMF-Former Hartco | Active | #REF! | #REF! | #REF! | 2019-09-28 | Hancock, Nathan
129 | C9FX | HWMF-Mount Sterling City Landfill | Active | 132600 | 42321.61 | 42321.61 | 2019-09-28 | Polly, Derek
129 | C9G5 | HWMF-Jefferson Memorial Forest | Active | 20000 | 20000 | 20000 | 2019-09-28 | Hancock, Nathan
| Total Current Budget | Total Unobligated | Total Cash balance
PRIDE | #REF! | #REF! | #REF!
Dept | Fund | Fund Name | Active Status | Current Budget | Unobligated | Cash Balance | Project Initiation Date | EEC Contacts | Estimated Completion Date | Notes
129 | C5Y8 | PRIDE-Mt. Sterling Landfill | Active | #REF! | #REF! | #REF! | 2011-05-24
129 | C62D | PRIDE - Johnson County Landfill | Active | #REF! | #REF! | #REF! | 2011-08-09 | Melton, Ken
129 | C70B | PRIDE - Butler Co. Landfill | Active | #REF! | #REF! | #REF! | 2014-04-21 | Melton, Ken
129 | C713 | PRIDE-Mercer County Landfill | Active | #REF! | #REF! | #REF! | 2014-06-09
129 | C714 | PRIDE-Well Abandonment at Closed Landfills | Active | #REF! | #REF! | #REF! | 2014-06-09
129 | C7UQ | PRIDE-Bullitt County Historic Landfill | Active | #REF! | #REF! | #REF! | 2015-02-12 | Melton, Ken
129 | C7VX | PRIDE-Foothills Sanitary Landfill | Active | #REF! | #REF! | #REF! | 2015-03-27 | Melton, Ken
129 | C7XC | PRIDE-McCracken County Historic Landfill | Active | #REF! | #REF! | #REF! | 2015-05-05 | Melton, Ken
129 | C84E | PRIDE - Covington Landfill | Active | 6883200 | #REF! | #REF! | 2016-02-17 | Melton, Ken
129 | C84L | PRIDE - Goodridge Avenue | Active | #REF! | #REF! | #REF! | 2016-02-17 | Melton, Ken
129 | C8CW | PRIDE- City of Cadiz | Active | #REF! | #REF! | #REF! | 2016-07-19
129 | C8J1 | PRIDE-Northwest-Central Site Characterization | Active | 2760000 | #REF! | #REF! | 2017-01-13 | Melton, Ken
129 | C8J4 | PRIDE- South Central Site Characterization | Active | 575000 | #REF! | #REF! | 2017-01-23 | Melton, Ken
129 | C9GR | PRIDE-Butler County Landfill II | Active | #REF! | #REF! | #REF! | 2019-10-01 | Melton, Ken
| Total Current Budget | Total Unobligated | Total Cash balance
UST | 4884900 | 4546777.94 | 4412200
Dept | Fund | Fund Name | Active Status | Current Budget | Unobligated | Cash Balance | Project Initiation Date | EEC Contacts | Estimated Completion Date | Notes
129 | C5PZ | LUST - Clinton Oil & Tire Emergency | Active | 1850000 | 1775000 | 1850000 | 2010-07-06
129 | C7WV | LUST - Logsdon Property | Active | 1850000 | 1756500 | 1850000 | 2015-04-22 | Voisard, Vicki
129 | C8GG | LUST-Mike Winchester Site | Active | 308000 | 308000 | 308000 | 2016-10-19 | Smith, Adam |  | Requested an additional $500,000 in apporpriation this week
129 | C8LX | LUST-Norb Nie | Active | 244200 | 244200 | 244200 | 2017-03-03 | Albright, Michael
129 | C9AL | LUST-Garner Quick Stop | Active | 160000 | 159981.31 | 160000 | 2019-02-26 | Hickerson, Kelly |  | Will be requesting $600,000 in apporpriation within the next week.
129 | C9AM | LUST-Interstate Brands Warehouse | Active | 142000 | 142000 | 0 | 2019-02-26 | Smith, Adam |  | Will be requesting $1,000,000 in apporpriation within the next week.
129 | C9AZ | LUST-Sportman Market | Active | 183000 | 161096.63 | 0 | 2019-03-04 | Highley, Alan |  | Will be requesting $500,000 in apporpriation within the next week.
129 | C9BA | LUST-H&T Stop & Go | Active | 147700 | 0 | 0 | 2019-03-04 | Highley, Alan |  | Will be requesting $500,000 in apporpriation within the next week.
| Total Current Budget | Total Unobligated | Total Cash balance
SODR | #REF! | #REF! | #REF!
Dept | Fund | Fund Name | Active Status | Current Budget | Unobligated | Cash Balance | Project Initiation Date | EEC Contacts | Estimated Completion Date | Notes
129 | C1GH | SODR-Willisburg Lake Dam-Washington County | Active | #REF! | #REF! | #REF! | 2000-07-01
129 | C1GK | SODR Bullock Pen Lake Dam | Active | #REF! | #REF! | #REF! |  | Wells, Gary
129 | C55B | SODR-Scenic Lake Dam | Active | #REF! | #REF! | #REF! | 2009-06-24
129 | C55C | SODR-Beech Creek Dam | Active | #REF! | #REF! | #REF! | 2009-06-24 | Wells, Gary
129 | C93R | State-Owned Dam Repair - 2018-2020 | Active | #REF! | #REF! | #REF!
| Total Current Budget | Total Unobligated | Total Cash balance
MISC-DEP | #REF! | #REF! | #REF!
Dept | Fund | Fund Name | Active Status | Current Budget | Unobligated | Cash Balance | Project Initiation Date | EEC Contacts | Estimated Completion Date | Notes
129 | C5J2 | Solid Waste - Jones Landfill | Active | #REF! | #REF! | #REF! | 2010-06-22

## CALE McKee Edits (hidden)
Updated as of 2/5/2024
Allotments
|  |  | Appropriation |  |  |  | Unobligated
Status | CALE- Superfund Sites | Cash Balance | Current Budget | Encumbrance | Expenditures | Unobligated | E701 | E703 | E166 | Total | Notes
Active | Capital Budget Line Item | 2742279.73 | 2824000 | 0 | 81720.27 | 2742279.73 | 214425 | 1480405 | 47449.73 | 1742279.73 | $1.8 loaded 7/2/2022. $1M loaded 7/5/2023.
|  | Total Expenditures | E701 | E703 | E166 | Notes
Active | 415 Sites with no Viable PRP & RCRA Generator Ranking Project | 62618.87 | 9575 | 3670 | 49373.87 | Testing and Samples
| Big B Cleaners, Hopkins Co- AI# 38519-Soil Characterization |  |  |  | 2500
| SFB-UST Oil Removal - Douglas Nunn Property AI# 174392 |  |  | 3670
| Beacon Environmental-Characterization-Soil Samples-Non IT |  |  |  | 2645
| Coronet Dry Cleaners, Jefferson County - AI# 47888 |  |  |  | 2950
| Coronet Dry Cleaners AI# 47888 - Jefferson County |  |  |  | 1094.4
| SFB - PSG Sample Collection and Analysis - Multiple Sites |  |  |  | 3370
| On the Spot Utility Services |  | 1600
| On the Spot Utility Services |  | 975
| On the Spot Utility Services |  | 1175
| On the Spot Utility Services |  | 1775
| SFB - PSG Sample Collection and Analysis - Multiple Sites |  |  |  | 1505
| SFB - PSG Sample Collection and Analysis - Multiple Sites |  |  |  | 2655
| SFB - PSG Sample Collection and Analysis - Multiple Sites |  |  |  | 1990
| BEACON - UNRETURNED SAMPLER FEE |  |  |  | 50
| SFB - PSG Sample Collection and Analysis - Multiple Sites |  |  |  | 840
| SFB - PSG Sample Collection and Analysis - Multiple Sites |  |  |  | 1530
| SFB - PSG Sample Collection and Analysis - Multiple Sites |  |  |  | 4315
| BEACON - UNRETURNED SAMPLER FEE |  |  |  | 50
| On the Spot Utility Services |  | 825
| On the Spot Utility Services |  | 650
| SFB - PSG Sample Collection and Analysis - Multiple Sites |  |  |  | 300
| SFB - PSG Sample Collection and Analysis - Multiple Sites |  |  |  | 2195
| On the Spot Utility Services |  | 825
| SFB Livermore Plating Project - sampling |  |  |  | 1002.21
| SFB Livermore Plating Project - sampling |  |  |  | 5816.46
| On the Spot Utility Services |  | 925
| SFB - PSG Sample Collection and Analysis - AI# 51529 Plant Cut-Off Road Area of Concern Calvert City |  |  |  | 4980
| On the Spot Utility Services |  | 825
| SFB - PSG Sample Collection and Analysis - Multiple Sites |  |  |  | 3345
| SFB - PSG Sample Collection and Analysis - Multiple Sites |  |  |  | 1810
| Former Peter Pan Dry Cleaner AI# 48115 - Sampling Event |  |  |  | 1921.2
| Hart's Laundry Project AI#37970 - Sample Event |  |  |  | 1004.6
| SFB - PSG Sample Collection and Analysis - Multiple Sites |  |  |  | 1300
| SFB - PSG Sample Collection and Analysis - Multiple Sites |  |  |  | 205
Complete | Rough River Youth Ranch (petro) | 15925 | 0 | 15925 | 0
| Rough River Youth Ranch, McDaniels Co. - AI# 107622 |  |  | 15925
Active | National Linen (ALSCO) | 0 | 0 | 0 | 0 | Estimate of $400k, pending selection of contractor. Set up in eComm
Active | Dorsey Plaza
Active | Mt Sterling Landfill |  |  |  |  | Construction could be $1m
Active | Lees Lane (NPL) |  |  |  |  | Monitoring only
Active | Leitchfield Cleaners |  |  |  |  | Investigation complete
Active | Kings Cleaners |  |  |  |  | Cannot access property
Active | Parrish Avenue |  |  |  |  | Will use CALE for remediation. Ready for Design
Active | Bowie Coal Washing plant in Estill Co |  |  |  |  | ERT handled first incident has been referred to Superfund Branch
Charges to projects NOT on the Orig CALE list
C7TQ | HWMF- Former Bill's Quality Cleaners | 3176.4 | 0 | 0 | 3176.4
| Quality Dry Cleaners AI#39175 Sample Analysis |  |  |  | 1462.9
| SFB - Quality Dry Cleaners - Marshall County - AI# 39175 |  |  |  | 1462.9
| Quality Dry Cleaners AI#39175 Sample Analysis-Expedited TAT |  |  |  | 250.6
| Other CALE Projects Not Active | Cost | Notes
| Former Standard Metals | 75000 | Corrective Action
| Hi-Acres Shopping Center | 60000 | Corrective Action
| Statewide Properties (petro) | 10000 | Characterization
| Barrel Services | 20000 | Characterization
| Saylor Battery Systems | 80000 | Characterization and Cleanup (Haz. Waste Site)
| York Properties(petro) | 10000 | Characterization
| Livermore Brass & Silver Shop | 200000 | Characterization, Corrective

## $71 MM
|  | $71 Million - HJR 56 |  |  |  |  | Updated as of 7/1/2024
Fund | Sub Fund | Project Name | Project Budget (Appropriation) | Expenditures | Bid Status | Estimated Completion | PARKS - Notes
$71 Million
CBD0 |  | Building Systems Repair & Replacement Pool | 6883200 |  |  |  | Replace automated controls for five Lodge HVAC systems. BR,GB,PF,RR,DH
| CB74 | CO-Multi Park BAS Updates (Finance - Facilities) | 6283200 | 49000 | In Design |  | Kick-Off site meetings in progress.
| CBE8 | Building Systems Upgrades- Various Parks (Parks) | 600000 | 37886.51 | In Design |  | Repair/Replace Chillers at KDV, BR and NB.
|  | BR-Chiller-MultiRepairs | 37886.51 |  |  |  | Purchase Order (PO) has been issued.
CBD1 |  | Life Safety System Upgrades and Replacement Pool | 3000000 | 80800 | In Design |  | All assessments completed, waiting on vendor for cost estimates. Door locking systems to be replaced on all guest accomodations.
|  | DH-Oak1-Elevator Upgrade | 80800 |  |  |  | Delivery Order (DO) has been issued
CBD2 |  | Structural and Safety Repairs Pool | 7011800 | 475000 | In Design |  | Moved funding to CA6S and CA6R E701 for design fees, the remaining funds will be processed in E703.
| CA6R | CO-Multi-Park StructInvest-West (Finance - Facilities) | 275000 |  | In Design |  | On-site assesments are complete, prioritizing most critical projects to begin design (Phase A)
| CA6S | CO-Multi-Park StructInvest-East (Finance - Facilities) | 200000 |  | In Design |  | On-site assesments are complete, prioritizing most critical projects to begin design (Phase A)
CBD3 |  | State Wide ADA Mobility Improvements Pool | 1065000 |  | In Design |  | DH Pedestrian Bridge construction costs will come from this pool. Finishing the design phase.
CBD4 |  | Dam Safety Reconstruction and Repairs Pool | 5000000 | 27736 | In Design |  | RFP is out, Finance - Facilities is preparing the contract for PF dam repairs. They will meet every other week on this.
CBD5 |  | EP Tom Sawyer Pool and Rec Bldg Upgrades Pool | 1280000 | 45000 | In Design |  | Site assesment Kick-off with consultant was held on 5/28/24 and they are now running a camera scope for more details on how to fix it.
CBD6 |  | Lake Barkley State Resort Park Lodge Wing Interior Upgrades | 2760000 | 52880 | Contract | 2025-05-01 | Initial site visit with contractor has been completed and consultant hired.
CBD7 |  | Accommodations & Hospitality Upgrades Pool | 22000000 |  | In Design |  | Established 2 projects, one for Finance - Facilities and one for PARKS to work from
| CBE9 | Accommodations & Hospitality Upgrades PARKS | 1000000 |  |  |  | Waiting on Finance - Procurement to issue a mattresses Master Agreement for various parks along with pricing other soft costs
| CBEA | Accommodations & Hospitality Upgrades Finance - Facilities | 21000000 |  |  |  | Finance - Facilities is preparing the RFP for consultant selections.
CBD8 |  | Pool Improvement and Repairs Pool | 11955900 |  | In Design |  | RFP's are getting ready to go out for bid.
CBD9 |  | Beach Refurbishment Pool | 346600 | 150000 | In Design |  | Funding is in place, working with Purchasing Dept and will be able to issue DO's soon for purchase of sand.
|  | CO-VariousParks-Beach Sand | 150000 |  |  |  | DO's will be issued soon for the purchase of sand.
CBDA |  | Playground Upgrades and Improvements Pool | 1200000 | 411401.57 | In Design |  | Site Visits started with Vendor, Master Agreement in place. Multi locations submitted to Finance - Procurement
|  | EP-Playground-NewEquipment | 88917.55 |  |  |  | Delivery Order (DO) has been issued for Material and Installation
|  | JD-Playground-NewEquipment | 86910.61 |  |  |  | Delivery Order (DO) has been issued for Material and Installation
|  | KD-Playground-NewEquipment | 85711.41 |  |  |  | Delivery Order (DO) has been issued for Material and Installation
|  | CC-Playground-NewEquipment | 149862 |  |  |  | Delivery Order (DO) has been issued for Material and Installation
CBDB |  | Golf Course Irrigation Replacement Pool | 5332500 |  | In Design |  | RFP for design forthcoming with construction in 2025
CBDC |  | Golf Course Bermuda Greens Conversion Pool | 575000 |  | In Design |  | The work on the Bermuda Greens will not start until 2025 due to busy season
CBDD |  | Golf Course Bunker Repairs Pool | 2590000 |  | In Design |  | RFP for design forthcoming with construction in 2025
|  | Totals | 71000000 | 1329704.08

## CB47 (hidden)
| CB47 | [12 empty] | updated 2/16/24
Fund | Project Name | Project Manager | Cash Balance | Total Project Budget (Appropriation) | Total Allotment | Encumbrance | Expenditures YTD | Total Allotment Unobligated | E701 Unobligated | E703 Unobligated | E726 Unobligated | E727 Unobligated | Project Initiation Date | Notes | eComm | eComm Notes | Fund Origan
CB5B | CO-Campground-MultiPark-West | Lisa Gorby | 1850000 | 1850000 |  | 75000 | 0 | 1775000 | 1775000 | 0 | 0 | 0 |  |  |  |  | C5KR
CB59 | CO-Campground-MultiPark-East | Tony Durham | 1850000 | 1850000 |  | 93500 | 0 | 1756500 | 1756500 | 0 | 0 | 0 |  |  |  |  | DWM- 2406
CB5D | KL-Campground-Bathhouse Reno |  | 308000 | 308000 |  | 0 | 0 | 308000 | 33000 | 275000 | 0 | 0 |  |  |  |  | DWM- 2406
CB7C | NB-Campground Bathhouses-Reno |  | 244200 | 244200 |  | 0 | 0 | 244200 | 0 | 107200 | 70500 | 66500 |  |  |  |  | DWM- 2406
CB7F | LB- Campground Bathhouses-Reno |  | 160000 | 160000 |  | 0 | 18.69 | 159981.31 | 0 | 81000 | 40500 | 38481.31 |  |  |  |  | DWM- 2406
CB7G | BS-Campground Bathhouse-Reno |  |  | 142000 |  | 0 | 0 | 142000 |  | 60000 | 56000 | 26000 |  |  |  | MA Selection Process #02 (ball: DECA MA) | DWM- 2406
CB7H | CC-Campground Bathhouses-Reno |  |  | 183000 |  | 10456 | 11447.37 | 161096.63 | 0 | 66000 | 62000 | 55000 |  |  | Yes | All Items Closed, Accepted | DWM- 2406
CB7J | DH-Campground1 - Signage |  |  | 31000 |  | 0 | 0 | 31000 | [6 empty] | Yes | All Items Closed, Accepted | DWM- 2406
CB7K | GB-Campground Bathhouses-Reno |  |  | 154000 |  |  | 0 | 154000 | [6 empty] | Yes | Invoice for MA DO #06 (ball: Project Manager) 4 days overdue | DWM- 2406
CB7L | GR-Campground Bathhouses-Reno |  |  | 117800 | [10 empty] | Yes | No Items | DWM- 2406
CB7M | GO-Campground Bathhouses-Reno |  |  | 160000 | [10 empty] | Yes | No Items | DWM- 2406
CB7N | KA-Campground Bathhouses- Reno |  |  | 147700 | [10 empty] | Yes | No Items | DWM- 2406
CB7P | NL-Campground Bathhouses-Reno |  |  | 51000 | [10 empty] | Yes | No Items | DWM- 2406
CB7Q | YL-Campground Bathhouses- Reno |  |  | 92300 | [10 empty] | Yes | No Items | DWM- 2406
CB7S | BB-Campground Bathhuses-Reno |  |  | 82000 | [10 empty] | Yes | No Items | DWM- 2406
CB89 | BR-Campground Bathhouses-Reno |  |  | 160000 | [10 empty] | Yes | All Items Closed, Accepted | DWM- 2406
CB8B | JW-Campground Bathhouses-Reno |  |  | 243500 | [10 empty] | Yes | No Items | DWM- 2406
DWM- 2406
|  | Total | 4412200 | 5976500 | 0 | 178956 | 11466.06 | 4731777.94 | 3564500 | 589200 | 229000 | 185981.31

## CB48 (hidden)
| CB48 | [12 empty] | Updated 2/16/24
Fund | Project Name | Project Manager | Cash Balance | Total Project Budget (Appropriation) | Total Allotment | Encumbrance | Expenditures YTD | Total Allotment Unobligated | E701 Unobligated | E703 Unobligated | E726 Unobligated | E727 Unobligated | Project Initiation Date | Notes | eComm | eComm Notes | Fund Origan
CB5C | KD-INFE-ElectricalEngStudy-WKRECC |  |  | 300000 |  | 0 | 0 | [8 empty] | MA Selection Process #02 (ball: DECA MA) | DWM- 2406
CB8X | CO-WW Collections Piping-East Parks |  |  | 100000 | [10 empty] | Yes | All Items Closed, Accepted | DWM- 2406
CB8Y | CO-WW Collections Piping-West Parks |  |  | 100000 |  | 0 | 0 | [7 empty] | Yes | All Items Closed, Accepted | DWM- 2406
DWM- 2406
DWM- 2406
DWM- 2406
DWM- 2406
DWM- 2406
DWM- 2406
DWM- 2406
DWM- 2406
DWM- 2406
DWM- 2406
|  | Total | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## CB49 (hidden)
CB49
Fund | Project Name | Project Manager | Cash Balance | Total Project Budget (Appropriation) | Total Allotment | Encumbrance | Expenditures YTD | Total Allotment Unobligated | E701 Unobligated | E703 Unobligated | E726 Unobligated | E727 Unobligated | Project Initiation Date | Notes | eComm | eComm Notes | Fund Origan
CBBT | DH-Campground-Install WiFi |  |  | 600000 |  | 0 | 0 | [9 empty] | DWM- 2406
CBBU | CC-Campground-Install Wifi |  |  | 500000 | [12 empty] | DWM- 2406
CB8V | PL-Campground-Install Wifi |  |  | 300000 |  | 0 | 0 | [9 empty] | DWM- 2406
DWM- 2406
DWM- 2406
DWM- 2406
DWM- 2406
DWM- 2406
DWM- 2406
DWM- 2406
DWM- 2406
DWM- 2406
DWM- 2406
|  | Total | 0 | 1400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## CB4B (hidden)
CB4B
Fund | Project Name | Project Manager | Cash Balance | Total Project Budget (Appropriation) | Total Allotment | Encumbrance | Expenditures YTD | Total Allotment Unobligated | E701 Unobligated | E703 Unobligated | E726 Unobligated | E727 Unobligated | Project Initiation Date | Notes | eComm | eComm Notes | Fund Origan
CB4B | Lake Barkley State Resort Park - Emergency Repairs |  |  | 7500000 |  | 304035.86 | 373540.54 | 6822423.6 | 607621 | 6214802.6 | [5 empty] | MA Selection Process #02 (ball: DECA MA) | DWM- 2406
[15 empty] | Yes | All Items Closed, Accepted | DWM- 2406
[15 empty] | Yes | All Items Closed, Accepted | DWM- 2406
DWM- 2406
DWM- 2406
DWM- 2406
DWM- 2406
DWM- 2406
DWM- 2406
DWM- 2406
DWM- 2406
DWM- 2406
DWM- 2406
|  | Total | 0 | 7500000 | 0 | 304035.86 | 373540.54 | 6822423.6 | 607621 | 6214802.6 | 0 | 0

## CB4C (hidden)
CB4C
Fund | Project Name | Project Manager | Cash Balance | Total Project Budget (Appropriation) | Total Allotment | Encumbrance | Expenditures YTD | Total Allotment Unobligated | E701 Unobligated | E703 Unobligated | E726 Unobligated | E727 Unobligated | Project Initiation Date | Notes | eComm | eComm Notes | Fund Origan
CB4C | Jenny Wiley State Resort Park - Emergency Repairs |  |  | 5500000 |  | 25000 | 0 | 5475000 | 1575000 | 3900000 | [5 empty] | MA Selection Process #02 (ball: DECA MA) | DWM- 2406
[15 empty] | Yes | All Items Closed, Accepted | DWM- 2406
[15 empty] | Yes | All Items Closed, Accepted | DWM- 2406
DWM- 2406
DWM- 2406
DWM- 2406
DWM- 2406
DWM- 2406
DWM- 2406
DWM- 2406
DWM- 2406
DWM- 2406
DWM- 2406
|  | Total | 0 | 5500000 | 0 | 25000 | 0 | 5475000 | 1575000 | 3900000 | 0 | 0

## $71 Million (hidden)
|  | HJR 56 |  | $71 Million |  |  | Updated as of 05/17/24
Fund | Sub Fund | Project Name | Total Project Budget (Appropriation) | Encumbrance | Expenditures | Total Unobligated | PARKS - Notes | eComm | eComm Notes
CBD0 |  | Building Systems Repair & Replacement Pool | 6883200 |  |  | 6883200 | Moved $6,283,200 into CB74 (DECA) Sitting up a new fund for Parks that will get $600,000 in E703
| CB74 | CO-Multi Park BAS Updates (DECA) | 6283200 |  |  |  | Waiting on funding to hit eMARS to start projects.
| CBE8 | Building Systems Upgrades- Various Parks (Parks) | 600000 |  |  |  | In process of funding
CBD1 |  | Life Safety System Upgrades and Replacement Pool | 3000000 |  |  | 3000000 | Waiting on funding to hit eMARS to start projects.
CBD2 |  | Structural and Safety Repairs Pool | 7011800 |  |  | 7011800 | Moved $200,000 to CA6S & $275,000 to CA6R E701 for DECA, will process the remaining in E703.
| CA6R | CO-Multi-Park StructInvest-West (DECA) | 275000 |  |  |  | Funding was processed and waiting for it to show in eMARS. Still needs to fund the balance in E703.
| CA6S | CO-Multi-Park StructInvest-East (DECA) | 200000 |  |  |  | Funding was processed and waiting for it to show in eMARS. Still needs to fund the balance in E703.
CBD3 |  | State Wide ADA Mobility Improvements | 1065000 |  |  | 1065000 | Funding was processed and waiting for it to show in eMARS
CBD4 |  | Dam Safety Reconstruction and Repairs Pool | 5000000 |  |  | 5000000 | Moved $300,000 to E712, $705,000 to E701 and $3,995,000 to E703 (DECA) Waiting on funding to show in eMARS.
CBD5 |  | EP Tom Pool and Rec Bldg Upgrades Pool | 1280000 |  |  | 1280000 | Moved $175,000 to E701 & $1,105,000 to E703 (DECA) Funding is in place, ready to start projects.
CBD6 |  | Lake Barkley State Reosort Park Lodge Wing Interior Upgrades | 2760000 | 52880 |  | 2707120 | Moved $414,000 to E701 & $2,346,000 to E703 (DECA) Funding is in place, ready to start projects
CBD7 |  | Accommodations & Hospitality Upgrades Pool | 22000000 |  |  | 22000000 | Establishing 2 projects, one for DECA and one for PARKS to move funds into
| CBE9 | Accommodations & Hospitality Upgrades PARKS | 1000000 |  |  |  | Processing funding now that we have a fund number.
| CBEA | Accommodations & Hospitality Upgrades DECA | 21000000 |  |  |  | Processing funding now that we have a fund number.
CBD8 |  | Pool Improvement and Repairs Pool | 11955900 |  |  | 11955900 | TBD by DECA
CBD9 |  | Beach Refurbishment Pool | 346600 |  |  | 346600 | Funding was processed and waiting for it to show in eMARS
CBDA |  | Playground Upgrades and Improvements | 1200000 |  |  | 1200000 | Funding was processed and waiting for it to show in eMARS
CBDB |  | Golf Course Irrigation Replacement Pool | 5332500 |  |  | 5332500 | Need to move funds into E701 and E703
CBDC |  | Golf Course Bermuda Greens Conversion Pool | 575000 |  |  | 575000 | Need to move all funds into E703
CBDD |  | Golf Course Bunker Repairs Pool | 2590000 |  |  | 2590000 | Need to move all funds into E703
|  |  | 71000000 | 52880 | 0 | 70947120

## $79 Million (hidden)
|  |  |  | $79 Million |  |  | Updated as of 05/17/24
Fund | Sub Fund | Project Name | Total Project Budget (Appropriation) | Encumbrance | Expenditures | Total Unobligated | PARKS - Notes | eComm | eComm Notes
CB47 |  | State Parks Improvements -Campground Updates | 40000000 | 0 | 0 | 34004100 | Moved $5,995,900.00 into other fund #'s getting ready for the remaining projects to be set up for the remainder of the $40 Million.
| Parks | Inhouse projects for Campground Bathhouses | 2295900 | 19200 | 209847.28 | 2066852.72
| CB58 | CO-Campground-Multi Park-West | 1850000 | 75000 |  | 1775000
| CB59 | CO-Campground-Multi Park-East | 1850000 | 93500 |  | 1756500
CB48 |  | State Parks Improvements -Utility Improvements | 20000000 | 0 | 0 | 19500000 | Only have 3 projects in process at this time.
| Parks | INFE-ElectricalEngStudy-WKRECC | 500000 |  |  | 500000 | Funded 3 separate projects to date, CB5C, CB8X and CB8Y
CB49 |  | State Parks Improvements-Broadband Upgrades | 6000000 | 0 | 0 | 4600000 | Have established 15 new projects for Wifi at the Campgrounds. Working with DOT for additional projects.
| Parks | Campground-Install Wifi | 1400000 | 0 | 218454.48 | 1181545.52
CB4B |  | Lake Barkley State Resort Park -Emergency Repairs | 7500000 | 139368.65 | 538207.75 | 6822423.6
CB4C |  | Jenny Wiley State Park Resort Park -Emergency Repairs | 5500000 | 75000 | 0 | 5425000
|  |  | 79000000 | 402068.65 | 966509.51 | 77631421.84