## PJM
Queue Number | Name | Commercial Name | State | County | Status | Transmission Owner | MFO | MW Energy | MW Capacity | MW In Service | Capacity or Energy | Project Type | Fuel | Project (AC/DC) | Rights (MW) | Initial Study | Feasibility Study | Feasibility Study Status | System Impact Study | System Impact Study Status | Facilities Study | Facilities Study Status | Interim Interconnection Service Agreement | Interim/Interconnection Service Agreement Status | Wholesale Market Participation Agreement | Construction Service Agreement | Construction Service Agreement Status | Upgrade Construction Service Agreement | Upgrade Construction Service Agreement Status | Backfeed Date | Queue Date | Long-Term Firm Service Start Date | Long-Term Firm Service End Date | Test Energy Date | Withdrawal Date | Withdrawn Remarks | Projected In Service Date | Revised In Service Date | Actual In Service Date | Attachment Type | Alternate Queue | Sliding Queue
AG2-179 | Coburg 69 kV |  | KY | Adair | Active | EKPC | 60 | 60 | 42.4 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/26/2021 | N/A | N/A |  |  |  | 9/15/2023 |  |  | N | No
AE1-246 | Barren County-Summer Shade 161 kV |  | KY | Barren | Active | EKPC | 120 | 120 | 80.7 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1246_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1246_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/24/2018 | N/A | N/A |  |  |  | 6/1/2022 |  |  | N | No
AF1-083 | Green County-Saloma 161 kV |  | KY | Barren | Active | EKPC | 55 | 55 | 33 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1083_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1083_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 8/29/2019 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AG1-067 | Temple Hill 69 kV |  | KY | Barren | Active | EKPC | 38 | 38 | 24.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1067_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1067_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2020 | N/A | N/A |  |  |  | 6/30/2023 |  |  | N | No
AG1-070 | Bon Ayr 69 kV |  | KY | Barren | Active | EKPC | 45 | 45 | 32.7 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1070_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1070_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2020 | N/A | N/A |  |  |  | 6/1/2024 |  |  | N | No
AG1-071 | Bon Ayr 69 kV |  | KY | Barren | Active | EKPC | 55 | 55 | 37.5 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1071_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1071_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2020 | N/A | N/A |  |  |  | 6/1/2024 |  |  | N | No
AG2-317 | Barren - Summer Shade 161 kV |  | KY | Barren | Active | EKPC | 155 | 35 | 23.3 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/24/2021 | N/A | N/A |  |  |  | 6/1/2024 |  |  | N | No
AH1-034 | Patton Road Junction - Summer Shade 69 kV |  | KY | Barren | Active | EKPC | 100 | 100 | 70 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/14/2021 | N/A | N/A |  |  |  | 11/15/2025 |  |  | N | No
AF2-307 | Hope-Blevins Valley Tap 69 kV |  | KY | Bath | Active | EKPC | 66 | 66 | 39.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2307_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2020 | N/A | N/A |  |  |  | 9/1/2023 |  |  | N | No
AG2-153 | Headquarters-Sideview 69 kV |  | KY | Bourbon | Active | EKPC | 75 | 75 | 45 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/24/2021 | N/A | N/A |  |  |  | 12/1/2023 |  |  | N | No
AG1-352 | Hunt Farm Junction 69 kV |  | KY | Boyle | Active | EKPC | 50 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1352_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1352_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG2-552 | Bullitt County 161 kV |  | KY | Bullitt | Active | EKPC | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 9/1/2024 |  |  | N | No
AE2-138 | Avon-North Clark 345 kV |  | KY | Clark | Active | EKPC | 260 | 260 | 189.8 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2138_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2138_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/8/2019 | N/A | N/A |  |  |  | 6/1/2022 |  |  | N | No
AE2-210 | Avon-North Clark 345 kV |  | KY | Clark | Active | EKPC | 90 | 90 | 65.4 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2210_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2210_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/20/2019 | N/A | N/A |  |  |  | 6/1/2022 |  |  | N | No
AF1-251 | Avon-North Clark 345 kV |  | KY | Clark | Active | EKPC | 220 | 220 | 132 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1251_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1251_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  |  |  | 5/15/2023 |  |  | N | No
AE2-339 | Avon 138 kV |  | KY | Fayette | Active | EKPC | 40 | 40 | 26.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2339_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2339_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2019 | N/A | N/A |  |  |  | 12/1/2022 |  |  | N | No
AF1-127 | Avon 345 kV |  | KY | Fayette | Active | EKPC | 80 | 80 | 53.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1127_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1127_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/17/2019 | N/A | N/A |  |  |  | 12/1/2023 |  |  | N | No
AH1-004 | Avon - Renaker 138 kV |  | KY | Fayette | Active | EKPC | 40 | 40 | 24 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/7/2021 | N/A | N/A |  |  |  | 12/1/2023 |  |  | N | No
AE1-144 | Goddard-Plumville 138 kV |  | KY | Fleming | Active | EKPC | 120 | 120 | 80.2 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1144_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1144_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/24/2018 | N/A | N/A |  |  |  | 6/1/2022 |  |  | N | No
AE2-038 | Goddard-Plumsville 138 kV II |  | KY | Fleming | Active | EKPC | 200 | 80 | 53.5 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2038_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2038_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 1/22/2019 | N/A | N/A |  |  |  | 6/1/2022 |  |  | N | No
AF1-233 | Flemingsburg 138 kV |  | KY | Fleming | Active | EKPC | 225 | 225 | 150.6 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1233_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1233_imp.pdf | Document Posted |  | In Progress | https://www.pjm.com/pub/planning/project-queues/isa/af1_233_isa2.pdf | Interim Study | N/A |  |  | N/A | N/A |  | 9/27/2019 | N/A | N/A |  |  |  | 5/31/2022 |  |  | N | No
AF1-256 | Flemingsburg-Spurlock 138 kV |  | KY | Fleming | Active | EKPC | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1256_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1256_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  |  |  | 6/1/2023 |  |  | N | No
AG1-526 | West Garrard 345 kV |  | KY | Garrard | Active | EKPC | 222 | 222 | 133.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1526_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 6/1/2023 |  |  | N | No
AG2-687 | Garrard 345 kV |  | KY | Garrard | Active | EKPC | 215 | 215 | 129 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 6/1/2024 |  |  | N | No
AG2-159 | Williamstown 69 kV |  | KY | Grant | Active | EKPC | 61 | 61 | 43 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/25/2021 | N/A | N/A |  |  |  | 9/15/2023 |  |  | N | No
AF1-050 | Summer Shade - Green County 161 kV |  | KY | Green | Active | EKPC | 60 | 60 | 36 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1050_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1050_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 7/12/2019 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AG1-354 | Summershade-Green County 161 kV |  | KY | Green | Active | EKPC | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1354_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG2-670 | Greensburg 69 kV |  | KY | Green | Active | EKPC | 75 | 75 | 45 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AF2-090 | Central Hardin 138 kV |  | KY | Hardin | Active | EKPC | 110 | 110 | 73.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2090_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2090_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 2/6/2020 | N/A | N/A |  |  |  | 10/1/2022 |  |  | N | No
AF2-260 | Stephensburg-Central Hardin 69 kV |  | KY | Hardin | Active | EKPC | 85 | 85 | 53 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2260_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2260_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/27/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AF2-309 | Central Hardin-Stephensburg 69 kV |  | KY | Hardin | Active | EKPC | 70 | 70 | 42 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2309_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2309_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2020 | N/A | N/A |  |  |  | 9/1/2023 |  |  | N | No
AF2-391 | Central Hardin 69 kV |  | KY | Hardin | Active | EKPC | 120 | 120 | 72 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2391_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 6/15/2023 |  |  | N | No
AG1-096 | Rineyville 69 kV |  | KY | Hardin | Active | EKPC | 55 | 55 | 36.6667 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/14/2020 | N/A | N/A |  |  |  | 10/31/2023 |  |  | N | No
AG1-320 | Glendale-Stephensburg 69 kV |  | KY | Hardin | Active | EKPC | 82 | 82 | 54.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1320_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 10/1/2023 |  |  | N | No
AG1-491 | Central Hardin 69 kV |  | KY | Hardin | Active | EKPC | 70 | 70 | 42 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1491_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 6/30/2023 |  |  | N | No
AG2-549 | Rineyville 69 kV |  | KY | Hardin | Active | EKPC | 40 | 40 | 26.6667 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AD2-048 | Cynthia-Headquarters 69 kV |  | KY | Harrison | Active | EKPC | 70 | 70 | 46.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2048_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2048_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ad2048_fac.pdf | Document Posted | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2018 | N/A | N/A |  |  |  | 6/1/2020 |  |  | N | No
AF2-365 | Munfordville KU Tap-Horse Cave Jct. 69 kV |  | KY | Hart | Active | EKPC | 50 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2365_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2365_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AG1-472 | Seymour-Cave City 69 kV |  | KY | Hart | Active | EKPC | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1472_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 10/9/2023 |  |  | N | No
AG2-666 | Spurlock - Flemingsburg 138 kV |  | KY | Jackson | Active | EKPC | 90 | 90 | 54 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG2-184 | Spicewood-Softshell 138 kV |  | KY | Knott | Active | AEP | 210 | 210 | 126 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/26/2021 | N/A | N/A |  |  |  | 6/1/2024 |  |  | N | No
AG2-678 | Vicco - Beckham 138 kV |  | KY | Knott | Active | AEP | 120 | 120 | 72 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 6/1/2024 |  |  | N | No
AG2-424 | Bonnieville - Lebanon 138 kV |  | KY | Larue | Active | EKPC | 63.3 | 63.25 | 34.95 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  |  |  | 5/31/2023 |  |  | N | No
AG2-513 | Hodgenville-Sulphur Creek 69 kV |  | KY | Larue | Active | EKPC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 7/31/2023 |  |  | N | No
AG2-682 | Stinnett 161 kV |  | KY | Leslie | Active | AEP | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 6/1/2024 |  |  | N | No
AG2-679 | Daisy - Collier 69 kV |  | KY | Letcher | Active | AEP | 50 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 6/1/2024 |  |  | N | No
AE2-275 | JK Smith-Fawkes 138 kV |  | KY | Madison | Active | EKPC | 90 | 90 | 65.4 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2275_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2275_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/28/2019 | N/A | N/A |  |  |  | 6/1/2022 |  |  | N | No
AE2-308 | Three Forks-Dale 138 kV |  | KY | Madison | Active | EKPC | 150 | 150 | 110 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2308_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2308_imp.pdf | Document Posted |  | In Progress | https://www.pjm.com/pub/planning/project-queues/isa/ae2_308_isa2.pdf | Interim Study | N/A |  |  | N/A | N/A |  | 3/29/2019 | N/A | N/A |  |  |  | 5/31/2021 |  |  | N | No
AF2-348 | North Clark-Spurlock 345 kV |  | KY | Madison | Active | EKPC | 250 | 250 | 150 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2348_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 7/1/2022 |  |  | N | No
AF2-355 | West Gerrard-J.K. Smith 345 nkV |  | KY | Madison | Active | EKPC | 225 | 225 | 135 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2355_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 7/1/2022 |  |  | N | No
AG1-306 | Fawkes-Dale 138 kV |  | KY | Madison | Active | EKPC | 65 | 65 | 39 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1306_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/29/2020 | N/A | N/A |  |  |  | 10/1/2023 |  |  | N | No
AG2-073 | Crooksville 69 kV |  | KY | Madison | Active | EKPC | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/11/2021 | N/A | N/A |  |  |  | 5/1/2024 |  |  | N | No
AG1-488 | Marion IP 161 kV |  | KY | Marion | Active | EKPC | 70 | 70 | 42 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1488_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 9/30/2022 |  |  | N | No
AG2-298 | Loretto 69 kV |  | KY | Marion | Active | EKPC | 60 | 60 | 40 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2021 | N/A | N/A |  |  |  | 9/1/2024 |  |  | N | No
AG2-512 | Sulphur Creek-Loretto 69 kV |  | KY | Marion | Active | EKPC | 17.5 | 17.5 | 11 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 7/31/2023 |  |  | N | No
AF1-130 | Inez 138 kV |  | KY | Martin | Active | AEP | 200 | 200 | 133.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1130_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1130_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/18/2019 | N/A | N/A |  |  |  | 12/1/2023 |  |  | N | No
AF2-018 | Inez 138 kV |  | KY | Martin | Active | AEP | 200 | 200 | 133.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2018_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2018_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 11/1/2019 | N/A | N/A |  |  |  | 12/1/2023 |  |  | N | No
AG2-685 | Big Sandy-Inez 138 kV |  | KY | Martin | Active | AEP | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 6/1/2024 |  |  | N | No
AF2-111 | North Clark-Spurlock 345 kV |  | KY | Mason | Active | EKPC | 250 | 250 | 150 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2111_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG1-405 | Walnut Grove-Asahi 69 kV |  | KY | McLean | Active | EKPC | 57 | 57 | 34.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1405_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1405_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 9/25/2024 |  |  | N | No
AE2-071 | Patton Rd-Summer Shade 69 kV |  | KY | Metcalfe | Active | EKPC | 35 | 35 | 21 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2071_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2071_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 2/14/2019 | N/A | N/A |  |  |  | 12/31/2021 |  |  | N | No
AF1-203 | Patton Rd-Summer Shade 69 kV |  | KY | Metcalfe | Active | EKPC | 55 | 20 | 12 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1203_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1203_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/25/2019 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AG1-341 | Summer Shade 161 kV |  | KY | Metcalfe | Active | EKPC | 106 | 106 | 63.6 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1341_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 6/15/2023 |  |  | N | No
AG2-094 | Summer Shade-Green County 161 kV |  | KY | Metcalfe | Active | EKPC | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/27/2021 | N/A | N/A |  |  |  | 4/1/2024 |  |  | N | No
AG2-598 | Knob Lick-JB Galloway Tap 69 kV |  | KY | Metcalfe | Active | EKPC | 50 | 50 | 40 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 11/30/2025 |  |  | N | No
AG2-684 | Summer Shade 161 kV |  | KY | Metcalfe | Active | EKPC | 331 | 331 | 198.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 6/1/2024 |  |  | N | No
AH1-081 | Knob Lick 69kV |  | KY | Metcalfe | Active | EKPC | 60 | 60 | 36 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2021 | N/A | N/A |  |  |  | 12/20/2024 |  |  | N | No
AH1-082 | Knob Lick 69kV |  | KY | Metcalfe | Active | EKPC | 104 | 44 | 26.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2021 | N/A | N/A |  |  |  | 12/20/2024 |  |  | N | No
AG2-081 | Mt. Sterling-Fogg Pike 69 kV |  | KY | Montgomery | Active | EKPC | 30 | 30 | 18 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/21/2021 | N/A | N/A |  |  |  | 5/1/2024 |  |  | N | No
AG2-671 | Hope - Frenchburg 69 kV |  | KY | Montgomery | Active | EKPC | 19.9 | 19.9 | 11.94 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG2-567 | Stanville - Dewey 138 kV |  | KY | N/A | Active | AEP | 200 | 200 | 100 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 3/24/2024 |  |  | N | No
AG1-066 | Bonnyman 69 kV |  | KY | Perry | Active | AEP | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1066_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1066_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2020 | N/A | N/A |  |  |  | 10/2/2024 |  |  | N | No
AG2-681 | Soft Shell - Bonny Man 138 kV |  | KY | Perry | Active | AEP | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 6/1/2024 |  |  | N | No
AC1-101 | Johns Creek-Excel 138kV I |  | KY | Pike | Active | AEP | 50 | 50 | 19 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1101_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1101_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 10/24/2016 | N/A | N/A |  |  |  | 6/1/2019 |  |  | N | No
AC1-102 | Johns Creek-Excel 138kV II |  | KY | Pike | Active | AEP | 50 | 50 | 19 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1102_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1102_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 10/23/2016 | N/A | N/A |  |  |  | 6/1/2019 |  |  | N | No
AF2-328 | Excel-Johns Creek 138 kV |  | KY | Pike | Active | AEP | 75 | 75 | 45 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2328_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2328_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2020 | N/A | N/A |  |  |  | 12/1/2023 |  |  | N | No
AF1-038 | Sewellton Jct-Webbs Crossroads 69 kV |  | KY | Russell | Active | EKPC | 60 | 60 | 36 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1038_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1038_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 6/6/2019 | N/A | N/A |  |  |  | 12/31/2021 |  |  | N | No
AG2-676 | Russell Co 161 kV |  | KY | Russell | Active | EKPC | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 6/1/2024 |  |  | N | No
AG2-677 | Russell Co J - Jamestown T 161 kV |  | KY | Russell | Active | EKPC | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 6/1/2024 |  |  | N | No
AG2-596 | Renaker-Avon 138 kV |  | KY | Scott | Active | EKPC | 65 | 65 | 39 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 6/1/2024 |  |  | N | No
AG1-353 | Greene County-Marion County 161 kV |  | KY | Taylor | Active | EKPC | 98 | 98 | 58.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1353_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AF1-116 | Marion County 161 kV |  | KY | Washington | Active | EKPC | 120 | 120 | 72 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1116_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af116_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/12/2019 | N/A | N/A |  |  |  | 12/29/2023 |  |  | N | No
AG1-471 | Up Church-Wayne County 69 kV |  | KY | Wayne | Active | EKPC | 60 | 60 | 36 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1471_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1471_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 10/2/2023 |  |  | N | No
AE2-254 | Garrard County-Tommy-Gooch 69 kV | Turkey Creek Solar | KY | Garrard | Engineering and Procurement | EKPC | 50 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2254_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2254_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae2254_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae2_254_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ae2_254_csa.pdf | Document Posted | N/A | N/A |  | 3/26/2019 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AC1-074 | Jacksonville-Renaker 138kV I | Bluebird Solar | KY | Harrison | Engineering and Procurement | EKPC | 80 | 80 | 56 | 1 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1074_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1074_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac1074_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac1_074_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ac1_074_csa.pdf | Document Posted | N/A | N/A |  | 9/29/2016 | N/A | N/A |  |  |  | 6/1/2023 | 6/1/2023 |  | N | No
AC2-075 | Jacksonville-Renaker 138 kV | Bluebird Solar | KY | Harrison | Engineering and Procurement | EKPC | 100 | 20 | 13.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2075_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2075_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac2075_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac2_075_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 2/27/2017 | N/A | N/A |  |  |  | 6/1/2023 | 6/1/2023 |  | N | No
AE1-143 | Marion County 161 kV | Northern Bobwhite Solar | KY | Marion | Engineering and Procurement | EKPC | 96 | 96 | 64.163 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1143_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1143_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae1143_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae1_143_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ae1_143_csa.pdf | Document Posted | N/A | N/A |  | 9/24/2018 | N/A | N/A |  |  |  | 11/30/2023 | 11/30/2023 |  | N | No
AD2-072 | Van Arsdell-Mercer Industrial 69kV | Mercer County Solar Project | KY | Mercer | Suspended | EKPC | 95 | 95 | 63.75 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2072_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2072_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ad2072_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ad2_072_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ad2_072_csa.pdf | Document Posted | N/A | N/A |  | 3/14/2018 | N/A | N/A |  |  |  | 11/30/2022 | 11/30/2022 |  | N | No

## MISO
Project # | Request Status | Queue Date | Withdrawn Date | Done Date | Appl In Service Date | Transmission Owner | County | State | Study Cycle | Study Group | Study Phase | Service Type | POI Name | Summer MW | Winter MW | Fuel | Generating Facility | Post GIA Status | Negotiated In Service Date | Decision Point 1 ERIS MW | Decision Point 1 NRIS MW | Decision Point 2 ERIS MW | Decision Point 2 NRIS MW
J753 | Done | 2016-11-14 |  | 2019-03-08 | 2021-04-01 | Big Rivers Electric Corporation | Breckinridge | KY | DPP-2017-FEB | Central | GIA | NRIS | Hardinsburg Sub 161kV | 100 | 100 | Solar | PV Photovoltaic | Under Construction | 2021-04-01 | 100 | 100 | 100 | 100
J1632 | Active | 2020-06-25 |  |  | 2023-09-01 | Big Rivers Electric Corporation | Caldwell | KY | DPP-2020-Cycle | Central | PHASE 1 | NRIS | Caldwell County - Barkley 161kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
J1448 | Active | 2019-04-29 |  |  | 2022-08-01 | Big Rivers Electric Corporation | Caldwell | KY | DPP-2019-Cycle | Central | PHASE 2 | NRIS | Hopkins - Caldwell County - Barkely 161kV Line | 150 | 150 | Solar | PV Photovoltaic | Not Started |  | 150 | 150 | 0 | 0
J1638 | Active | 2020-06-25 |  |  | 2023-09-01 | Big Rivers Electric Corporation | Hancock | KY | DPP-2020-Cycle | Central | PHASE 1 | NRIS | Skillman Substation 161kV | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
J1604 | Active | 2020-06-25 |  |  | 2023-08-31 | Henderson Municipal Power & Light | Henderson | KY | DPP-2020-Cycle | Central | PHASE 1 | NRIS | HMPL Substation #7 69kV | 50 | 50 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
J1696 | Active | 2020-06-25 |  |  | 2023-10-01 | Big Rivers Electric Corporation | Henderson | KY | DPP-2020-Cycle | Central | PHASE 1 | NRIS | Reid 161kV | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
J1466 | Active | 2019-04-29 |  |  | 2022-08-01 | Big Rivers Electric Corporation | Henderson | KY | DPP-2019-Cycle | Central | PHASE 2 | NRIS | Reid EHV 161 kV Substation | 250 | 250 | Solar | PV Photovoltaic | Not Started |  | 250 | 250 | 0 | 0
J1619 | Active | 2020-06-25 |  |  | 2023-09-01 | Big Rivers Electric Corporation | Henderson,Webster | KY | DPP-2020-Cycle | Central | PHASE 1 | NRIS | Reid Switchyard 161kV | 160 | 160 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
J1231 | Active | 2019-04-28 |  |  | 2022-09-01 | Big Rivers Electric Corporation | Lyon | KY | DPP-2019-Cycle | Central | PHASE 2 | NRIS | Barkley - Caldwell 161kV Line | 125 | 125 | Solar | PV Photovoltaic | Not Started |  | 125 | 125 | 0 | 0
J1649 | Active | 2020-06-25 |  |  | 2022-10-31 | Big Rivers Electric Corporation | McCracken | KY | DPP-2020-Cycle | Central | PHASE 1 | NRIS | McCracken County to Shell 69kV | 60 | 60 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
J1600 | Active | 2020-06-25 |  |  | 2022-10-31 | Big Rivers Electric Corporation | Meade | KY | DPP-2020-Cycle | Central | PHASE 1 | NRIS | Flaherty Tap to Custer 69kV | 40 | 40 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
J762 | Done | 2016-11-14 |  | 2019-03-08 | 2021-04-01 | Big Rivers Electric Corporation | Meade | KY | DPP-2017-FEB | Central | GIA | NRIS | Meade Sub 161kV | 200 | 200 | Solar | PV Photovoltaic | Under Construction | 2021-04-01 | 200 | 200 | 200 | 200
J1703 | Active | 2020-06-25 |  |  | 2023-09-01 | Big Rivers Electric Corporation | Webster | KY | DPP-2020-Cycle | Central | PHASE 1 | NRIS | Reid to Hopkins County 161kV | 74 | 74 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
J1450 | Active | 2019-04-29 |  |  | 2022-08-01 | Big Rivers Electric Corporation | Webster | KY | DPP-2019-Cycle | Central | PHASE 2 | NRIS | Hopkins - Reid161kV Line | 150 | 150 | Solar | PV Photovoltaic | Not Started |  | 150 | 150 | 0 | 0

## Summary
| Megawatts (MW) | As of 8/31/2021
PJM
88 | 9052
MISO
14 | 1859
Total - Proposed Solar Facilities
102 | 10911

## KY Siting Board
| Commercial Name | # Panels | MW | # Panels/MW | County | Acres according to KY Siting Board filings | Acres/MW | Acres per Reported News
2021
| 2021-00312 - Hardin Solar LLC | 192000 | 85 | 2258.8235 | Hardin | 850 | 10 | 10
| 2021-00235 - Russellville Solar LLC |  | 130 |  | Logan | 1600 | 12.3077 | 12.3077
| 2021-00213 - AEUG Boonesborough Solar, LLC |  | 65 |  | Madison | 650 | 10 | 10
| 2021-00212 - AEUG Richmond Solar, LLC |  |  |  | Madison
| 2021-00170 - AEUG Mason Solar, LLC |  | 250 |  | Mason | 2500 | 10
| 2021-00141 - Bluebird Solar LLC |  | 90 |  | Harrison | 700 | 7.7778
| 2021-00127 - Rhudes Creek Solar, LLC |  | 100 |  | Hardin | 729 | 7.29
| 2021-00072 - Sebree Solar, LLC | 863095 | 150 | 5753.9667 | Webster | 1500 | 10
| 2021-00029 - Martin County Solar Project, LLC |  | 200 |  | Martin | 1500 | 7.5
2020
| 2020-00417 - Horus Kentucky 1 LLC |  | 69.3 |  | Simpson | 550 | 7.9365
| 2020-00392 - McCracken County Solar LLC | 156000 | 60 | 2600 | McCracken | 572 | 9.5333
| 2020-00391 - Henderson County Solar LLC |  | 50 |  | Henderson | 541 | 10.82
| 2020-00390 - Meade County Solar LLC |  | 40 |  | Meade | 370 | 9.25
| 2020-00387 - Green River Solar, LLC |  | 200 |  | Breckenridge/Meade | 1559 | 7.795
| 2020-00370 - Fleming Solar, LLC |  | 80 |  | Fleming | 770 | 9.625
| 2020-00280 - Ashwood Solar I, LLC |  | 86 |  | Lyon | 900 | 10.4651
| 2020-00272 - Flat Run Solar, LLC |  | 55 |  | Taylor | 450 | 8.1818
| 2020-00261 - Woodpecker Solar, LLC |  | 120 |  | Barren | 1500 | 12.5
| 2020-00244 - Caldwell Solar, LLC |  | 200 |  | Caldwell | 3000 | 15
| 2020-00243 - Golden Solar, LLC |  | 150 |  | Caldwell | 2400 | 16
| 2020-00242 - Unbridled Solar, LLC |  | 160 |  | Henderson/Webster | 1680 | 10.5
| 2020-00226 - Mt Olive Creek Solar, LLC |  | 60 |  | Russell | 475 | 7.9167
| 2020-00219 - AEUG Madison Solar, LLC |  | 100 |  | Madison | 1100 | 11 | 1770 | 17.7 MW/Acre
2020-00208 - Northern Bobwhite Solar, LLC
| 2020-00206 - AEUG Fleming Solar, LLC |  | 188 |  | Fleming | 1590 | 8.4574
| 2020-00190 - Horseshoe Bend Solar, LLC |  | 60 |  | Green | 550 | 9.1667
| 2020-00043 - Glover Creek Solar, LLC |  | 55 |  | Metcalfe | 560 | 10.1818
| 2020-00040 - Turkey Creek Solar, LLC |  | 50 |  | Garrard | 320 | 10.4 | 520
Summary
| Total Megawatts before Siting Board, 2020-21 |  | 2853.3
| # of counties with active proposed solar developments |  | 47
| Average Acres needed per MW, per Siting Board applications |  | 9.9848
| Estimated Total Acres before Siting Board, 2020-21 |  | 28916
| Total MW in PJM/MISO Interconnection Queues |  | 10911
| Solar panels per MW - Low |  | 2259
| Solar panels per MW - High |  | 5754
|  |  | Low | High
| Potential number of solar panels requiring disposal, under current proposals |  | 24647949 | 62781894

## Counties
County
Adair
Barren
Bath
Bourbon
Boyle
Breckinridge
Bullitt
Caldwell
Caldwell
Clark
Fayette
Fleming
Garrard
Grant
Green
Hancock
Hardin
Harrison
Hart
Henderson
Henderson
Jackson
Knott
Larue
Leslie
Letcher
Lyon
Madison
Marion
Martin
Mason
McCracken
McLean
Meade
Meade
Mercer
Metcalfe
Montgomery
N/A
Perry
Pike
Russell
Scott
Taylor
Washington
Wayne
Webster

## Definitions-Mapping
Column Names from Data Tab
Queue | Queue/OASIS Number
Name | The commercial name becomes public after the System Impact Study is issued. Not all developers have a commercial name once the System Impact Study is posted and there is no tariff requirement for them to have one. Also, the name users search under may vary. For ARR upgrades, the project name is the source and sink. Name is also referred to as the following: PJM Substation, Terminals, Customer Name and Source + Sink.
Commercial Name | The commercial name becomes public after the System Impact Study is issued. Not all developers have a commercial name once the System Impact Study is posted and there is no tariff requirement for them to have one. Also, the name users search under may vary. For ARR upgrades, the project name is the source and sink. Name is also referred to as the following: PJM Substation, Terminals, Customer Name and Source + Sink.
State | The state the project resides in.
County | Point of Interconnection County
Status | Contains the following statuses: Active, Active-In Service, Annulled, Cancelled, Confirmed, Engineering Procurement, In Service, Pending, Renewal, Retracted, Suspended, Under Construction, Under Construction - In Service & Withdrawn
Transmission Owner | A member that owns or leases, with rights equivalent to ownership, Transmission Facilities. Taking transmission service is not sufficient to qualify a Member as a Transmission Owner. Path name is included.
MFO | Maximum Facility Output
MW Energy | The MW energy for the interconnection request (winter net).
MW Capacity | The Capacity interconnection request for the queue position (summer net).
MW In Service | The number of megawatts when the project is in service.
Capacity or Energy
Project Type | GI: Generation Interconnection, TI: Transmission Interconnection, LTFT: Long-Term Firm Transmission, UR: Upgrade Request
Fuel | The type of fuel the project is running.
Project (AC/DC) | AC or DC
Rights (MW) | The type of rights the terminal has.
Initial Study
Feasibility Study | A Feasibility Study assesses project practicality and developer cost to interconnect to PJM and is the first study in the interconnection process.
Feasibility Study Status
System Impact Study | A System Impact Study provides a comprehensive and detailed system analysis that tests deliverability under peak load conditions as well as tests impacts on system stability.
System Impact Study Status
Facilities Study | A Facilities Study encompasses the engineering design work necessary to begin construction of required expansion plan upgrades identified by PJM to accommodate an interconnection request.
Facilities Study Status
Interim Interconnection Service Agreement | Under certain circumstances, an applicant for an ISA may wish to initiate project construction activities on an expedited basis prior to completion of the Facilities Study.
Interim Interconnection Service Agreement Status
Wholesale Market Participation Agreement | The WMPA request is placed into the interconnection queue process so that PJM may assess the impact of any such wholesale power transactions on the PJM bulk power system.
Construction Service Agreement | The terms and conditions of a Construction Service Agreement govern the construction of all transmission facilities for interconnection to the PJM transmission system. PJM and the developer execute a separate CSA with each impacted transmission owner. A developer retains the right (“Option to Build”), but not the obligation to design, procure, construct and install all or any portion of required transmission upgrades which are otherwise the obligation of the Transmission Owner to construct.
Construction Service Agreement Status
Upgrade Construction Service Agreement | The terms and conditions of an Upgrade Construction Service Agreement govern the construction activities associated with the upgrade of capability along an existing PJM bulk electric system circuit in order to accommodate a merchant transmission interconnection request. Facilities constructed under an UCSA are not owned by a developer. All ownership rights of the physical facilities are retained by the respective Transmission Owner following the completion of construction. PJM and the developer execute a separate UCSA with each impacted transmission owner.
Upgrade Construction Service Agreement Status
BackFeed Date
Queue Date
LTF Service Start Date
LTF Service End Date
Test Energy Date
Withdrawal Date
Withdrawn Remarks | CIW: Customer Initiated Withdraw, CMN: Customer Milestone Not Met, QNR: Queue Not Required, WBSD: Withdrawn Before Study Due
Revised In Service Date
Actual In Service Date
Date Suspended
Attachment Type | N, Y, BB = Generation Interconnection, S = Transmission Interconnection, EE = Upgrade Request, FF = Transmission Service
Alternate Queue
Sliding Queue