## Slide 1: SERVS Project Updates Kentucky State Police February 2026 Legislative Oversight & Investigations Committee

## Slide 2: Phase I – West & User Equipment Funded and 100% Completed 2 Cores Completed 70 Console Positions Completed 14 Existing Tower Sites - Radio Installs Completed 4 New Tower Sites – Towers Constructed & Radio Installs Completed Subscriber Equipment Completed
Notes: Post 1, 2

## Slide 3: Phase II – Central Funded and 77% Completed 48 Existing Tower Sites - Radio Installs Completed 13 New Tower Sites – Pending Acquisition 3 New Tower Sites – Construction Completed 2 New Tower Sites- Under Construction
Notes: Post 3, 4, 5, 6, 7, 12, 15, 16

## Slide 4: Phase IIIA - East Funded and 0% Completed (estimated to be at least 60% completed this biennium) 2 Cores – In Progress 24 Existing Sites – Radio Installation In Progress 18 New Sites Pending
Notes: Post 8, 11, 14

## Slide 5: Phase III - Statewide Funded and 69% Completed (Router Upgrade Portion) 129 Existing Sites Replaced 58 New Sites Pending 4 New Sites Completed 3 New Sites to be Completed 30 Days
Notes: Statewide

## Slide 6: Phase III - Statewide Funded and 68% Completed (Microwave Upgrade Portion) 129 Existing Sites Replaced 1 Existing Site to be Completed 30 days 4 New Sites Completed 58 New Sites Pending 3 New Sites to be Completed 30 Days
Notes: Statewide

## Slide 7: Closeout Phase - East Funding Requested 16 Existing Sites – Radio Installations to be completed by the end of 2027 25 New Sites – Pending Site Acquisition
Notes: Post 9, 10, 13

## Slide 8: Post 1 / 2 / 16 Fully operational Post 3 Equipment installs completed on existing sites New constructed site completed Jan 2026. Equipment installs begin Feb 2026 Scheduled to be fully operational Spring 2026
Post 16
Post 3
Post 2
Post 1
Current Coverage
& Post Status

## Slide 9: Approved Status
State Police Post 1 and 2 Fully operational
State Police Post 16 Fully operational
Graves County Sheriff’s Office Fully operational
• Mayfield Police Department Fully operational
• Mayfield Fire/EMS Department Fully operational
Currently in Process
Simpson County
• Concord Fire (McCracken Co)
• Calloway County Fire
Hart County
Elizabethtown PD
• Carroll County
• Grant County
• Floyd County – Prestonsburg
State Police Post 3
SERVS User Agency Status Update
• Fleming County – Flemingsburg
• Pendleton County
• Rockcastle County
• Lincoln County
• Morgan County
Boyd County Sheriff
KY Department of Corrections
• KY Fish and Wildlife

## Slide 10: Combined SERVS Project Status as of 21 January 2026

## Slide 11: SERVS Budget Status as of 15 January 2026

## Slide 12: SERVS Site Acquisition as of 21 January 2026

## Slide 13: SERVS Site Acquisition as of 21 January 2026
Site Status - Typical Progression of Steps
Collect site information, provide site options
Review site options and information
Title Work and Appraisal
Legal Review
Contract / Survey and Environmental
Closing/Recording
Construction

## Slide 14: SERVS Site Acquisition as of 21 January 2026
Site Status - Typical Progression of Steps
Collect site information, provide site options
Review site options and information
Title Work and Appraisal
Legal Review
Contract / Survey and Environmental
Closing/Recording
Construction

## Slide 15: SERVS Site Acquisition as of 21 January 2026
Site Status - Typical Progression of Steps
Collect site information, provide site options
Review site options and information
Title Work and Appraisal
Legal Review
Contract / Survey and Environmental
Closing/Recording
Construction