# AN ACT relating to the construction industry.

Be it enacted by the General Assembly of the Commonwealth of Kentucky:

# SECTION 1.   A NEW SECTION OF KRS CHAPTER 371 IS CREATED TO READ AS FOLLOWS:

As used in this Sections 1 to 7 of this Act:

## (1)	"Construction" means the process of building, altering, repairing, improving, or demolishing any structures or buildings, or other improvements of any kind to any real property, but does not include the routine maintenance of existing structures, buildings, or real property;

## (2)	"Contract" means a contract or agreement concerning construction made and entered into by and between a contracting entity and a contractor, a contractor and a subcontractor, or a subcontractor and another subcontractor;

## (3)	"Contracting entity" means an owner of real property; a trustee, agent, or spouse of an owner of real property; or a public official, public authority, or other public entity authorized to contract under the Kentucky Revised Statutes;

## (4)	"Contractor" means a person performing construction and having a contract with a contracting entity;

## (5)	"Owner" means a person who holds an ownership interest in real property;

## (6)	"Person" means an individual, corporation, estate, trust, partnership, limited liability company, association, joint venture, or any other legal entity;

## (7)	"Retainage" means money earned by a contractor or subcontractor but withheld to ensure proper performance by the contractor or subcontractor and that shall be paid upon completion of contractual obligations; and

## (8)	"Subcontractor" means any person performing construction covered by a contract between a contracting entity and a contractor who does not have a contract with the contracting entity.

# SECTION 2.   A NEW SECTION OF KRS CHAPTER 371 IS CREATED TO READ AS FOLLOWS:

## (1)	All payments on construction contracts entered into after the effective date of Sections 1 to 7 of this Act shall be made pursuant to the terms of the contract and as required in this section and Sections 3 and 4 of this Act.

## (2)	The following provisions in a contract for construction shall be against the public policy of this Commonwealth and shall be void and unenforceable:

### (a)	A provision that purports to waive, release, or extinguish the right to resolve disputes through litigation, in court or substantive or procedural rights in connection with such litigation, except that a contract may require binding arbitration as a substitute for litigation or require nonbinding alternative dispute resolution as a prerequisite to litigation;

### (b)	A provision that purports to waive, release, or extinguish rights provided by KRS Chapter 376 with the exception of partial waivers of lien rights provided by the contractor or subcontractor for progress payments; or

### (c)	A provision that purports to waive, release, or extinguish the right of a contractor or subcontractor to recover costs, additional time, or damages, or obtain an equitable adjustment of the contract, for delays that can be shown to affect the critical path of the project if the delay is caused, in whole or in part, by acts or omissions within the control of the contracting entity or person acting on behalf of the contracting entity.

## (3)	Paragraph (c) of subsection (2) of this section shall not render null, void, and unenforceable a contract provision that:

### (a)	Permits a contractor or subcontractor to recover that portion of delay costs caused by acts or omissions of the contracting entity;

### (b)	Requires notice of any delay by the party affected by the delay;

### (c)	Provides for reasonable liquidated damages; or

### (d)	Provides for arbitration or any other procedure designed to settle contract disputes.

## (4)	If a provision of a construction contract is found to be null and unenforceable, that provision shall not affect other provisions of the contract that are in compliance with this section and, to this end, the provisions of the contract are severable.

## (5)	All contracts for construction shall provide that payment of amounts due a contractor from a contracting entity, except retainage, shall be made within thirty (30) days after the contracting entity receives a timely, properly completed, undisputed request for payment.

## (6)	If the contracting entity fails to pay a contractor within thirty (30) days following receipt of a timely, properly completed, undisputed request for payment, the contracting entity shall pay interest to the contractor beginning on the thirty-first day after receipt of the request for payment, computed at the rate of twelve percent (12%) per annum on the undisputed amount due.

## (7)	A contractor shall pay its subcontractors any amounts due within fifteen (15) business days of receipt of payment from the contracting entity, including payment of retainage if retainage is released by the contracting entity, if the subcontractor has provided a timely, properly completed, and undisputed request for payment to the contractor.

## (8)	If a contractor fails to pay a subcontractor within fifteen (15) business days, the contractor shall pay interest to the subcontractor beginning on the sixteenth business day after receipt of payment by the contractor, computed at the rate of twelve percent (12%) per annum on the disputed amount.

## (9)	Subsections (7) and (8) of this section shall apply to all payments from subcontractors to their subcontractors.

# SECTION 3.   A NEW SECTION OF KRS CHAPTER 371 IS CREATED TO READ AS FOLLOWS:

## (1)	Notwithstanding any provision of the Kentucky Revised Statutes to the contrary, until fifty percent (50%) of the construction project has been completed, a contracting entity, contractor, or subcontractor may withhold no more than ten percent (10%) retainage from the amount of any undisputed payment due, and retainage held after fifty-one percent (51%) of the construction project has been completed shall not be more than five percent (5%) of the total contract amount.

## (2)	Within thirty (30) days after substantial completion of a construction project, the contracting entity, contractor, or subcontractor shall release the retainage less an amount equal to one hundred fifty percent (150%) of the reasonably estimated cost of the balance of any contractor's or subcontractor's contractually obligated, yet uncompleted, work remaining. Within fifteen (15) business days after the retainage has been released by the contracting entity to the contractor, the contractor shall release to the subcontractors their proportionate shares of the retainage. For purposes of this subsection, "substantial completion" shall be deemed to have occurred upon the date the certificate of substantial completion is issued;

## (3)	If a contracting entity, contractor, or subcontractor fails to pay retainage, if any, pursuant to the terms of a contract or as required in this section, the contracting entity, contractor, or subcontractor shall pay interest to the contractor or subcontractor to whom payment was due, beginning on the first business day after the payment was due, at the rate of twelve percent (12%) per annum.

# SECTION 4.   A NEW SECTION OF KRS CHAPTER 371 IS CREATED TO READ AS FOLLOWS:

If any undisputed payment is not made by the contracting entity within ten (10) business days after the payment date established in a contract, the contractor and any subcontractors, regardless of tier, upon ten (10) additional business days' written notice to the contracting entity and, in the case of a subcontractor, written notice to the contractor, shall, without prejudice to any other available remedy, be entitled to suspend further performance until payment, including applicable interest, is made. The contract time for each contract affected by the suspension shall be extended appropriately and the contract sum for each affected contract shall be increased by the suspending party's reasonable costs of demobilization, delay, and remobilization.

# SECTION 5.   A NEW SECTION OF KRS CHAPTER 371 IS CREATED TO READ AS FOLLOWS:

In any action to enforce Sections 1 to 7 of this Act, including arbitration, the court or arbitrator shall award costs and reasonable attorney fees to the prevailing party. For public construction contracts, recovery of attorney fees under this section shall be limited to the public contract rate for attorney's fees. Venue of such an action shall be within the Commonwealth of Kentucky.

# SECTION 6.   A NEW SECTION OF KRS CHAPTER 371 IS CREATED TO READ AS FOLLOWS:

## (1)	Sections 1 to 7 of this Act shall be known and may be cited as the Kentucky Fairness in Construction Act.

## (2)	The rights and duties prescribed by Sections 1 to 7 of this Act shall not be waivable or varied under the terms of a contract. The terms of any contract waiving the rights and duties prescribed by Sections 1 to 7 of this Act shall be unenforceable.

## (3)	Notwithstanding any provision of the Kentucky Revised Statutes to the contrary, after a judgment for the contractor against a contracting entity is entered by a court of competent jurisdiction, a contractor has thirty (30) days to file a lien against the property.

# SECTION 7.   A NEW SECTION OF KRS CHAPTER 371 IS CREATED TO READ AS FOLLOWS:

## (1)	Sections 1 to 7 of this Act shall apply to public construction and public works projects, and to private construction, excluding residential construction.

## (2)	Sections 1 to 7 of this Act shall apply to construction contracts entered into after the effective date of Sections 1 to 7 of this Act.

## (3)	Sections 1 to 7 of this Act shall not apply to contracts entered into by a borrower of funds that are provided, insured, or guaranteed by the United States Department of Agriculture's Rural Utilities Service, or financed under a lien accommodation by the Rural Utilities Service.

# Section 8.   KRS 371.160 is amended to read as follows:

## (1)	If, in any contract in the amount of five hundred thousand dollars ($500,000) or more involving the improvement of real estate, a certain amount or percentage of the contract is held back by the owner, that retained amount shall be deposited in a separate escrow account with a bank or trust company authorized to do business in the Commonwealth of Kentucky.

## (2)	As of the time of the deposit of the retained funds, they shall become the sole and separate property of the contractor to whom they are owed.

## (3)	The escrow agent shall promptly invest all escrowed principal in obligations selected by the escrow agent in its discretion.

## (4)	Upon satisfactory completion of the contract, to be evidenced by a written release by the owner, all funds accumulated in the escrow account, together with any interest thereon, shall be paid immediately to the contractor to whom it is owed.

## (5)	The escrow agent shall be compensated for its services in an amount agreed to by the owner, contractor, and escrow agent. The compensation shall be a commercially reasonable fee commensurate with fees being charged for handling of escrow accounts of similar size and duration. The compensation shall be paid from the escrow account.

## (6)	In the event the owner fails or refuses to execute the release provided for in subsection (4) of this section, then the contractor shall have a cause of action against the owner in a court of proper jurisdiction.

## [(7)	This section shall not apply to contracts with the Commonwealth, any county, charter county, urban-county government, or municipality, or any other political subdivision, agency, or instrumentality of the Commonwealth, or school boards.]

# Section 9.   KRS 45A.245 is amended to read as follows:

## (1)	Any person, firm or corporation, having a lawfully authorized written contract with the Commonwealth at the time of or after June 21, 1974, may bring an action against the Commonwealth on the contract, including but not limited to actions either for breach of contracts or for enforcement of contracts or for both. Notwithstanding KRS Chapter 13B, any such action shall be brought in the Franklin Circuit Court and shall be tried by the court sitting without a jury. All defenses in law or equity, except the defense of governmental immunity, shall be preserved to the Commonwealth.

## (2)	If damages awarded on any contract claim under this section exceed the original amount of the contract, such excess shall be limited to an amount which is equal to the amount of the original contract.